## March 2026
No | Filled By | Date | Company | Name Surname | Column1 | Designation | Man/Equ | Category | Area | Reference | Item Tag | Shift | Manhours | Main Activity | Sub Act | Sub-Sub Act | Note | JSA LOCATION
1 | Ebin | 2026-03-01 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Dismantling | DBD Bld | Day | 8 | Steel Structure Works | Dismantling | Dismantling | _
2 | Ebin | 2026-03-01 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 5 | Electrical Works | Electrical Works | Dismantling | _
3 | Ebin | 2026-03-01 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 8 | Steel Structure Works | Dismantling | Dismantling | _
4 | Ebin | 2026-03-01 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 5 | Steel Structure Works | Dismantling | Dismantling | _
5 | Ebin | 2026-03-01 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 8 | Steel Structure Works | Dismantling | Dismantling | _
6 | Ebin | 2026-03-01 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 8 | Steel Structure Works | Dismantling | Dismantling | _
7 | Ebin | 2026-03-01 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 8 | Steel Structure Works | Dismantling | Dismantling | _
8 | Ebin | 2026-03-01 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 8 | Steel Structure Works | Dismantling | Dismantling | _ | Parking Area
9 | Ebin | 2026-03-01 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Dismantling | DBD Bld | Day | 5 | Steel Structure Works | Dismantling | Dismantling | _
10 | Ebin | 2026-03-01 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 8 | Steel Structure Works | Dismantling | Dismantling | _
11 | Ebin | 2026-03-01 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
12 | Ebin | 2026-03-01 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 8 | Steel Structure Works | Dismantling | Dismantling | _ | YARD 3
13 | Ebin | 2026-03-01 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Day | 5 | Steel Structure Works | Dismantling | Dismantling | _
14 | Ebin | 2026-03-01 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
15 | Ebin | 2026-03-01 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 150T crawler crane handed over to Bashaer Projects for their own work for the day
16 | Ebin | 2026-03-01 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
17 | Ebin | 2026-03-01 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 8 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | No usage
18 | Ebin | 2026-03-01 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
18 | Ebin | 2026-03-01 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
19 | Ebin | 2026-03-01 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
20 | Ebin | 2026-03-01 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation | YARD 3
21 | Ebin | 2026-03-01 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation | YARD 3
22 | Ebin | 2026-03-01 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
23 | Ebin | 2026-03-01 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
23 | Ebin | 2026-03-01 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
24 | Ebin | 2026-03-01 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
25 | Ebin | 2026-03-01 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
26 | Ebin | 2026-03-01 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
27 | Ebin | 2026-03-01 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 6 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
28 | Ebin | 2026-03-01 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
29 | Ebin | 2026-03-01 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
30 | Ebin | 2026-03-01 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
31 | Ebin | 2026-03-01 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
32 | Ebin | 2026-03-01 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
33 | Ebin | 2026-03-01 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
34 | Ebin | 2026-03-01 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
35 | Ebin | 2026-03-01 | Encogroup | Arunkumar Surendran | 127859069 | QC Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
35 | Ebin | 2026-03-01 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 3 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
35 | Ebin | 2026-03-01 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 3 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
35 | Ebin | 2026-03-01 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
36 | Tamil | 2026-03-01 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Pre-assembly of Tower- 03
37 | Tamil | 2026-03-01 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Torque tightening | Bolt Torquing of Tower- 05
38 | Tamil | 2026-03-01 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Pre-assembly of Tower- 03
39 | Tamil | 2026-03-01 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 8 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Alignment of tower 6
40 | Tamil | 2026-03-01 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 6 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | _
41 | Tamil | 2026-03-01 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-7 | TR-1010-26 | Day | 8 | Painting Coating | Surface cleaning | Surface cleaning | Painting touch-up- tower 7&columns
42 | Tamil | 2026-03-01 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
43 | Tamil | 2026-03-01 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
44 | Tamil | 2026-03-01 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
45 | Tamil | 2026-03-01 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 8 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Alignment of tower 6 | YARD 3
46 | Tamil | 2026-03-01 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
47 | Tamil | 2026-03-01 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
48 | Tamil | 2026-03-01 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Steel Structure Works | Steel Structure Works | Pre-assembly of Tower- 03
49 | Tamil | 2026-03-01 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 6 | Steel Structure Works | Steel Structure Works | Steel Structure Works | Pre-assembly of Tower- 03, bolt torquing of tower 5, painting touch up
50 | Tamil | 2026-03-01 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Steel Structure Works | Steel Structure Works | Pre-assembly of Tower- 03
51 | Tamil | 2026-03-01 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Steel Structure Works | Steel Structure Works | Pre-assembly of Tower- 03, bolt torquing of tower 5, painting touch up
52 | Tamil | 2026-03-01 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 8 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Alignment of tower 6
53 | Tamil | 2026-03-01 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
54 | Tamil | 2026-03-01 | Encogroup | Mathan Kumar | 140796986 | Mechanical QC | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
54 | Tamil | 2026-03-01 | Encogroup | Bittu Kumar | 140844604 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
55 | Tamil | 2026-03-01 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
56 | Tamil | 2026-03-01 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
57 | Tamil | 2026-03-01 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
58 | Tamil | 2026-03-01 | Encogroup | Sanjay Kumar Suresh Ram | 141365037 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
59 | Tamil | 2026-03-01 | Encogroup | Suresh Selvam | 141377709 | Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
60 | Tamil | 2026-03-01 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing Tower- 05
61 | Tamil | 2026-03-01 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
62 | Tamil | 2026-03-01 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03
63 | Tamil | 2026-03-01 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Storekeeper | TR-1010-26 | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | StoreKeeper
64 | Tamil | 2026-03-01 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03
65 | Tamil | 2026-03-01 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03
66 | Tamil | 2026-03-01 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03, bolt torquing of tower 5, painting touch up
67 | Tamil | 2026-03-01 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
68 | Tamil | 2026-03-01 | Encogroup | Mustafa Moosa Ahned Al Balushi | 18114443 | Driver | Manpower | Manpower | Common Area | Tower-5&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
68 | Tamil | 2026-03-01 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03, bolt torquing of tower 5, painting touch up
69 | Tamil | 2026-03-01 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
69 | Tamil | 2026-03-01 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 8 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
70 | Shijo | 2026-03-01 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
71 | Shijo | 2026-03-01 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
71 | Shijo | 2026-03-01 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 8 |  |  |  | 130T crawler crane dis-mantling started
72 | Shijo | 2026-03-01 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
73 | Shijo | 2026-03-01 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material Handling | Material Handling | _
74 | Shijo | 2026-03-01 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 6 |  |  |  | 150T crawler crane dis-mantling completed
75 | Shijo | 2026-03-01 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
76 | Shijo | 2026-03-01 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
77 | Shijo | 2026-03-01 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 |  |  |  | _
78 | Shijo | 2026-03-01 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 8 |  |  |  | _
79 | Shijo | 2026-03-01 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
80 | Shijo | 2026-03-01 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material unloading by crane | Material unloading by crane | Material unloading by crane | Dis-assembly of crane-150T crawler
81 | Shijo | 2026-03-01 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 6 | Material unloading by crane | Material unloading by crane | Material unloading by crane | Dis-assembly of crane-150T crawler
82 | Shijo | 2026-03-01 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material unloading by crane | Material unloading by crane | Material unloading by crane | Dis-assembly of crane-150T crawler
82 | Shijo | 2026-03-01 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
83 | Shijo | 2026-03-01 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
84 | Shijo | 2026-03-01 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
84 | Shijo | 2026-03-01 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
85 | Shijo | 2026-03-01 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
86 | Shijo | 2026-03-01 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _ | parking area
87 | Shijo | 2026-03-01 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
88 | Shijo | 2026-03-01 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
89 | Shijo | 2026-03-01 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
90 | Shijo | 2026-03-01 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
91 | Shijo | 2026-03-01 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
92 | Shijo | 2026-03-01 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver | parking area
93 | Shijo | 2026-03-01 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
94 | Shijo | 2026-03-01 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
95 | Shijo | 2026-03-01 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
96 | Shijo | 2026-03-01 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
97 | Shijo | 2026-03-01 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
98 | Shijo | 2026-03-01 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
99 | Shijo | 2026-03-01 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works | YARD 3
100 | Shijo | 2026-03-01 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
101 | Shijo | 2026-03-01 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
102 | Shijo | 2026-03-01 | AL Omar International TRAD AND CONT | Mohammad Shahadat Hossain Sikdar | 95335424 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
103 | Shijo | 2026-03-01 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
104 | Shijo | 2026-03-01 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
105 | Shijo | 2026-03-01 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator | parking area
106 | Shijo | 2026-03-01 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
107 | Shijo | 2026-03-01 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
108 | Shijo | 2026-03-01 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
109 | Shijo | 2026-03-01 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
110 | Shijo | 2026-03-01 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
111 | Shijo | 2026-03-01 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
112 | Shijo | 2026-03-01 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
113 | Shijo | 2026-03-01 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
114 | Shijo | 2026-03-01 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Mobilization Preparation | Mobilization Preparation | Mobilization Preparation | _ | YARD 3
115 | Shijo | 2026-03-01 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
116 | Shijo | 2026-03-01 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Electrical Works | Electrical Works | Electrical Works | TSF works
117 | Shijo | 2026-03-01 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
118 | Shijo | 2026-03-01 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
119 | Shijo | 2026-03-01 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
120 | Shijo | 2026-03-01 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
121 | Shijo | 2026-03-01 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
122 | Shijo | 2026-03-01 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
123 | Shijo | 2026-03-01 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 8 |  |  |  | 130T crawler crane dis-mantling started
124 | Shijo | 2026-03-01 | Sarens Nass | Rampratap Chauhan | 112346941 | Rigger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | 130T crawler crane dis-mantling started
124 | Shijo | 2026-03-01 | Sarens Nass | Padmanaban Sevu | 77873529 | Mechanic | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | 130T crawler crane dis-mantling started
124 | Shijo | 2026-03-01 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
125 | Shijo | 2026-03-01 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Electrical Works | Electrical Works | Electrical Works | TSF works
126 | Shijo | 2026-03-01 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 8 |  |  |  | No usage
127 | Shijo | 2026-03-01 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 8 |  |  |  | No usage
128 | Shijo | 2026-03-01 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
129 | Shijo | 2026-03-01 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 150T crawler crane dis-mantling works
130 | Shijo | 2026-03-01 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
131 | Shijo | 2026-03-01 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
132 | Shijo | 2026-03-01 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Dis-assembly of crane-150T crawler
133 | Shijo | 2026-03-01 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | YARD 3
134 | Ebin | 2026-03-02 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
135 | Ebin | 2026-03-02 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
136 | Ebin | 2026-03-02 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
137 | Ebin | 2026-03-02 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
138 | Ebin | 2026-03-02 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
139 | Ebin | 2026-03-02 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
140 | Ebin | 2026-03-02 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
141 | Ebin | 2026-03-02 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
142 | Ebin | 2026-03-02 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
143 | Ebin | 2026-03-02 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
144 | Ebin | 2026-03-02 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
145 | Ebin | 2026-03-02 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
146 | Ebin | 2026-03-02 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
147 | Ebin | 2026-03-02 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
148 | Ebin | 2026-03-02 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
149 | Ebin | 2026-03-02 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
150 | Ebin | 2026-03-02 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
151 | Ebin | 2026-03-02 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
152 | Ebin | 2026-03-02 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
153 | Ebin | 2026-03-02 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
154 | Ebin | 2026-03-02 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
155 | Ebin | 2026-03-02 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
156 | Ebin | 2026-03-02 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
156 | Ebin | 2026-03-02 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
157 | Ebin | 2026-03-02 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
158 | Ebin | 2026-03-02 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
159 | Ebin | 2026-03-02 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
160 | Ebin | 2026-03-02 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
161 | Ebin | 2026-03-02 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
162 | Ebin | 2026-03-02 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
163 | Ebin | 2026-03-02 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
164 | Ebin | 2026-03-02 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
165 | Ebin | 2026-03-02 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
166 | Ebin | 2026-03-02 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
167 | Ebin | 2026-03-02 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
168 | Ebin | 2026-03-02 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
169 | Tamil | 2026-03-02 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
170 | Tamil | 2026-03-02 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
171 | Tamil | 2026-03-02 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
172 | Tamil | 2026-03-02 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
173 | Tamil | 2026-03-02 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
174 | Tamil | 2026-03-02 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
175 | Tamil | 2026-03-02 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
176 | Tamil | 2026-03-02 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
177 | Tamil | 2026-03-02 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
178 | Tamil | 2026-03-02 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
179 | Tamil | 2026-03-02 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
180 | Tamil | 2026-03-02 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
181 | Tamil | 2026-03-02 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
182 | Tamil | 2026-03-02 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
183 | Tamil | 2026-03-02 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
184 | Tamil | 2026-03-02 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
185 | Tamil | 2026-03-02 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
186 | Tamil | 2026-03-02 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 8 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
187 | Tamil | 2026-03-02 | Encogroup | Bittu Kumar | 140844604 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
188 | Tamil | 2026-03-02 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
189 | Tamil | 2026-03-02 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
190 | Tamil | 2026-03-02 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
191 | Tamil | 2026-03-02 | Encogroup | Sanjay Kumar Suresh Ram | 141365037 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
192 | Tamil | 2026-03-02 | Encogroup | Suresh Selvam | 141377709 | Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
193 | Tamil | 2026-03-02 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
194 | Tamil | 2026-03-02 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
195 | Tamil | 2026-03-02 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
196 | Tamil | 2026-03-02 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Storekeeper | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
197 | Tamil | 2026-03-02 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
198 | Tamil | 2026-03-02 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
199 | Tamil | 2026-03-02 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
200 | Tamil | 2026-03-02 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
201 | Tamil | 2026-03-02 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
202 | Tamil | 2026-03-02 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
202 | Tamil | 2026-03-02 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
203 | Shijo | 2026-03-02 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
204 | Shijo | 2026-03-02 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
204 | Shijo | 2026-03-02 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
205 | Shijo | 2026-03-02 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
206 | Shijo | 2026-03-02 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
207 | Shijo | 2026-03-02 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
208 | Shijo | 2026-03-02 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
209 | Shijo | 2026-03-02 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
210 | Shijo | 2026-03-02 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
211 | Shijo | 2026-03-02 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
212 | Shijo | 2026-03-02 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
213 | Shijo | 2026-03-02 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
214 | Shijo | 2026-03-02 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
215 | Shijo | 2026-03-02 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
216 | Shijo | 2026-03-02 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
217 | Shijo | 2026-03-02 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
218 | Shijo | 2026-03-02 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
219 | Shijo | 2026-03-02 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
220 | Shijo | 2026-03-02 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
221 | Shijo | 2026-03-02 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
222 | Shijo | 2026-03-02 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
223 | Shijo | 2026-03-02 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
224 | Shijo | 2026-03-02 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
225 | Shijo | 2026-03-02 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
226 | Shijo | 2026-03-02 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
227 | Shijo | 2026-03-02 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
228 | Shijo | 2026-03-02 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
229 | Shijo | 2026-03-02 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
230 | Shijo | 2026-03-02 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
231 | Shijo | 2026-03-02 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
232 | Shijo | 2026-03-02 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
233 | Shijo | 2026-03-02 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
234 | Shijo | 2026-03-02 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
235 | Shijo | 2026-03-02 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
236 | Shijo | 2026-03-02 | AL Omar International TRAD AND CONT | Mohammad Shahadat Hossain Sikdar | 95335424 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
237 | Shijo | 2026-03-02 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
238 | Shijo | 2026-03-02 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
239 | Shijo | 2026-03-02 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
240 | Shijo | 2026-03-02 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
241 | Shijo | 2026-03-02 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
242 | Shijo | 2026-03-02 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
243 | Shijo | 2026-03-02 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
244 | Shijo | 2026-03-02 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
245 | Shijo | 2026-03-02 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
246 | Shijo | 2026-03-02 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
247 | Shijo | 2026-03-02 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
248 | Shijo | 2026-03-02 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
249 | Shijo | 2026-03-02 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
250 | Shijo | 2026-03-02 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
251 | Shijo | 2026-03-02 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
252 | Shijo | 2026-03-02 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
253 | Shijo | 2026-03-02 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
254 | Shijo | 2026-03-02 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
255 | Shijo | 2026-03-02 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
256 | Shijo | 2026-03-02 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
257 | Shijo | 2026-03-02 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
258 | Shijo | 2026-03-02 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
259 | Shijo | 2026-03-02 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
260 | Shijo | 2026-03-02 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
261 | Shijo | 2026-03-02 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
262 | Shijo | 2026-03-02 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
263 | Shijo | 2026-03-02 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
264 | Shijo | 2026-03-02 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
265 | Shijo | 2026-03-02 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
266 | Shijo | 2026-03-02 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
267 | Shijo | 2026-03-02 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
268 | Ebin | 2026-03-03 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
269 | Ebin | 2026-03-03 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
270 | Ebin | 2026-03-03 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
271 | Ebin | 2026-03-03 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
272 | Ebin | 2026-03-03 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
273 | Ebin | 2026-03-03 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
274 | Ebin | 2026-03-03 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
275 | Ebin | 2026-03-03 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
276 | Ebin | 2026-03-03 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
277 | Ebin | 2026-03-03 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
278 | Ebin | 2026-03-03 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
279 | Ebin | 2026-03-03 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
280 | Ebin | 2026-03-03 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
281 | Ebin | 2026-03-03 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
282 | Ebin | 2026-03-03 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
283 | Ebin | 2026-03-03 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
284 | Ebin | 2026-03-03 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
285 | Ebin | 2026-03-03 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
286 | Ebin | 2026-03-03 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
287 | Ebin | 2026-03-03 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
288 | Ebin | 2026-03-03 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
289 | Ebin | 2026-03-03 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
290 | Ebin | 2026-03-03 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
290 | Ebin | 2026-03-03 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
291 | Ebin | 2026-03-03 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
292 | Ebin | 2026-03-03 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
293 | Ebin | 2026-03-03 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
294 | Ebin | 2026-03-03 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
295 | Ebin | 2026-03-03 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
296 | Ebin | 2026-03-03 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
297 | Ebin | 2026-03-03 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
298 | Ebin | 2026-03-03 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
299 | Ebin | 2026-03-03 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
300 | Ebin | 2026-03-03 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
301 | Tamil | 2026-03-03 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
302 | Tamil | 2026-03-03 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
303 | Tamil | 2026-03-03 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
304 | Tamil | 2026-03-03 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
305 | Tamil | 2026-03-03 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
306 | Tamil | 2026-03-03 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
307 | Tamil | 2026-03-03 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
308 | Tamil | 2026-03-03 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
309 | Tamil | 2026-03-03 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
310 | Tamil | 2026-03-03 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
311 | Tamil | 2026-03-03 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
312 | Tamil | 2026-03-03 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
313 | Tamil | 2026-03-03 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
314 | Tamil | 2026-03-03 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
315 | Tamil | 2026-03-03 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
316 | Tamil | 2026-03-03 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
317 | Tamil | 2026-03-03 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
318 | Tamil | 2026-03-03 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
319 | Tamil | 2026-03-03 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
320 | Tamil | 2026-03-03 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 8 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
321 | Tamil | 2026-03-03 | Encogroup | Bittu Kumar | 140844604 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
322 | Tamil | 2026-03-03 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
323 | Tamil | 2026-03-03 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
324 | Tamil | 2026-03-03 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
325 | Tamil | 2026-03-03 | Encogroup | Sanjay Kumar Suresh Ram | 141365037 | Painter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
326 | Tamil | 2026-03-03 | Encogroup | Suresh Selvam | 141377709 | Helper | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
327 | Tamil | 2026-03-03 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
328 | Tamil | 2026-03-03 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Storekeeper | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
329 | Tamil | 2026-03-03 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
330 | Tamil | 2026-03-03 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
331 | Tamil | 2026-03-03 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
332 | Tamil | 2026-03-03 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
333 | Tamil | 2026-03-03 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
334 | Tamil | 2026-03-03 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
334 | Tamil | 2026-03-03 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
335 | Shijo | 2026-03-03 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
336 | Shijo | 2026-03-03 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
337 | Shijo | 2026-03-03 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
337 | Shijo | 2026-03-03 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
338 | Shijo | 2026-03-03 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
339 | Shijo | 2026-03-03 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
340 | Shijo | 2026-03-03 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
341 | Shijo | 2026-03-03 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
342 | Shijo | 2026-03-03 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
343 | Shijo | 2026-03-03 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Site Office | _ | _ | Day | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
344 | Shijo | 2026-03-03 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
345 | Shijo | 2026-03-03 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
346 | Shijo | 2026-03-03 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
347 | Shijo | 2026-03-03 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
348 | Shijo | 2026-03-03 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
349 | Shijo | 2026-03-03 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
350 | Shijo | 2026-03-03 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
351 | Shijo | 2026-03-03 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
352 | Shijo | 2026-03-03 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
353 | Shijo | 2026-03-03 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
354 | Shijo | 2026-03-03 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
355 | Shijo | 2026-03-03 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
356 | Shijo | 2026-03-03 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
357 | Shijo | 2026-03-03 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
358 | Shijo | 2026-03-03 |  | HIAB | #N/A |  |  |  | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
359 | Shijo | 2026-03-03 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
360 | Shijo | 2026-03-03 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
361 | Shijo | 2026-03-03 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
362 | Shijo | 2026-03-03 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
363 | Shijo | 2026-03-03 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
364 | Shijo | 2026-03-03 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
365 | Shijo | 2026-03-03 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
366 | Shijo | 2026-03-03 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
367 | Shijo | 2026-03-03 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
368 | Shijo | 2026-03-03 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
369 | Shijo | 2026-03-03 | AL Omar International TRAD AND CONT | Mohammad Shahadat Hossain Sikdar | 95335424 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
370 | Shijo | 2026-03-03 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
371 | Shijo | 2026-03-03 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
372 | Shijo | 2026-03-03 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
373 | Shijo | 2026-03-03 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
374 | Shijo | 2026-03-03 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
375 | Shijo | 2026-03-03 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
376 | Shijo | 2026-03-03 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
377 | Shijo | 2026-03-03 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
378 | Shijo | 2026-03-03 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
379 | Shijo | 2026-03-03 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
380 | Shijo | 2026-03-03 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
381 | Shijo | 2026-03-03 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
382 | Shijo | 2026-03-03 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
383 | Shijo | 2026-03-03 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
384 | Shijo | 2026-03-03 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
385 | Shijo | 2026-03-03 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
386 | Shijo | 2026-03-03 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
387 | Shijo | 2026-03-03 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
388 | Shijo | 2026-03-03 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
389 | Shijo | 2026-03-03 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
390 | Shijo | 2026-03-03 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
391 | Shijo | 2026-03-03 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
392 | Shijo | 2026-03-03 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
393 | Shijo | 2026-03-03 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
394 | Shijo | 2026-03-03 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
395 | Shijo | 2026-03-03 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
396 | Shijo | 2026-03-03 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
397 | Shijo | 2026-03-03 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
398 | Shijo | 2026-03-03 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
399 | Shijo | 2026-03-03 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
400 | Shijo | 2026-03-03 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
401 | Ebin | 2026-03-04 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment |  |  |  | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
402 | Ebin | 2026-03-04 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
403 | Ebin | 2026-03-04 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
404 | Ebin | 2026-03-04 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
405 | Ebin | 2026-03-04 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
406 | Ebin | 2026-03-04 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
407 | Ebin | 2026-03-04 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
408 | Ebin | 2026-03-04 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
409 | Ebin | 2026-03-04 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
410 | Ebin | 2026-03-04 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
411 | Ebin | 2026-03-04 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
412 | Ebin | 2026-03-04 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
413 | Ebin | 2026-03-04 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
414 | Ebin | 2026-03-04 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
415 | Ebin | 2026-03-04 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
416 | Ebin | 2026-03-04 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
417 | Ebin | 2026-03-04 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
418 | Ebin | 2026-03-04 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
419 | Ebin | 2026-03-04 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
420 | Ebin | 2026-03-04 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
421 | Ebin | 2026-03-04 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
422 | Ebin | 2026-03-04 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
423 | Ebin | 2026-03-04 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
423 | Ebin | 2026-03-04 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
424 | Ebin | 2026-03-04 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
425 | Ebin | 2026-03-04 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
426 | Ebin | 2026-03-04 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
427 | Ebin | 2026-03-04 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
428 | Ebin | 2026-03-04 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
429 | Ebin | 2026-03-04 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
430 | Ebin | 2026-03-04 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
431 | Ebin | 2026-03-04 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
432 | Ebin | 2026-03-04 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
433 | Ebin | 2026-03-04 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
434 | Ebin | 2026-03-04 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
435 | Ebin | 2026-03-04 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
436 | Tamil | 2026-03-03 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
436 | Tamil | 2026-03-04 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
437 | Tamil | 2026-03-04 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
438 | Tamil | 2026-03-04 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
439 | Tamil | 2026-03-04 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
440 | Tamil | 2026-03-04 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
441 | Tamil | 2026-03-04 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
442 | Tamil | 2026-03-04 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
443 | Tamil | 2026-03-04 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
444 | Tamil | 2026-03-04 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
445 | Tamil | 2026-03-04 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
446 | Tamil | 2026-03-04 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
447 | Tamil | 2026-03-04 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
448 | Tamil | 2026-03-04 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
449 | Tamil | 2026-03-04 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
450 | Tamil | 2026-03-04 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
451 | Tamil | 2026-03-04 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
452 | Tamil | 2026-03-04 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
453 | Tamil | 2026-03-04 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
454 | Tamil | 2026-03-04 | Encogroup | Bittu Kumar | 140844604 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
455 | Tamil | 2026-03-04 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
456 | Tamil | 2026-03-04 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
457 | Tamil | 2026-03-04 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region. | LAYDOWN
458 | Tamil | 2026-03-04 | Encogroup | Sanjay Kumar Suresh Ram | 141365037 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
459 | Tamil | 2026-03-04 | Encogroup | Suresh Selvam | 141377709 | Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
460 | Tamil | 2026-03-04 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
461 | Tamil | 2026-03-04 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
462 | Tamil | 2026-03-04 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
463 | Tamil | 2026-03-04 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Storekeeper | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
464 | Tamil | 2026-03-04 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
465 | Tamil | 2026-03-04 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
466 | Tamil | 2026-03-04 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
467 | Tamil | 2026-03-04 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
468 | Tamil | 2026-03-04 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
469 | Tamil | 2026-03-04 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
469 | Tamil | 2026-03-04 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
470 | Shijo | 2026-03-04 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
471 | Shijo | 2026-03-04 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
471 | Shijo | 2026-03-04 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
472 | Shijo | 2026-03-04 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
473 | Shijo | 2026-03-04 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
474 | Shijo | 2026-03-04 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
475 | Shijo | 2026-03-04 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
476 | Shijo | 2026-03-04 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
477 | Shijo | 2026-03-04 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
478 | Shijo | 2026-03-04 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
479 | Shijo | 2026-03-04 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
480 | Shijo | 2026-03-04 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
481 | Shijo | 2026-03-04 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
482 | Shijo | 2026-03-04 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
483 | Shijo | 2026-03-04 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
484 | Shijo | 2026-03-04 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
485 | Shijo | 2026-03-04 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
486 | Shijo | 2026-03-04 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
487 | Shijo | 2026-03-04 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
488 | Shijo | 2026-03-04 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
489 | Shijo | 2026-03-04 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
490 | Shijo | 2026-03-04 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
491 | Shijo | 2026-03-04 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
492 | Shijo | 2026-03-04 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
493 | Shijo | 2026-03-04 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
494 | Shijo | 2026-03-04 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
495 | Shijo | 2026-03-04 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
496 | Shijo | 2026-03-04 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
497 | Shijo | 2026-03-04 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
498 | Shijo | 2026-03-04 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
499 | Shijo | 2026-03-04 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
500 | Shijo | 2026-03-04 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
501 | Shijo | 2026-03-04 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
502 | Shijo | 2026-03-04 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
503 | Shijo | 2026-03-04 | AL Omar International TRAD AND CONT | Mohammad Shahadat Hossain Sikdar | 95335424 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
504 | Shijo | 2026-03-04 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
505 | Shijo | 2026-03-04 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
506 | Shijo | 2026-03-04 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
507 | Shijo | 2026-03-04 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
508 | Shijo | 2026-03-04 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
509 | Shijo | 2026-03-04 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
510 | Shijo | 2026-03-04 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
511 | Shijo | 2026-03-04 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
512 | Shijo | 2026-03-04 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
513 | Shijo | 2026-03-04 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
514 | Shijo | 2026-03-04 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
515 | Shijo | 2026-03-04 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
516 | Shijo | 2026-03-04 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
517 | Shijo | 2026-03-04 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
518 | Shijo | 2026-03-04 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
519 | Shijo | 2026-03-04 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
520 | Shijo | 2026-03-04 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
521 | Shijo | 2026-03-04 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
522 | Shijo | 2026-03-04 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
523 | Shijo | 2026-03-04 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
524 | Shijo | 2026-03-04 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
525 | Shijo | 2026-03-04 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
525 | Shijo | 2026-03-04 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
526 | Shijo | 2026-03-04 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
527 | Shijo | 2026-03-04 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
528 | Shijo | 2026-03-04 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
529 | Shijo | 2026-03-04 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
530 | Shijo | 2026-03-04 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
531 | Shijo | 2026-03-04 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
532 | Shijo | 2026-03-04 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
533 | Shijo | 2026-03-04 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
534 | Shijo | 2026-03-04 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
535 | Ebin | 2026-03-05 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
536 | Ebin | 2026-03-05 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
537 | Ebin | 2026-03-05 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
538 | Ebin | 2026-03-05 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
539 | Ebin | 2026-03-05 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
540 | Ebin | 2026-03-05 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
541 | Ebin | 2026-03-05 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
542 | Ebin | 2026-03-05 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
543 | Ebin | 2026-03-05 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
544 | Ebin | 2026-03-05 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
545 | Ebin | 2026-03-05 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
546 | Ebin | 2026-03-05 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
547 | Ebin | 2026-03-05 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
548 | Ebin | 2026-03-05 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
549 | Ebin | 2026-03-05 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
550 | Ebin | 2026-03-05 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
551 | Ebin | 2026-03-05 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
552 | Ebin | 2026-03-05 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
553 | Ebin | 2026-03-05 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
554 | Ebin | 2026-03-05 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
555 | Ebin | 2026-03-05 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
556 | Ebin | 2026-03-05 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
557 | Ebin | 2026-03-05 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
557 | Ebin | 2026-03-05 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
558 | Ebin | 2026-03-05 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
559 | Ebin | 2026-03-05 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
560 | Ebin | 2026-03-05 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
561 | Ebin | 2026-03-05 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
562 | Ebin | 2026-03-05 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
563 | Ebin | 2026-03-05 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
564 | Ebin | 2026-03-05 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
565 | Ebin | 2026-03-05 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
566 | Ebin | 2026-03-05 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
567 | Ebin | 2026-03-05 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
568 | Ebin | 2026-03-05 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
569 | Ebin | 2026-03-05 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
570 | Tamil | 2026-03-05 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
571 | Tamil | 2026-03-05 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
572 | Tamil | 2026-03-05 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
573 | Tamil | 2026-03-05 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
574 | Tamil | 2026-03-05 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
575 | Tamil | 2026-03-05 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
576 | Tamil | 2026-03-05 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
577 | Tamil | 2026-03-05 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
578 | Tamil | 2026-03-05 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
579 | Tamil | 2026-03-05 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
580 | Tamil | 2026-03-05 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
581 | Tamil | 2026-03-05 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
582 | Tamil | 2026-03-05 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
583 | Tamil | 2026-03-05 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
584 | Tamil | 2026-03-05 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
585 | Tamil | 2026-03-05 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
586 | Tamil | 2026-03-05 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
587 | Tamil | 2026-03-05 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
588 | Tamil | 2026-03-05 | Encogroup | Bittu Kumar | 140844604 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
589 | Tamil | 2026-03-05 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
590 | Tamil | 2026-03-05 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
591 | Tamil | 2026-03-05 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
592 | Tamil | 2026-03-05 | Encogroup | Sanjay Kumar Suresh Ram | 141365037 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
593 | Tamil | 2026-03-05 | Encogroup | Suresh Selvam | 141377709 | Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
594 | Tamil | 2026-03-05 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
595 | Tamil | 2026-03-05 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
596 | Tamil | 2026-03-05 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
597 | Tamil | 2026-03-05 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Storekeeper | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
598 | Tamil | 2026-03-05 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
599 | Tamil | 2026-03-05 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
600 | Tamil | 2026-03-05 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
601 | Tamil | 2026-03-05 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
602 | Tamil | 2026-03-05 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
603 | Tamil | 2026-03-05 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
603 | Tamil | 2026-03-05 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
604 | Shijo | 2026-03-05 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
605 | Shijo | 2026-03-05 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
605 | Shijo | 2026-03-05 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
606 | Shijo | 2026-03-05 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
607 | Shijo | 2026-03-05 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
608 | Shijo | 2026-03-05 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
609 | Shijo | 2026-03-05 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
610 | Shijo | 2026-03-05 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
611 | Shijo | 2026-03-05 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
612 | Shijo | 2026-03-05 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
613 | Shijo | 2026-03-05 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
614 | Shijo | 2026-03-05 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
615 | Shijo | 2026-03-05 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
616 | Shijo | 2026-03-05 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
617 | Shijo | 2026-03-05 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
618 | Shijo | 2026-03-05 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
619 | Shijo | 2026-03-05 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
620 | Shijo | 2026-03-05 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
621 | Shijo | 2026-03-05 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
622 | Shijo | 2026-03-05 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
623 | Shijo | 2026-03-05 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
624 | Shijo | 2026-03-05 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
625 | Shijo | 2026-03-05 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
626 | Shijo | 2026-03-05 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
627 | Shijo | 2026-03-05 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
628 | Shijo | 2026-03-05 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
629 | Shijo | 2026-03-05 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
630 | Shijo | 2026-03-05 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
631 | Shijo | 2026-03-05 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
632 | Shijo | 2026-03-05 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
633 | Shijo | 2026-03-05 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
634 | Shijo | 2026-03-05 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
635 | Shijo | 2026-03-05 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
636 | Shijo | 2026-03-05 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
637 | Shijo | 2026-03-05 | AL Omar International TRAD AND CONT | Mohammad Shahadat Hossain Sikdar | 95335424 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
638 | Shijo | 2026-03-05 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
639 | Shijo | 2026-03-05 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
640 | Shijo | 2026-03-05 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
641 | Shijo | 2026-03-05 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
642 | Shijo | 2026-03-05 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
643 | Shijo | 2026-03-05 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
644 | Shijo | 2026-03-05 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
645 | Shijo | 2026-03-05 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
646 | Shijo | 2026-03-05 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
647 | Shijo | 2026-03-05 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
648 | Shijo | 2026-03-05 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
649 | Shijo | 2026-03-05 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
650 | Shijo | 2026-03-05 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
651 | Shijo | 2026-03-05 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
652 | Shijo | 2026-03-05 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
653 | Shijo | 2026-03-05 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
654 | Shijo | 2026-03-05 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
655 | Shijo | 2026-03-05 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
656 | Shijo | 2026-03-05 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
657 | Shijo | 2026-03-05 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
658 | Shijo | 2026-03-05 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
659 | Shijo | 2026-03-05 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
660 | Shijo | 2026-03-05 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
661 | Shijo | 2026-03-05 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
662 | Shijo | 2026-03-05 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
663 | Shijo | 2026-03-05 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
664 | Shijo | 2026-03-05 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
665 | Shijo | 2026-03-05 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
666 | Shijo | 2026-03-05 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
667 | Shijo | 2026-03-05 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
668 | Shijo | 2026-03-05 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
669 | Ebin | 2026-03-07 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
670 | Ebin | 2026-03-07 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
671 | Ebin | 2026-03-07 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
672 | Ebin | 2026-03-07 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
673 | Ebin | 2026-03-07 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
674 | Ebin | 2026-03-07 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
675 | Ebin | 2026-03-07 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
676 | Ebin | 2026-03-07 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
677 | Ebin | 2026-03-07 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
678 | Ebin | 2026-03-07 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
679 | Ebin | 2026-03-07 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
680 | Ebin | 2026-03-07 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
681 | Ebin | 2026-03-07 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Dismantling | DBD Bld | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
682 | Ebin | 2026-03-07 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
683 | Ebin | 2026-03-07 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
684 | Ebin | 2026-03-07 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
685 | Ebin | 2026-03-07 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
686 | Ebin | 2026-03-07 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
687 | Ebin | 2026-03-07 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
688 | Ebin | 2026-03-07 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
689 | Ebin | 2026-03-07 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
690 | Ebin | 2026-03-07 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
691 | Ebin | 2026-03-07 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
691 | Ebin | 2026-03-07 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
692 | Ebin | 2026-03-07 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
693 | Ebin | 2026-03-07 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
694 | Ebin | 2026-03-07 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
695 | Ebin | 2026-03-07 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
696 | Ebin | 2026-03-07 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
697 | Ebin | 2026-03-07 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
698 | Ebin | 2026-03-07 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
699 | Ebin | 2026-03-07 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
700 | Ebin | 2026-03-07 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
701 | Ebin | 2026-03-07 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
702 | Ebin | 2026-03-07 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
703 | Ebin | 2026-03-07 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
704 | Tamil | 2026-03-07 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
705 | Tamil | 2026-03-07 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
706 | Tamil | 2026-03-07 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
707 | Tamil | 2026-03-07 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
708 | Tamil | 2026-03-07 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
709 | Tamil | 2026-03-07 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
710 | Tamil | 2026-03-07 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
711 | Tamil | 2026-03-07 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
712 | Tamil | 2026-03-07 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
713 | Tamil | 2026-03-07 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
714 | Tamil | 2026-03-07 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
715 | Tamil | 2026-03-07 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
716 | Tamil | 2026-03-07 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
717 | Tamil | 2026-03-07 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
718 | Tamil | 2026-03-07 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
719 | Tamil | 2026-03-07 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
720 | Tamil | 2026-03-07 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
721 | Tamil | 2026-03-07 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
722 | Tamil | 2026-03-07 | Encogroup | Bittu Kumar | 140844604 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
723 | Tamil | 2026-03-07 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
724 | Tamil | 2026-03-07 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
725 | Tamil | 2026-03-07 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 6 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
726 | Tamil | 2026-03-07 | Encogroup | Sanjay Kumar Suresh Ram | 141365037 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
727 | Tamil | 2026-03-07 | Encogroup | Suresh Selvam | 141377709 | Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
728 | Tamil | 2026-03-07 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
729 | Tamil | 2026-03-07 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
730 | Tamil | 2026-03-07 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
731 | Tamil | 2026-03-07 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Storekeeper | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
732 | Tamil | 2026-03-07 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
733 | Tamil | 2026-03-07 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
734 | Tamil | 2026-03-07 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
735 | Tamil | 2026-03-07 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
736 | Tamil | 2026-03-07 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
737 | Tamil | 2026-03-07 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
737 | Tamil | 2026-03-07 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
738 | Shijo | 2026-03-07 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
739 | Shijo | 2026-03-07 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
739 | Shijo | 2026-03-07 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
740 | Shijo | 2026-03-07 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
741 | Shijo | 2026-03-07 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
742 | Shijo | 2026-03-07 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
743 | Shijo | 2026-03-07 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
744 | Shijo | 2026-03-07 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
745 | Shijo | 2026-03-07 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
746 | Shijo | 2026-03-07 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
747 | Shijo | 2026-03-07 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
748 | Shijo | 2026-03-07 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
749 | Shijo | 2026-03-07 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
750 | Shijo | 2026-03-07 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
751 | Shijo | 2026-03-07 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
752 | Shijo | 2026-03-07 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
753 | Shijo | 2026-03-07 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
754 | Shijo | 2026-03-07 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
755 | Shijo | 2026-03-07 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
756 | Shijo | 2026-03-07 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
757 | Shijo | 2026-03-07 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
758 | Shijo | 2026-03-07 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
759 | Shijo | 2026-03-07 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
760 | Shijo | 2026-03-07 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
761 | Shijo | 2026-03-07 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
762 | Shijo | 2026-03-07 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
763 | Shijo | 2026-03-07 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
764 | Shijo | 2026-03-07 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
765 | Shijo | 2026-03-07 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
766 | Shijo | 2026-03-07 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
767 | Shijo | 2026-03-07 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
768 | Shijo | 2026-03-07 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
769 | Shijo | 2026-03-07 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
770 | Shijo | 2026-03-07 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
771 | Shijo | 2026-03-07 | AL Omar International TRAD AND CONT | Mohammad Shahadat Hossain Sikdar | 95335424 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
772 | Shijo | 2026-03-07 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
773 | Shijo | 2026-03-07 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
774 | Shijo | 2026-03-07 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
775 | Shijo | 2026-03-07 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
776 | Shijo | 2026-03-07 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
777 | Shijo | 2026-03-07 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
778 | Shijo | 2026-03-07 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
779 | Shijo | 2026-03-07 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
780 | Shijo | 2026-03-07 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
781 | Shijo | 2026-03-07 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
782 | Shijo | 2026-03-07 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
783 | Shijo | 2026-03-07 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
784 | Shijo | 2026-03-07 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
785 | Shijo | 2026-03-07 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
786 | Shijo | 2026-03-07 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
787 | Shijo | 2026-03-07 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
788 | Shijo | 2026-03-07 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
789 | Shijo | 2026-03-07 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
790 | Shijo | 2026-03-07 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
791 | Shijo | 2026-03-07 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
792 | Shijo | 2026-03-07 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
793 | Shijo | 2026-03-07 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
794 | Shijo | 2026-03-07 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
795 | Shijo | 2026-03-07 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
796 | Shijo | 2026-03-07 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
797 | Shijo | 2026-03-07 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
798 | Shijo | 2026-03-07 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
799 | Shijo | 2026-03-07 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
800 | Shijo | 2026-03-07 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
801 | Shijo | 2026-03-07 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
802 | Shijo | 2026-03-07 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work suspended due to site blockage as per Vale e-mail dated 01 March- "Notification to Contractors for 24th Site Blockage", due to escalating geopolitical tensions in the region.
803 | Ebin | 2026-03-08 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
804 | Ebin | 2026-03-08 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
805 | Ebin | 2026-03-08 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
806 | Ebin | 2026-03-08 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
807 | Ebin | 2026-03-08 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
808 | Ebin | 2026-03-08 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
809 | Ebin | 2026-03-08 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
810 | Ebin | 2026-03-08 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
811 | Ebin | 2026-03-08 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
| Ebin | 2026-03-08 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
812 | Ebin | 2026-03-08 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
813 | Ebin | 2026-03-08 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
814 | Ebin | 2026-03-08 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
815 | Ebin | 2026-03-08 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
816 | Ebin | 2026-03-08 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
817 | Ebin | 2026-03-08 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Structural material segregation, offloading of materials from yard-3 to yard-2, pre-assembly&erection on temporary support installation
818 | Ebin | 2026-03-08 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | No usage
819 | Ebin | 2026-03-08 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
820 | Ebin | 2026-03-08 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
821 | Ebin | 2026-03-08 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
822 | Ebin | 2026-03-08 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
823 | Ebin | 2026-03-08 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _ | YARD 3
824 | Ebin | 2026-03-08 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
825 | Ebin | 2026-03-08 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
825 | Ebin | 2026-03-08 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
826 | Ebin | 2026-03-08 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
827 | Ebin | 2026-03-08 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
828 | Ebin | 2026-03-08 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
829 | Ebin | 2026-03-08 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
830 | Ebin | 2026-03-08 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
831 | Ebin | 2026-03-08 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
832 | Ebin | 2026-03-08 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
833 | Ebin | 2026-03-08 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
834 | Ebin | 2026-03-08 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 3 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
835 | Ebin | 2026-03-08 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
834 | Ebin | 2026-03-08 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
836 | Ebin | 2026-03-08 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
837 | Ebin | 2026-03-08 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
838 | Tamil | 2026-03-08 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Pre-assembly of Tower- 03, Bolt torquing of tower 3
839 | Tamil | 2026-03-08 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
840 | Tamil | 2026-03-08 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Pre-assembly of Tower- 03
841 | Tamil | 2026-03-08 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
842 | Tamil | 2026-03-08 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Tower-5 | TR-1010-26 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
843 | Tamil | 2026-03-08 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 6 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Pre-assembly of Tower- 03, bolt torquing of tower 5, painting touch up
844 | Tamil | 2026-03-08 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-7 | TR-1010-26 | Day | 10 | Painting Coating | Surface cleaning | Surface cleaning | Painting touch-up- tower 7&columns
845 | Tamil | 2026-03-08 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
846 | Tamil | 2026-03-08 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
847 | Tamil | 2026-03-08 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
848 | Tamil | 2026-03-08 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 3 | Tower-5 | TR-1010-26 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
849 | Tamil | 2026-03-08 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
850 | Tamil | 2026-03-08 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
851 | Tamil | 2026-03-08 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03
852 | Tamil | 2026-03-08 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03, bolt torquing of tower 5, painting touch up
853 | Tamil | 2026-03-08 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03
854 | Tamil | 2026-03-08 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03, bolt torquing of tower 5, painting touch up
855 | Tamil | 2026-03-08 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
856 | Tamil | 2026-03-08 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
857 | Tamil | 2026-03-08 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Common Area | _ |  | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
858 | Tamil | 2026-03-08 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ |  | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
859 | Tamil | 2026-03-08 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor
859 | Tamil | 2026-03-08 | Encogroup | Mustafa Moosa Ahned Al Balushi | 18114443 | Driver | Manpower | Manpower | Parking Area
859 | Tamil | 2026-03-08 | Encogroup | Ahmed Khadeem Said Al Tourashi | 19753414 | Bus Driver | Manpower | Manpower | Parking Area
857 | Tamil | 2026-03-08 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
860 | Tamil | 2026-03-08 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
861 | Tamil | 2026-03-08 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
862 | Tamil | 2026-03-08 | Encogroup | Sanjay Kumar Suresh Ram | 141365037 | Painter | Manpower | Manpower | Parking Area | Tower 7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 7&columns
863 | Tamil | 2026-03-08 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
864 | Tamil | 2026-03-08 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03& Material segregation
865 | Tamil | 2026-03-08 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Storekeeper | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | StoreKeeper
866 | Tamil | 2026-03-08 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03
867 | Tamil | 2026-03-08 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03
868 | Tamil | 2026-03-08 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03, bolt torquing of tower 5, painting touch up
869 | Tamil | 2026-03-08 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
870 | Tamil | 2026-03-08 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of Tower- 03, bolt torquing of tower 5, painting touch up
871 | Tamil | 2026-03-08 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
871 | Tamil | 2026-03-08 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
872 | Shijo | 2026-03-08 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
873 | Shijo | 2026-03-08 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
873 | Shijo | 2026-03-08 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane dis-mantling completed
874 | Shijo | 2026-03-08 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Crane operator Absent
875 | Shijo | 2026-03-08 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | _
876 | Shijo | 2026-03-08 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 8 |  |  |  | 150T crawler crane is dis-manted
877 | Shijo | 2026-03-08 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
878 | Shijo | 2026-03-08 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
879 | Shijo | 2026-03-08 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
880 | Shijo | 2026-03-08 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
881 | Shijo | 2026-03-08 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
882 | Shijo | 2026-03-08 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 8 |  |  |  | 150T crawler crane dis-mantling completed
883 | Shijo | 2026-03-08 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
884 | Shijo | 2026-03-08 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works
885 | Shijo | 2026-03-08 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
886 | Shijo | 2026-03-08 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works
887 | Shijo | 2026-03-08 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading | PARKING AREA
888 | Shijo | 2026-03-08 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
889 | Shijo | 2026-03-08 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
890 | Shijo | 2026-03-08 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
891 | Shijo | 2026-03-08 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
892 | Shijo | 2026-03-08 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
893 | Shijo | 2026-03-08 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
894 | Shijo | 2026-03-08 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver | PARKING AREA
895 | Shijo | 2026-03-08 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
896 | Shijo | 2026-03-08 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
897 | Shijo | 2026-03-08 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
898 | Shijo | 2026-03-08 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works
899 | Shijo | 2026-03-08 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
900 | Shijo | 2026-03-08 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works
901 | Shijo | 2026-03-08 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
902 | Shijo | 2026-03-08 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
903 | Shijo | 2026-03-08 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
904 | Shijo | 2026-03-08 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
905 | Shijo | 2026-03-08 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator | PARKING AREA + YARD 3
906 | Shijo | 2026-03-08 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
907 | Shijo | 2026-03-08 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works | PARKING AREA
908 | Shijo | 2026-03-08 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
909 | Shijo | 2026-03-08 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
910 | Shijo | 2026-03-08 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
911 | Shijo | 2026-03-08 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
912 | Shijo | 2026-03-08 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works
913 | Shijo | 2026-03-08 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
914 | Shijo | 2026-03-08 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
915 | Shijo | 2026-03-08 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
916 | Shijo | 2026-03-08 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
917 | Shijo | 2026-03-08 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works
918 | Shijo | 2026-03-08 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
919 | Shijo | 2026-03-08 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
920 | Shijo | 2026-03-08 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
921 | Shijo | 2026-03-08 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works
922 | Shijo | 2026-03-08 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane dis-mantling completed
923 | Shijo | 2026-03-08 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
924 | Shijo | 2026-03-08 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
925 | Shijo | 2026-03-08 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
926 | Shijo | 2026-03-08 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
927 | Shijo | 2026-03-08 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
928 | Shijo | 2026-03-08 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
929 | Shijo | 2026-03-08 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works
930 | Shijo | 2026-03-08 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials and 130T crawler crane dis-mantling works
931 | Shijo | 2026-03-08 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
932 | Shijo | 2026-03-08 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
933 | Shijo | 2026-03-08 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
934 | Shijo | 2026-03-08 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TR1010-026- Material loading
935 | Shijo | 2026-03-08 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver
936 | Ebin | 2026-03-09 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
937 | Ebin | 2026-03-09 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
938 | Ebin | 2026-03-09 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
939 | Ebin | 2026-03-09 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
940 | Ebin | 2026-03-09 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
941 | Ebin | 2026-03-09 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _ | YARD 2
942 | Ebin | 2026-03-09 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
943 | Ebin | 2026-03-09 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
944 | Ebin | 2026-03-09 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
945 | Ebin | 2026-03-09 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
946 | Ebin | 2026-03-09 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
947 | Ebin | 2026-03-09 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
947 | Ebin | 2026-03-09 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
948 | Ebin | 2026-03-09 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _ | YARD 2
949 | Ebin | 2026-03-09 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
950 | Ebin | 2026-03-09 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
951 | Ebin | 2026-03-09 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
952 | Ebin | 2026-03-09 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | No usage
953 | Ebin | 2026-03-09 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
954 | Ebin | 2026-03-09 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
955 | Ebin | 2026-03-09 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
956 | Ebin | 2026-03-09 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
957 | Ebin | 2026-03-09 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
957 | Ebin | 2026-03-09 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
958 | Ebin | 2026-03-09 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
959 | Ebin | 2026-03-09 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
960 | Ebin | 2026-03-09 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
961 | Ebin | 2026-03-09 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
962 | Ebin | 2026-03-09 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
963 | Ebin | 2026-03-09 | BUSHRA | Rashid | #N/A | Diesel Re-fueling team | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 1 | Diesel filling | Diesel filling | Diesel filling | _
963 | Ebin | 2026-03-09 | BUSHRA | Adil | Not Required | Diesel Re-fueling team | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 1 | Diesel filling | Diesel filling | Diesel filling | _
964 | Ebin | 2026-03-09 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
963 | Ebin | 2026-03-09 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
965 | Ebin | 2026-03-09 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
966 | Ebin | 2026-03-09 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
967 | Ebin | 2026-03-09 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
968 | Ebin | 2026-03-09 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
969 | Ebin | 2026-03-09 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
970 | Ebin | 2026-03-09 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
971 | Ebin | 2026-03-09 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
972 | Tamil | 2026-03-09 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolting of Tower- 03
973 | Tamil | 2026-03-09 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
974 | Tamil | 2026-03-09 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material offloading&segregation of tower-4
975 | Tamil | 2026-03-09 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
976 | Tamil | 2026-03-09 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
977 | Tamil | 2026-03-09 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 6 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Material offloading&segregation of tower-4, bolting of tower-3, torquing of tower-5 &paint touch-up works
978 | Tamil | 2026-03-09 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 10 | Painting Coating | Surface cleaning | Surface cleaning | Painting touch-up- tower 6& 7
979 | Tamil | 2026-03-09 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
980 | Tamil | 2026-03-09 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
981 | Tamil | 2026-03-09 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolting of Tower- 03
982 | Tamil | 2026-03-09 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
983 | Tamil | 2026-03-09 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
984 | Tamil | 2026-03-09 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
985 | Tamil | 2026-03-09 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material offloading&segregation of tower-4
986 | Tamil | 2026-03-09 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material offloading&segregation of tower-4, bolting of tower-3, torquing of tower-5 &paint touch-up works
987 | Tamil | 2026-03-09 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material offloading&segregation of tower-4
988 | Tamil | 2026-03-09 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material offloading&segregation of tower-4
989 | Tamil | 2026-03-09 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
990 | Tamil | 2026-03-09 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
991 | Tamil | 2026-03-09 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
992 | Tamil | 2026-03-09 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
993 | Tamil | 2026-03-09 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
994 | Tamil | 2026-03-09 | Encogroup | Sanjay Kumar Suresh Ram | 141365037 | Painter | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
995 | Tamil | 2026-03-09 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolting of Tower- 03
996 | Tamil | 2026-03-09 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material offloading&segregation of tower-4
997 | Tamil | 2026-03-09 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Storekeeper | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | StoreKeeper
998 | Tamil | 2026-03-09 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material offloading&segregation of tower-4
999 | Tamil | 2026-03-09 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material offloading&segregation of tower-4
1000 | Tamil | 2026-03-09 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material offloading&segregation of tower-4, bolting of tower-3, torquing of tower-5 &paint touch-up works
1001 | Tamil | 2026-03-09 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1002 | Tamil | 2026-03-09 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material offloading&segregation of tower-4, bolting of tower-3, torquing of tower-5 &paint touch-up works
1003 | Tamil | 2026-03-09 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1004 | Tamil | 2026-03-09 | Encogroup | Mustafa Moosa Ahned Al Balushi | 18114443 | Driver | Manpower | Manpower | Common Area | Tower-5&3 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1003 | Tamil | 2026-03-09 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
1005 | Shijo | 2026-03-09 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1006 | Shijo | 2026-03-09 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1006 | Shijo | 2026-03-09 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-manted
1007 | Shijo | 2026-03-09 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Crane operator Absent
1008 | Shijo | 2026-03-09 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | _
1009 | Shijo | 2026-03-09 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 150T crawler crane is dis-manted
1010 | Shijo | 2026-03-09 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1011 | Shijo | 2026-03-09 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1012 | Shijo | 2026-03-09 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
1013 | Shijo | 2026-03-09 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1014 | Shijo | 2026-03-09 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1015 | Shijo | 2026-03-09 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1016 | Shijo | 2026-03-09 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1017 | Shijo | 2026-03-09 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1018 | Shijo | 2026-03-09 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1019 | Shijo | 2026-03-09 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3 | PARKING AREA
1020 | Shijo | 2026-03-09 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1021 | Shijo | 2026-03-09 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1022 | Shijo | 2026-03-09 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1023 | Shijo | 2026-03-08 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1024 | Shijo | 2026-03-09 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
1025 | Shijo | 2026-03-09 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1026 | Shijo | 2026-03-09 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver | PARKING AREA
1027 | Shijo | 2026-03-09 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1028 | Shijo | 2026-03-09 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1029 | Shijo | 2026-03-09 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1030 | Shijo | 2026-03-09 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1031 | Shijo | 2026-03-09 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1032 | Shijo | 2026-03-09 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1033 | Shijo | 2026-03-09 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
1034 | Shijo | 2026-03-09 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1035 | Shijo | 2026-03-09 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1036 | Shijo | 2026-03-09 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1037 | Shijo | 2026-03-09 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator
1038 | Shijo | 2026-03-09 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1039 | Shijo | 2026-03-09 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1040 | Shijo | 2026-03-09 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1041 | Shijo | 2026-03-09 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1042 | Shijo | 2026-03-09 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1043 | Shijo | 2026-03-09 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1044 | Shijo | 2026-03-09 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1045 | Shijo | 2026-03-09 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1046 | Shijo | 2026-03-09 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1047 | Shijo | 2026-03-09 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1048 | Shijo | 2026-03-09 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1049 | Shijo | 2026-03-09 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
1050 | Shijo | 2026-03-09 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1051 | Shijo | 2026-03-09 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1052 | Shijo | 2026-03-09 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1053 | Shijo | 2026-03-08 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 |  |  |  | 130T crawler crane is dis-manted
1054 | Shijo | 2026-03-09 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1055 | Shijo | 2026-03-09 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1056 | Shijo | 2026-03-09 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1057 | Shijo | 2026-03-09 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1058 | Shijo | 2026-03-09 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1059 | Shijo | 2026-03-09 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1060 | Shijo | 2026-03-09 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1061 | Shijo | 2026-03-09 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1062 | Shijo | 2026-03-09 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1063 | Shijo | 2026-03-09 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Site Office | _ | _ | Day | 8 | Mobilization Preparation | Crane mobilization & inspection | Crane mobilization & inspection | Mechanics of Dis-mantled Crane
1064 | Shijo | 2026-03-09 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Site Office | _ | _ | Day | 8 | Mobilization Preparation | Crane mobilization & inspection | Crane mobilization & inspection | Mechanics of Dis-mantled Crane
1065 | Shijo | 2026-03-09 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1066 | Shijo | 2026-03-09 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1067 | Shijo | 2026-03-09 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1068 | Shijo | 2026-03-08 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1068 | Shijo | 2026-03-09 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver
1069 | Ebin | 2026-03-10 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 3 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1070 | Ebin | 2026-03-10 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1071 | Ebin | 2026-03-10 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1072 | Ebin | 2026-03-10 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1073 | Ebin | 2026-03-10 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1074 | Ebin | 2026-03-10 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1075 | Ebin | 2026-03-10 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1076 | Ebin | 2026-03-10 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1077 | Ebin | 2026-03-10 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1078 | Ebin | 2026-03-10 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1079 | Ebin | 2026-03-10 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1080 | Ebin | 2026-03-10 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1080 | Ebin | 2026-03-10 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 3 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1081 | Ebin | 2026-03-10 | SARENS NASS | Moshin Saleem Salim AL-Shukaili | 14552941 | Crane Operator- 70T Hitachi Crawler crane | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1081 | Ebin | 2026-03-10 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1082 | Ebin | 2026-03-10 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, CT1010-02 material offloading& shifting to yard-2, Offloading operations involving six trailers transporting a 70-ton crawler crane
1083 | Ebin | 2026-03-10 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1084 | Ebin | 2026-03-10 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1085 | Ebin | 2026-03-10 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1086 | Ebin | 2026-03-10 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1087 | Ebin | 2026-03-10 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1088 | Ebin | 2026-03-10 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1089 | Ebin | 2026-03-10 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1090 | Ebin | 2026-03-10 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1091 | Ebin | 2026-03-10 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1091 | Ebin | 2026-03-10 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1092 | Ebin | 2026-03-10 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1093 | Ebin | 2026-03-10 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1094 | Ebin | 2026-03-10 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1095 | Ebin | 2026-03-10 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1096 | Ebin | 2026-03-10 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _ | YARD 3
1097 | Ebin | 2026-03-10 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1098 | Ebin | 2026-03-10 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1099 | Ebin | 2026-03-10 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1100 | Ebin | 2026-03-10 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1101 | Ebin | 2026-03-10 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1102 | Ebin | 2026-03-10 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1103 | Ebin | 2026-03-10 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1104 | Ebin | 2026-03-10 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1105 | Tamil | 2026-03-10 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1106 | Tamil | 2026-03-10 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
1107 | Tamil | 2026-03-10 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material segregation of tower-4
1108 | Tamil | 2026-03-10 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
1109 | Tamil | 2026-03-10 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
1110 | Tamil | 2026-03-10 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Material segregation of tower-4, torquing of tower-3, torquing of tower-5 &paint touch-up works
1111 | Tamil | 2026-03-10 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
1112 | Tamil | 2026-03-10 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1113 | Tamil | 2026-03-10 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1114 | Tamil | 2026-03-10 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5 | YARD 3
1115 | Tamil | 2026-03-10 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
1116 | Tamil | 2026-03-10 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-5 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 05
1117 | Tamil | 2026-03-10 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4
1118 | Tamil | 2026-03-10 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4, torquing of tower-3, torquing of tower-5 &paint touch-up works
1119 | Tamil | 2026-03-10 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
1120 | Tamil | 2026-03-10 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4
1121 | Tamil | 2026-03-10 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4
1122 | Tamil | 2026-03-10 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Common Area | Tower-5 | TR-1010-26 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Alignment of tower 5
1123 | Tamil | 2026-03-10 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Common Area | _ |  | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
1123 | Tamil | 2026-03-10 | Encogroup | Mustafa Moosa Ahned Al Balushi | 18114443 | Driver | Manpower | Manpower | Common Area | Tower-5 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane
1123 | Tamil | 2026-03-10 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
1124 | Tamil | 2026-03-10 | Encogroup | Mathan Kumar | 140796986 | Mechanical QC | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1124 | Tamil | 2026-03-10 | Encogroup | Dhinesh Vaithiyanathan | 140645388 | Store keeper | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Diesel filling | Diesel filling | Diesel filling | _
1124 | Tamil | 2026-03-10 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
1125 | Tamil | 2026-03-10 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
1126 | Tamil | 2026-03-10 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
1127 | Tamil | 2026-03-10 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6& 7
1128 | Tamil | 2026-03-10 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1129 | Tamil | 2026-03-10 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4
1130 | Tamil | 2026-03-10 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4
1131 | Tamil | 2026-03-10 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4
1132 | Tamil | 2026-03-10 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4, torquing of tower-3, torquing of tower-5 &paint touch-up works
1133 | Tamil | 2026-03-10 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1134 | Tamil | 2026-03-10 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4, torquing of tower-3, torquing of tower-5 &paint touch-up works
1135 | Tamil | 2026-03-10 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1135 | Tamil | 2026-03-10 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-5,3&4 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
1136 | Shijo | 2026-03-10 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1137 | Shijo | 2026-03-10 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1137 | Shijo | 2026-03-10 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-manted
1138 | Shijo | 2026-03-10 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Used for Enco works
1138 | Shijo | 2026-03-10 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Used for Enco works
1139 | Shijo | 2026-03-10 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | _
1140 | Shijo | 2026-03-10 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 150T crawler crane is dis-manted
1141 | Shijo | 2026-03-10 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1142 | Shijo | 2026-03-10 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1143 | Shijo | 2026-03-10 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
1144 | Shijo | 2026-03-10 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1145 | Shijo | 2026-03-10 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1146 | Shijo | 2026-03-10 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1147 | Shijo | 2026-03-10 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1148 | Shijo | 2026-03-10 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1149 | Shijo | 2026-03-10 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1150 | Shijo | 2026-03-10 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1151 | Shijo | 2026-03-10 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1152 | Shijo | 2026-03-10 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1153 | Shijo | 2026-03-10 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1154 | Shijo | 2026-03-10 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
1155 | Shijo | 2026-03-10 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1156 | Shijo | 2026-03-10 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver | PARKING AREA + YARD 3
1157 | Shijo | 2026-03-10 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1158 | Shijo | 2026-03-10 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1159 | Shijo | 2026-03-10 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1160 | Shijo | 2026-03-10 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1161 | Shijo | 2026-03-10 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1162 | Shijo | 2026-03-10 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1163 | Shijo | 2026-03-10 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
1164 | Shijo | 2026-03-10 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1165 | Shijo | 2026-03-10 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1166 | Shijo | 2026-03-10 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1167 | Shijo | 2026-03-10 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator | PARKING AREA
1168 | Shijo | 2026-03-10 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1169 | Shijo | 2026-03-10 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1170 | Shijo | 2026-03-10 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1171 | Shijo | 2026-03-10 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1172 | Shijo | 2026-03-10 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1173 | Shijo | 2026-03-10 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1174 | Shijo | 2026-03-10 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1175 | Shijo | 2026-03-10 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1176 | Shijo | 2026-03-10 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1177 | Shijo | 2026-03-10 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1178 | Shijo | 2026-03-10 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1179 | Shijo | 2026-03-10 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1180 | Shijo | 2026-03-10 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1181 | Shijo | 2026-03-10 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
1182 | Shijo | 2026-03-10 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1183 | Shijo | 2026-03-10 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1184 | Shijo | 2026-03-10 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-manted
1185 | Shijo | 2026-03-10 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1186 | Shijo | 2026-03-10 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1187 | Shijo | 2026-03-10 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 11 | Piping Works | Fit-up | Fit-up | TSF works- 1 hr O.T For excavation works
1188 | Shijo | 2026-03-10 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1189 | Shijo | 2026-03-10 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1190 | Shijo | 2026-03-10 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1191 | Shijo | 2026-03-10 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1192 | Shijo | 2026-03-10 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1193 | Shijo | 2026-03-10 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1194 | Shijo | 2026-03-10 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1194 | Shijo | 2026-03-10 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1195 | Shijo | 2026-03-10 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1196 | Shijo | 2026-03-10 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1197 | Shijo | 2026-03-10 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1198 | Shijo | 2026-03-10 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1197 | Shijo | 2026-03-10 | SARENS NASS | Moshin Saleem Salim AL-Shukaili | 14552941 | Crane Operator- 70T Hitachi Crawler crane | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 materials to yard-3
1197 | Shijo | 2026-03-10 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | YARD 3
1199 | Ebin | 2026-03-11 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1200 | Ebin | 2026-03-11 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1201 | Ebin | 2026-03-11 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1202 | Ebin | 2026-03-11 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights | YARD 2
1203 | Ebin | 2026-03-11 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1204 | Ebin | 2026-03-11 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights | YARD 2
1205 | Ebin | 2026-03-11 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1206 | Ebin | 2026-03-11 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1207 | Ebin | 2026-03-11 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1208 | Ebin | 2026-03-11 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1209 | Ebin | 2026-03-11 | SARENS NASS | Moshin Saleem Salim AL-Shukaili | 14552941 | Crane Operator- 70T Hitachi Crawler crane | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1210 | Ebin | 2026-03-11 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1210 | Ebin | 2026-03-11 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1211 | Ebin | 2026-03-11 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1211 | Ebin | 2026-03-11 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1212 | Ebin | 2026-03-11 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1213 | Ebin | 2026-03-11 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1211 | Ebin | 2026-03-11 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1214 | Ebin | 2026-03-11 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Ground pre-assembly | Surveyor assistant
1215 | Ebin | 2026-03-11 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Ground pre-assembly | Surveyor assistant
1216 | Ebin | 2026-03-11 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 temporary chassis modification, offloading of the 70-ton crawler crane has been completed, and its assembly is currently in progress, including installation of the counterweights
1217 | Ebin | 2026-03-11 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1218 | Ebin | 2026-03-11 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1219 | Ebin | 2026-03-11 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1220 | Ebin | 2026-03-11 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1221 | Ebin | 2026-03-11 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1222 | Ebin | 2026-03-11 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1223 | Ebin | 2026-03-11 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1224 | Ebin | 2026-03-11 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1225 | Ebin | 2026-03-11 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1225 | Ebin | 2026-03-11 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1226 | Ebin | 2026-03-11 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1227 | Ebin | 2026-03-11 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1228 | Ebin | 2026-03-11 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1229 | Ebin | 2026-03-11 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1229 | Ebin | 2026-03-11 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1230 | Ebin | 2026-03-11 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1231 | Ebin | 2026-03-11 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1232 | Ebin | 2026-03-11 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1233 | Ebin | 2026-03-11 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1234 | Ebin | 2026-03-11 | Encogroup | Fenil Paul | 137098196 | Lifting engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1234 | Ebin | 2026-03-11 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1235 | Ebin | 2026-03-11 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1236 | Ebin | 2026-03-11 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1237 | Ebin | 2026-03-11 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1238 | Ebin | 2026-03-11 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1239 | Tamil | 2026-03-11 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1240 | Tamil | 2026-03-11 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1241 | Tamil | 2026-03-11 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material segregation of tower-4&8
1242 | Tamil | 2026-03-11 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Material segregation of tower-4, torquing of tower-3, torquing of tower-5 &paint touch-up works
1243 | Tamil | 2026-03-11 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 10 | Painting Coating | Surface cleaning | Surface cleaning | Painting touch-up- tower 5&6
1244 | Tamil | 2026-03-11 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1245 | Tamil | 2026-03-11 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1246 | Tamil | 2026-03-11 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1247 | Tamil | 2026-03-11 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
1248 | Tamil | 2026-03-11 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1249 | Tamil | 2026-03-11 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4&8
1250 | Tamil | 2026-03-11 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4&8, torquing of tower-3,paint touch-up works
1251 | Tamil | 2026-03-11 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
1252 | Tamil | 2026-03-11 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4&8
1253 | Tamil | 2026-03-11 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4&8
1254 | Tamil | 2026-03-11 | Encogroup | Ahmed Khadeem Said Al Tourashi | 19753414 | Bus Driver | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 |  |  |  | Driver
1254 | Tamil | 2026-03-11 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 |  |  |  | Driver
1254 | Tamil | 2026-03-11 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ |  | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
1254 | Tamil | 2026-03-11 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Common Area | _ |  | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Mechanic
1254 | Tamil | 2026-03-11 | Encogroup | Fenil Paul | 137098196 | Lifting engineer | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Lifting Engineer
1254 | Tamil | 2026-03-11 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5&6
1255 | Tamil | 2026-03-11 | Encogroup | Mathan Kumar | 140796986 | Mechanical QC | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1256 | Tamil | 2026-03-11 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Surveyor
1255 | Tamil | 2026-03-11 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5&6
1257 | Tamil | 2026-03-11 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5&6
1258 | Tamil | 2026-03-11 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5&6
1259 | Tamil | 2026-03-11 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5&6
1260 | Tamil | 2026-03-11 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1261 | Tamil | 2026-03-11 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4&8
1262 | Tamil | 2026-03-11 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4&8 | LAYDOWN
1263 | Tamil | 2026-03-11 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4&8 | LAYDOWN
1264 | Tamil | 2026-03-11 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4&8, torquing of tower-3,paint touch-up works
1265 | Tamil | 2026-03-11 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1266 | Tamil | 2026-03-11 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-4&8, torquing of tower-3,paint touch-up works
1267 | Tamil | 2026-03-11 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1267 | Tamil | 2026-03-11 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
1268 | Shijo | 2026-03-11 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1269 | Shijo | 2026-03-11 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1269 | Shijo | 2026-03-11 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-mantled
1270 | Shijo | 2026-03-11 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1271 | Shijo | 2026-03-11 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1272 | Shijo | 2026-03-11 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1272 | Shijo | 2026-03-11 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Laydown | _ | Offloading | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1272 | Shijo | 2026-03-11 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1273 | Shijo | 2026-03-11 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 8 |  |  |  | 150T crawler crane is dis-manted
1274 | Shijo | 2026-03-11 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1275 | Shijo | 2026-03-11 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1276 | Shijo | 2026-03-11 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
1277 | Shijo | 2026-03-11 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1278 | Shijo | 2026-03-11 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1279 | Shijo | 2026-03-11 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1280 | Shijo | 2026-03-11 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1281 | Shijo | 2026-03-11 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1282 | Shijo | 2026-03-11 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1283 | Shijo | 2026-03-11 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1284 | Shijo | 2026-03-11 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1285 | Shijo | 2026-03-11 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1286 | Shijo | 2026-03-11 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1287 | Shijo | 2026-03-11 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
1288 | Shijo | 2026-03-11 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1289 | Shijo | 2026-03-11 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver | PARKING AREA
1290 | Shijo | 2026-03-11 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
1291 | Shijo | 2026-03-11 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1292 | Shijo | 2026-03-11 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1293 | Shijo | 2026-03-11 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1294 | Shijo | 2026-03-11 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1295 | Shijo | 2026-03-11 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1296 | Shijo | 2026-03-11 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
1297 | Shijo | 2026-03-11 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1298 | Shijo | 2026-03-11 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1299 | Shijo | 2026-03-11 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1300 | Shijo | 2026-03-11 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1301 | Shijo | 2026-03-11 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator | PARKING AREA
1302 | Shijo | 2026-03-11 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1303 | Shijo | 2026-03-11 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1304 | Shijo | 2026-03-11 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1305 | Shijo | 2026-03-11 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1306 | Shijo | 2026-03-11 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1307 | Shijo | 2026-03-11 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1308 | Shijo | 2026-03-11 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1309 | Shijo | 2026-03-11 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1310 | Shijo | 2026-03-11 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1311 | Shijo | 2026-03-11 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1312 | Shijo | 2026-03-11 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1313 | Shijo | 2026-03-11 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1314 | Shijo | 2026-03-11 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
1315 | Shijo | 2026-03-11 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1316 | Shijo | 2026-03-11 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1317 | Shijo | 2026-03-11 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-mantled
1318 | Shijo | 2026-03-11 | Sarens Nass | Padmanaban Sevu | 77873529 | Mechanic | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Technicians
1319 | Shijo | 2026-03-11 | Sarens Nass | Dinesh Yadav | 12284034 | Rigger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Technicians
1318 | Shijo | 2026-03-11 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 8 |  |  |  | 150T crawler crane is dis-manted
1320 | Shijo | 2026-03-11 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of TR1010-026 materials to parking area
1321 | Shijo | 2026-03-11 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1322 | Shijo | 2026-03-11 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
1323 | Shijo | 2026-03-11 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
1324 | Shijo | 2026-03-11 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1325 | Shijo | 2026-03-11 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1326 | Shijo | 2026-03-11 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1327 | Shijo | 2026-03-11 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1328 | Shijo | 2026-03-11 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1329 | Shijo | 2026-03-11 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1330 | Shijo | 2026-03-11 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1331 | Shijo | 2026-03-11 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1332 | Shijo | 2026-03-11 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1332 | Shijo | 2026-03-11 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area
1333 | Shijo | 2026-03-11 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | PARKING AREA
1334 | Ebin | 2026-03-12 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1335 | Ebin | 2026-03-12 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 3 | DBD BUILDING | DBD Bld | Day | 10 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | DBD building stopper installation for overhead crane
1336 | Ebin | 2026-03-12 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Yard 3 | DBD BUILDING | DBD Bld | Day | 10 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | DBD building stopper installation for overhead crane
1337 | Ebin | 2026-03-12 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | DBD BUILDING | DBD Bld | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | DBD building stopper installation for overhead crane
1338 | Ebin | 2026-03-12 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1339 | Ebin | 2026-03-12 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1340 | Ebin | 2026-03-12 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1341 | Ebin | 2026-03-12 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1342 | Ebin | 2026-03-12 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1343 | Ebin | 2026-03-12 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1344 | Ebin | 2026-03-12 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1345 | Ebin | 2026-03-12 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1345 | Ebin | 2026-03-12 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification | YARD 2
1346 | Ebin | 2026-03-12 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1347 | Ebin | 2026-03-12 | SARENS NASS | Moshin Saleem Salim AL-Shukaili | 14552941 | Crane Operator- 70T Hitachi Crawler crane | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1348 | Ebin | 2026-03-12 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1348 | Ebin | 2026-03-12 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1349 | Ebin | 2026-03-12 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1350 | Ebin | 2026-03-12 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1349 | Ebin | 2026-03-12 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1351 | Ebin | 2026-03-12 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1352 | Ebin | 2026-03-12 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 3 | Surveying | CT-1010-02 | Day | 10 | Alignment of surveyor | Strucutre Pre-Assembly | Ground pre-assembly | Surveyor Assistant
1353 | Ebin | 2026-03-12 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification | PARKING AREA
1354 | Ebin | 2026-03-12 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1355 | Ebin | 2026-03-12 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1356 | Ebin | 2026-03-12 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1357 | Ebin | 2026-03-12 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1358 | Ebin | 2026-03-12 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1359 | Ebin | 2026-03-12 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1360 | Ebin | 2026-03-12 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1361 | Ebin | 2026-03-12 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1362 | Ebin | 2026-03-12 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1362 | Ebin | 2026-03-12 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1363 | Ebin | 2026-03-12 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1364 | Ebin | 2026-03-12 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1365 | Ebin | 2026-03-12 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1366 | Ebin | 2026-03-12 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1367 | Ebin | 2026-03-12 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1368 | Ebin | 2026-03-12 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1369 | Ebin | 2026-03-12 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1370 | Ebin | 2026-03-12 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1370 | Ebin | 2026-03-12 | Encogroup | Ali Riza | 140849254 | Construction Manager | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1371 | Ebin | 2026-03-12 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1372 | Ebin | 2026-03-12 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1370 | Ebin | 2026-03-12 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1373 | Ebin | 2026-03-12 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1374 | Ebin | 2026-03-12 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1375 | Ebin | 2026-03-12 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1376 | Ebin | 2026-03-12 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1377 | Tamil | 2026-03-12 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1378 | Tamil | 2026-03-12 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1379 | Tamil | 2026-03-12 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material segregation of tower-8, pre-assembly of tower-4
1380 | Tamil | 2026-03-12 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-3 &paint touch-up works
1381 | Tamil | 2026-03-12 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 10 | Painting Coating | Surface cleaning | Surface cleaning | Painting touch-up- tower 6&7
1382 | Tamil | 2026-03-12 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1383 | Tamil | 2026-03-12 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1384 | Tamil | 2026-03-12 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1385 | Tamil | 2026-03-12 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
1386 | Tamil | 2026-03-12 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1387 | Tamil | 2026-03-12 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4
1388 | Tamil | 2026-03-12 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-3 &paint touch-up works
1389 | Tamil | 2026-03-12 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
1390 | Tamil | 2026-03-12 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4
1391 | Tamil | 2026-03-12 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4
1392 | Tamil | 2026-03-12 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | _
1393 | Tamil | 2026-03-12 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 8 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
1394 | Tamil | 2026-03-12 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | Tower-5&6 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1395 | Tamil | 2026-03-12 | Encogroup | Mathan Kumar | 140796986 | Mechanical QC | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | _
loke | Tamil | 2026-03-12 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 5 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
1393 | Tamil | 2026-03-12 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1396 | Tamil | 2026-03-12 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1397 | Tamil | 2026-03-12 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1398 | Tamil | 2026-03-12 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1399 | Tamil | 2026-03-12 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 03
1400 | Tamil | 2026-03-12 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4
1401 | Tamil | 2026-03-12 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4
1402 | Tamil | 2026-03-12 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4
1403 | Tamil | 2026-03-12 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-3 &paint touch-up works
1404 | Tamil | 2026-03-12 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1405 | Tamil | 2026-03-12 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-3 &paint touch-up works
1406 | Tamil | 2026-03-12 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1406 | Tamil | 2026-03-12 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4,8&3 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
1407 | Shijo | 2026-03-12 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1408 | Shijo | 2026-03-12 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1408 | Shijo | 2026-03-12 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-manted
1409 | Shijo | 2026-03-12 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
| Shijo | 2026-03-12 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works
1410 | Shijo | 2026-03-12 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 8 |  |  |  | 150T crawler crane is dis-manted
1411 | Shijo | 2026-03-12 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1412 | Shijo | 2026-03-12 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1413 | Shijo | 2026-03-12 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
1414 | Shijo | 2026-03-12 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1415 | Shijo | 2026-03-12 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1416 | Shijo | 2026-03-12 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1417 | Shijo | 2026-03-12 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1418 | Shijo | 2026-03-12 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1419 | Shijo | 2026-03-12 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1420 | Shijo | 2026-03-12 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1421 | Shijo | 2026-03-12 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1422 | Shijo | 2026-03-12 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1423 | Shijo | 2026-03-12 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1424 | Shijo | 2026-03-12 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
1425 | Shijo | 2026-03-12 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1426 | Shijo | 2026-03-12 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver
1427 | Shijo | 2026-03-12 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
1428 | Shijo | 2026-03-12 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1429 | Shijo | 2026-03-12 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1430 | Shijo | 2026-03-12 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1431 | Shijo | 2026-03-12 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works
1432 | Shijo | 2026-03-12 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1433 | Shijo | 2026-03-12 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
1434 | Shijo | 2026-03-12 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1435 | Shijo | 2026-03-12 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1436 | Shijo | 2026-03-12 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1437 | Shijo | 2026-03-12 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator | PARKING AREA
1438 | Shijo | 2026-03-12 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1439 | Shijo | 2026-03-12 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1440 | Shijo | 2026-03-12 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1441 | Shijo | 2026-03-12 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1442 | Shijo | 2026-03-12 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1443 | Shijo | 2026-03-12 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1444 | Shijo | 2026-03-12 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1445 | Shijo | 2026-03-12 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1446 | Shijo | 2026-03-12 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1447 | Shijo | 2026-03-12 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1448 | Shijo | 2026-03-12 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1449 | Shijo | 2026-03-12 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1450 | Shijo | 2026-03-12 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
1451 | Shijo | 2026-03-12 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1452 | Shijo | 2026-03-12 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1453 | Shijo | 2026-03-12 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-manted
1454 | Shijo | 2026-03-12 | Encogroup | Syed Ihsan Haider | 100398391 | DuqmTrailer Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Duqm Trailer Driver
1454 | Shijo | 2026-03-12 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1455 | Shijo | 2026-03-12 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1456 | Shijo | 2026-03-12 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
1457 | Shijo | 2026-03-12 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1458 | Shijo | 2026-03-12 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1459 | Shijo | 2026-03-12 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1460 | Shijo | 2026-03-12 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1461 | Shijo | 2026-03-12 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1462 | Shijo | 2026-03-12 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3 | PARKING AREA
1463 | Shijo | 2026-03-12 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1464 | Shijo | 2026-03-12 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1465 | Shijo | 2026-03-12 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1466 | Shijo | 2026-03-12 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-026 materials to parking area& crawler crane materials to yard-3
1467 | Shijo | 2026-03-12 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | PARKING AREA
1468 | Ebin | 2026-03-14 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1469 | Ebin | 2026-03-14 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 3 | DBD BUILDING | DBD Bld | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1470 | Ebin | 2026-03-14 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Yard 3 | DBD BUILDING | DBD Bld | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1471 | Ebin | 2026-03-14 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | DBD BUILDING | DBD Bld | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1472 | Ebin | 2026-03-14 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1473 | Ebin | 2026-03-14 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1474 | Ebin | 2026-03-14 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1475 | Ebin | 2026-03-14 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1476 | Ebin | 2026-03-14 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1477 | Ebin | 2026-03-14 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 5 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1478 | Ebin | 2026-03-14 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 5 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1479 | Ebin | 2026-03-14 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1480 | Ebin | 2026-03-14 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1481 | Ebin | 2026-03-14 | SARENS NASS | Moshin Saleem Salim AL-Shukaili | 14552941 | Crane Operator- 70T Hitachi Crawler crane | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1482 | Ebin | 2026-03-14 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1483 | Ebin | 2026-03-14 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1484 | Ebin | 2026-03-14 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1485 | Ebin | 2026-03-14 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 3 | Surveying | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1486 | Ebin | 2026-03-14 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1487 | Ebin | 2026-03-14 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1488 | Ebin | 2026-03-14 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1489 | Ebin | 2026-03-14 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1490 | Ebin | 2026-03-14 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1491 | Ebin | 2026-03-14 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1492 | Ebin | 2026-03-14 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1493 | Ebin | 2026-03-14 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1494 | Ebin | 2026-03-14 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1495 | Ebin | 2026-03-14 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1495 | Ebin | 2026-03-14 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1496 | Ebin | 2026-03-14 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1497 | Ebin | 2026-03-14 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1498 | Ebin | 2026-03-14 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1499 | Ebin | 2026-03-14 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1500 | Ebin | 2026-03-14 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5
1501 | Ebin | 2026-03-14 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5
1502 | Ebin | 2026-03-14 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1503 | Ebin | 2026-03-14 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1504 | Ebin | 2026-03-14 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1505 | Ebin | 2026-03-14 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1506 | Ebin | 2026-03-14 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1507 | Ebin | 2026-03-14 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1508 | Tamil | 2026-03-14 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1509 | Tamil | 2026-03-14 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1510 | Tamil | 2026-03-14 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1511 | Tamil | 2026-03-14 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 6 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1512 | Tamil | 2026-03-14 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1513 | Tamil | 2026-03-14 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1514 | Tamil | 2026-03-14 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1515 | Tamil | 2026-03-14 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1516 | Tamil | 2026-03-14 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1517 | Tamil | 2026-03-14 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 6 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1518 | Tamil | 2026-03-14 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1519 | Tamil | 2026-03-14 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Idle | 6 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1520 | Tamil | 2026-03-14 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1521 | Tamil | 2026-03-14 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1522 | Tamil | 2026-03-14 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1523 | Tamil | 2026-03-14 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1524 | Tamil | 2026-03-14 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1525 | Tamil | 2026-03-14 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1526 | Tamil | 2026-03-14 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1527 | Tamil | 2026-03-14 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Idle | 6 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1528 | Tamil | 2026-03-14 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1529 | Tamil | 2026-03-14 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1530 | Tamil | 2026-03-14 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1531 | Tamil | 2026-03-14 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1532 | Tamil | 2026-03-14 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4,8&3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1533 | Tamil | 2026-03-14 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1534 | Tamil | 2026-03-14 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4,8&3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1535 | Tamil | 2026-03-14 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4,8&3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1535 | Tamil | 2026-03-14 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4,8&3 | TR-1010-26 | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1536 | Shijo | 2026-03-14 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1537 | Shijo | 2026-03-14 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1537 | Shijo | 2026-03-14 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1538 | Shijo | 2026-03-14 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1539 | Shijo | 2026-03-14 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1540 | Shijo | 2026-03-14 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1541 | Shijo | 2026-03-14 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1542 | Shijo | 2026-03-14 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1543 | Shijo | 2026-03-14 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1544 | Shijo | 2026-03-14 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1545 | Shijo | 2026-03-14 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1546 | Shijo | 2026-03-14 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1547 | Shijo | 2026-03-14 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1548 | Shijo | 2026-03-14 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1549 | Shijo | 2026-03-14 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1550 | Shijo | 2026-03-14 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1551 | Shijo | 2026-03-14 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1552 | Shijo | 2026-03-14 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1553 | Shijo | 2026-03-14 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1554 | Shijo | 2026-03-14 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1555 | Shijo | 2026-03-14 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1556 | Shijo | 2026-03-14 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1557 | Shijo | 2026-03-14 | GAF | Irfan Ansari | 78785394 | Helper | Sub Contactor | Sub Contactor | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1558 | Shijo | 2026-03-14 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1559 | Shijo | 2026-03-14 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1560 | Shijo | 2026-03-14 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1561 | Shijo | 2026-03-14 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1562 | Shijo | 2026-03-14 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1563 | Shijo | 2026-03-14 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1564 | Shijo | 2026-03-14 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1565 | Shijo | 2026-03-14 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1566 | Shijo | 2026-03-14 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1567 | Shijo | 2026-03-14 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1568 | Shijo | 2026-03-14 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1569 | Shijo | 2026-03-14 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1570 | Shijo | 2026-03-14 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1571 | Shijo | 2026-03-14 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1572 | Shijo | 2026-03-14 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1573 | Shijo | 2026-03-14 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1574 | Shijo | 2026-03-14 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1575 | Shijo | 2026-03-14 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1576 | Shijo | 2026-03-14 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1577 | Shijo | 2026-03-14 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1578 | Shijo | 2026-03-14 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1579 | Shijo | 2026-03-14 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1580 | Shijo | 2026-03-14 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 8 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1581 | Shijo | 2026-03-14 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1582 | Shijo | 2026-03-14 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1583 | Shijo | 2026-03-14 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1584 | Shijo | 2026-03-14 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1585 | Shijo | 2026-03-14 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1586 | Shijo | 2026-03-14 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1587 | Shijo | 2026-03-14 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1588 | Shijo | 2026-03-14 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1589 | Shijo | 2026-03-14 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1590 | Shijo | 2026-03-14 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1591 | Shijo | 2026-03-14 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1592 | Shijo | 2026-03-14 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1593 | Shijo | 2026-03-14 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1594 | Shijo | 2026-03-14 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1595 | Shijo | 2026-03-14 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1596 | Shijo | 2026-03-14 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1597 | Shijo | 2026-03-14 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work has been suspended due to site blockage, as per the Vale telephone communication received from Claudio Cannas.
1598 | Ebin | 2026-03-15 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1599 | Ebin | 2026-03-15 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Chassis Assembly | DBD Bld | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | 70-ton crawler crane assembly&chassis assembly modification have been completed
1600 | Ebin | 2026-03-15 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1601 | Ebin | 2026-03-15 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1602 | Ebin | 2026-03-15 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1603 | Ebin | 2026-03-15 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed | YARD 2
1604 | Ebin | 2026-03-15 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1605 | Ebin | 2026-03-15 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1606 | Ebin | 2026-03-15 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1607 | Ebin | 2026-03-15 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1608 | Ebin | 2026-03-15 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1609 | Ebin | 2026-03-15 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1608 | Ebin | 2026-03-15 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1610 | Ebin | 2026-03-15 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Alignment of surveyor | Alignment of surveyor | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1611 | Ebin | 2026-03-15 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1612 | Ebin | 2026-03-15 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
| Ebin | 2026-03-15 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1612 | Ebin | 2026-03-15 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1613 | Ebin | 2026-03-15 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1613 | Ebin | 2026-03-15 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1610 | Ebin | 2026-03-15 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly is currently in-progress&chassis assembly modification
1614 | Ebin | 2026-03-15 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed
1615 | Ebin | 2026-03-15 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed | YARD 2
1616 | Ebin | 2026-03-15 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane assembly&chassis assembly modification have been completed | YARD 2
1617 | Ebin | 2026-03-15 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1618 | Ebin | 2026-03-15 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1619 | Ebin | 2026-03-15 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1620 | Ebin | 2026-03-15 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly
1621 | Ebin | 2026-03-15 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1622 | Ebin | 2026-03-15 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1623 | Ebin | 2026-03-15 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1624 | Ebin | 2026-03-15 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1625 | Ebin | 2026-03-15 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1625 | Ebin | 2026-03-15 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1626 | Ebin | 2026-03-15 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1627 | Ebin | 2026-03-15 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1628 | Ebin | 2026-03-15 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1629 | Ebin | 2026-03-15 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1630 | Ebin | 2026-03-15 | Encogroup | Arunkumar Surendran | 127859069 | QC Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | _
1631 | Ebin | 2026-03-16 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
1632 | Ebin | 2026-03-16 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
1629 | Ebin | 2026-03-15 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1633 | Ebin | 2026-03-15 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1634 | Ebin | 2026-03-15 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1635 | Ebin | 2026-03-15 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1636 | Ebin | 2026-03-15 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1637 | Ebin | 2026-03-15 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1638 | Ebin | 2026-03-15 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1639 | Ebin | 2026-03-15 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1640 | Ebin | 2026-03-15 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1641 | Ebin | 2026-03-15 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1642 | Tamil | 2026-03-15 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1643 | Tamil | 2026-03-15 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1644 | Tamil | 2026-03-15 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material segregation of tower-9, pre-assembly of tower-4
1645 | Tamil | 2026-03-15 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-3 &paint touch-up works
1646 | Tamil | 2026-03-15 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Painting Coating | Surface cleaning | Surface cleaning | Painting touch-up- tower 6&7
1647 | Tamil | 2026-03-15 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1648 | Tamil | 2026-03-15 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1649 | Tamil | 2026-03-15 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1650 | Tamil | 2026-03-15 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
1651 | Tamil | 2026-03-15 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1652 | Tamil | 2026-03-15 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1653 | Tamil | 2026-03-15 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4,9 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-3 &paint touch-up works
1654 | Tamil | 2026-03-15 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
1655 | Tamil | 2026-03-15 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1656 | Tamil | 2026-03-15 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1657 | Tamil | 2026-03-15 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
1657 | Tamil | 2026-03-15 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
1657 | Tamil | 2026-03-15 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
1657 | Tamil | 2026-03-15 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1658 | Tamil | 2026-03-15 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1659 | Tamil | 2026-03-15 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Common Area | _ |  | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
1660 | Tamil | 2026-03-15 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | _ | _ | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1660 | Tamil | 2026-03-15 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ |  | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
1658 | Tamil | 2026-03-15 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1661 | Tamil | 2026-03-15 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1662 | Tamil | 2026-03-15 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-9& 4 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1663 | Tamil | 2026-03-15 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1664 | Tamil | 2026-03-15 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1665 | Tamil | 2026-03-15 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1666 | Tamil | 2026-03-15 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1667 | Tamil | 2026-03-15 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1668 | Tamil | 2026-03-15 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-3 &paint touch-up works
1669 | Tamil | 2026-03-15 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1670 | Tamil | 2026-03-15 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-3 &paint touch-up works
1671 | Tamil | 2026-03-15 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
1671 | Tamil | 2026-03-15 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
1672 | Shijo | 2026-03-15 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1673 | Shijo | 2026-03-15 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1673 | Shijo | 2026-03-15 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-manted
1674 | Shijo | 2026-03-15 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1675 | Shijo | 2026-03-15 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works
1676 | Shijo | 2026-03-15 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 150T crawler crane is dis-manted
1677 | Shijo | 2026-03-15 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1678 | Shijo | 2026-03-15 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1679 | Shijo | 2026-03-15 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
1680 | Shijo | 2026-03-15 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1681 | Shijo | 2026-03-15 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1682 | Shijo | 2026-03-15 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1683 | Shijo | 2026-03-15 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1684 | Shijo | 2026-03-15 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1685 | Shijo | 2026-03-15 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1686 | Shijo | 2026-03-15 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1687 | Shijo | 2026-03-15 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1688 | Shijo | 2026-03-15 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1689 | Shijo | 2026-03-15 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1690 | Shijo | 2026-03-15 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
1691 | Shijo | 2026-03-15 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1692 | Shijo | 2026-03-15 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver
1693 | Shijo | 2026-03-15 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1694 | Shijo | 2026-03-15 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1695 | Shijo | 2026-03-15 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1696 | Shijo | 2026-03-15 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1697 | Shijo | 2026-03-15 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 6 | Material Handling | Material storage & preservation | Material storage & preservation | _
1698 | Shijo | 2026-03-15 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1699 | Shijo | 2026-03-15 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1700 | Shijo | 2026-03-15 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1701 | Shijo | 2026-03-15 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator | PARKING AREA
1702 | Shijo | 2026-03-15 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1703 | Shijo | 2026-03-15 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1704 | Shijo | 2026-03-15 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1705 | Shijo | 2026-03-15 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1706 | Shijo | 2026-03-15 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1707 | Shijo | 2026-03-15 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1708 | Shijo | 2026-03-15 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1709 | Shijo | 2026-03-15 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1710 | Shijo | 2026-03-15 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1711 | Shijo | 2026-03-15 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1712 | Shijo | 2026-03-15 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1713 | Shijo | 2026-03-15 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1714 | Shijo | 2026-03-15 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
1715 | Shijo | 2026-03-15 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1716 | Shijo | 2026-03-15 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1717 | Shijo | 2026-03-15 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 |  |  |  | 130T crawler crane is dis-manted
1718 | Shijo | 2026-03-15 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1719 | Shijo | 2026-03-15 | BG | MD Rizwan | #N/A | Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1719 | Shijo | 2026-03-15 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1720 | Shijo | 2026-03-15 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
1721 | Shijo | 2026-03-15 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
1722 | Shijo | 2026-03-15 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1723 | Shijo | 2026-03-15 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1724 | Shijo | 2026-03-15 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1725 | Shijo | 2026-03-15 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1726 | Shijo | 2026-03-15 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1727 | Shijo | 2026-03-15 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1728 | Shijo | 2026-03-15 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1729 | Shijo | 2026-03-15 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1730 | Shijo | 2026-03-15 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 material (Tower-9) case 43 & 130 Ton crawler crane to TR1010-26 assembly at parking area
1731 | Shijo | 2026-03-15 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | PARKING AREA
1732 | Ebin | 2026-03-16 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Went to outside of Vale for maintenance (oil change)and remained idle for the day once it returned to site at around 02.30 pm
1733 | Ebin | 2026-03-16 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | 70-ton crawler crane load test has been completed | YARD 2
1734 | Ebin | 2026-03-16 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1735 | Ebin | 2026-03-16 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1736 | Ebin | 2026-03-16 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1737 | Ebin | 2026-03-16 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1738 | Ebin | 2026-03-16 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1739 | Ebin | 2026-03-16 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1740 | Ebin | 2026-03-16 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed | YARD 2
1741 | Ebin | 2026-03-16 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1742 | Ebin | 2026-03-16 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Idle | 10 |  |  |  | Went to outside of Vale for maintenance (oil change)and remained idle for the day once it returned to site at around 02.30 pm
1743 | Ebin | 2026-03-16 | SARENS NASS | Moshin Saleem Salim AL-Shukaili | 14552941 | Crane Operator- 70T Hitachi Crawler crane | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane load test has been completed
1744 | Ebin | 2026-03-16 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1745 | Ebin | 2026-03-16 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1746 | Ebin | 2026-03-16 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1746 | Ebin | 2026-03-16 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1747 | Ebin | 2026-03-16 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1748 | Ebin | 2026-03-16 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1749 | Ebin | 2026-03-16 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1744 | Ebin | 2026-03-16 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70-ton crawler crane assembly&chassis assembly modification have been completed
1744 | Ebin | 2026-03-16 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1750 | Ebin | 2026-03-16 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1751 | Ebin | 2026-03-16 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Chassis Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70-ton crawler crane load test has been completed
1752 | Ebin | 2026-03-16 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 4 hrs | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | The crane worked around 4 hrs only; 6 am to 09.30 am, stopped its operation after 09:30 AM due to oil leakage problem and it went outside of Vale at 4 PM after receiving LOTO to access yard 2 gate
1753 | Ebin | 2026-03-16 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1754 | Ebin | 2026-03-16 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1755 | Ebin | 2026-03-16 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1756 | Ebin | 2026-03-16 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1757 | Ebin | 2026-03-16 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1758 | Ebin | 2026-03-16 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1759 | Ebin | 2026-03-16 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1760 | Ebin | 2026-03-16 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1760 | Ebin | 2026-03-16 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1761 | Ebin | 2026-03-16 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1762 | Ebin | 2026-03-16 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1763 | Ebin | 2026-03-16 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1764 | Ebin | 2026-03-16 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1765 | Ebin | 2026-03-16 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 3 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1766 | Ebin | 2026-03-16 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1767 | Ebin | 2026-03-16 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1768 | Ebin | 2026-03-16 | Encogroup | Sreejith Thekkedath Sivaraman | 141322471 | Welding Inspector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1769 | Ebin | 2026-03-16 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1770 | Ebin | 2026-03-16 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 3 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1771 | Ebin | 2026-03-16 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1772 | Ebin | 2026-03-16 | Bright Light | Subash H.K | 83935096 | Technician | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1773 | Ebin | 2026-03-16 | Bright Light | Praveen Prakash | #N/A | Technician | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1765 | Ebin | 2026-03-16 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1774 | Ebin | 2026-03-16 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1775 | Ebin | 2026-03-16 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1776 | Ebin | 2026-03-16 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1777 | Ebin | 2026-03-16 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | The crane worked around 4 hrs only; 6 am to 09.30 am, stopped its operation after 09:30 AM due to oil leakage problem and it went outside of Vale at 4 PM after receiving LOTO to access yard 2 gate
1778 | Ebin | 2026-03-16 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1779 | Ebin | 2026-03-16 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1780 | Ebin | 2026-03-16 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1781 | Ebin | 2026-03-16 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1782 | Tamil | 2026-03-16 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1783 | Tamil | 2026-03-16 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1784 | Tamil | 2026-03-16 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material segregation of tower-9, pre-assembly of tower-4
1785 | Tamil | 2026-03-16 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-4 &paint touch-up works
1786 | Tamil | 2026-03-16 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Painting Coating | Surface cleaning | Surface cleaning | Painting touch-up- tower 6&7
1787 | Tamil | 2026-03-16 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1788 | Tamil | 2026-03-16 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1789 | Tamil | 2026-03-16 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1790 | Tamil | 2026-03-16 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
1791 | Tamil | 2026-03-16 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1792 | Tamil | 2026-03-16 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1793 | Tamil | 2026-03-16 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4,9 | TR-1010-26 | Day | 9 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-4 &paint touch-up works
1794 | Tamil | 2026-03-16 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
1795 | Tamil | 2026-03-16 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1796 | Tamil | 2026-03-16 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1797 | Tamil | 2026-03-16 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1798 | Tamil | 2026-03-16 | Encogroup | Mathan Kumar | 140796986 | Mechanical QC | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1799 | Tamil | 2026-03-16 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 8 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
1800 | Tamil | 2026-03-16 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
1801 | Tamil | 2026-03-16 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1800 | Tamil | 2026-03-16 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1798 | Tamil | 2026-03-16 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1802 | Tamil | 2026-03-16 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1803 | Tamil | 2026-03-16 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-9& 4 | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1804 | Tamil | 2026-03-16 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1805 | Tamil | 2026-03-16 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 9 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1806 | Tamil | 2026-03-16 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Bolt Torquing of Tower- 04
1807 | Tamil | 2026-03-16 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1808 | Tamil | 2026-03-16 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1809 | Tamil | 2026-03-16 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&9 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-9, pre-assembly of tower-4
1810 | Tamil | 2026-03-16 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-4&paint touch-up works
1811 | Tamil | 2026-03-16 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1812 | Tamil | 2026-03-16 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material segregation of tower-8, pre-assembly of tower-4,torquing of tower-4&paint touch-up works
1813 | Tamil | 2026-03-16 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1813 | Tamil | 2026-03-16 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4&9 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
1814 | Shijo | 2026-03-16 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1815 | Shijo | 2026-03-16 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1815 | Shijo | 2026-03-16 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-manted
1816 | Shijo | 2026-03-16 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | 130T crawler crane is dis-manted
1817 | Shijo | 2026-03-16 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1818 | Shijo | 2026-03-16 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works
1819 | Shijo | 2026-03-16 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 150T crawler crane is dis-manted
1820 | Shijo | 2026-03-16 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 8 |  |  |  | 150T crawler crane is dis-manted
1821 | Shijo | 2026-03-16 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1822 | Shijo | 2026-03-16 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1823 | Shijo | 2026-03-16 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
1824 | Shijo | 2026-03-16 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1825 | Shijo | 2026-03-16 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1826 | Shijo | 2026-03-16 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1827 | Shijo | 2026-03-16 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 9 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1828 | Shijo | 2026-03-16 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1829 | Shijo | 2026-03-16 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1830 | Shijo | 2026-03-16 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1831 | Shijo | 2026-03-16 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1832 | Shijo | 2026-03-16 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1833 | Shijo | 2026-03-16 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1834 | Shijo | 2026-03-16 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 9 | Piping Works | Fit-up | Fit-up | TSF works
1835 | Shijo | 2026-03-16 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1836 | Shijo | 2026-03-16 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Yard 3 | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver
1837 | Shijo | 2026-03-16 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1838 | Shijo | 2026-03-16 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1839 | Shijo | 2026-03-16 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1840 | Shijo | 2026-03-16 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1841 | Shijo | 2026-03-16 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
1842 | Shijo | 2026-03-16 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1843 | Shijo | 2026-03-16 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1844 | Shijo | 2026-03-16 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator | PARKING AREA
1845 | Shijo | 2026-03-16 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1846 | Shijo | 2026-03-16 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1847 | Shijo | 2026-03-16 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1848 | Shijo | 2026-03-16 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1849 | Shijo | 2026-03-16 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1850 | Shijo | 2026-03-16 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1851 | Shijo | 2026-03-16 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1852 | Shijo | 2026-03-16 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1853 | Shijo | 2026-03-16 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1854 | Shijo | 2026-03-16 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1855 | Shijo | 2026-03-16 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1856 | Shijo | 2026-03-16 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1857 | Shijo | 2026-03-16 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
1858 | Shijo | 2026-03-16 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1859 | Shijo | 2026-03-16 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1860 | Shijo | 2026-03-16 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1861 | Shijo | 2026-03-16 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material tagging & segregation | Material storage & preservation | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1862 | Shijo | 2026-03-16 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
1863 | Shijo | 2026-03-16 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1864 | Shijo | 2026-03-16 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1865 | Shijo | 2026-03-16 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1866 | Shijo | 2026-03-16 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1867 | Shijo | 2026-03-16 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area | PARKING AREA
1868 | Shijo | 2026-03-16 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1869 | Shijo | 2026-03-16 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1870 | Shijo | 2026-03-16 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1871 | Shijo | 2026-03-16 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1872 | Shijo | 2026-03-16 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 27) & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1873 | Shijo | 2026-03-16 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | PARKING AREA
1874 | Ebin | 2026-03-17 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1875 | Ebin | 2026-03-17 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1876 | Ebin | 2026-03-17 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1877 | Ebin | 2026-03-17 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1878 | Ebin | 2026-03-17 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1879 | Ebin | 2026-03-17 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1880 | Ebin | 2026-03-17 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 4 hrs | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | The 100T telescopic crane came back to yard-2 at around 11:00 AM after receiving LOTO to access yard 2 gate
1881 | Ebin | 2026-03-17 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1882 | Ebin | 2026-03-17 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1883 | Ebin | 2026-03-17 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1884 | Ebin | 2026-03-17 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1885 | Ebin | 2026-03-17 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Electrical Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1886 | Ebin | 2026-03-17 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1887 | Ebin | 2026-03-17 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1888 | Ebin | 2026-03-17 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | _
1888 | Ebin | 2026-03-17 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
1889 | Ebin | 2026-03-17 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1890 | Ebin | 2026-03-17 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1891 | Ebin | 2026-03-17 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1892 | Ebin | 2026-03-17 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1893 | Ebin | 2026-03-17 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1894 | Ebin | 2026-03-17 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1895 | Ebin | 2026-03-17 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 3 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1896 | Ebin | 2026-03-17 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1897 | Ebin | 2026-03-17 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1898 | Ebin | 2026-03-17 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1899 | Ebin | 2026-03-17 | BUSHRA | Rashid | #N/A | Diesel Re-fueling team | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 1 | Diesel filling | Diesel filling | Diesel filling | _
1899 | Ebin | 2026-03-17 | BUSHRA | Adil | Not Required | Diesel Re-fueling team | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 1 | Diesel filling | Diesel filling | Diesel filling | _
1898 | Ebin | 2026-03-17 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1900 | Ebin | 2026-03-17 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1900 | Ebin | 2026-03-17 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1901 | Ebin | 2026-03-17 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1902 | Ebin | 2026-03-17 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1903 | Ebin | 2026-03-17 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1904 | Ebin | 2026-03-17 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1905 | Ebin | 2026-03-17 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | The100T telescopic crane came back to yard-2 at around 11:00 AM after receiving LOTO to access yard 2 gate
1906 | Ebin | 2026-03-17 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1907 | Ebin | 2026-03-17 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1908 | Ebin | 2026-03-17 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1909 | Ebin | 2026-03-17 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | _
1910 | Tamil | 2026-03-17 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Pre-assembly&torquing of tower-4
1911 | Tamil | 2026-03-17 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Painting touch-up, Pre-assembly&torquing of tower-4
1912 | Tamil | 2026-03-17 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane offloading& assembly, pre-assembly&torquing of tower-4
1913 | Tamil | 2026-03-17 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
1914 | Tamil | 2026-03-17 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | Crane assembly | TR-1010-26 | Idle | 10 |  |  |  | Crane Assembly is in-progress | _
1915 | Tamil | 2026-03-17 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | Crane assembly | TR-1010-26 | Idle | 10 |  |  |  | Crane Assembly is in-progress | _
1916 | Tamil | 2026-03-17 | Sarens Nass | Dinesh Yadav | 12284034 | Rigger | Sub Contactor | Sub Contactor | Parking Area | Crane assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Assembly is in-progress | _
1916 | Tamil | 2026-03-17 | Sarens Nass | Padmanaban Sevu | 77873529 | Mechanic | Sub Contactor | Sub Contactor | Common Area | Crane assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Assembly is in-progress | _
1917 | Tamil | 2026-03-17 | Sarens Nass | Rampratap Chauhan | 112346941 | Rigger | Sub Contactor | Sub Contactor | Common Area | Crane assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Assembly is in-progress | _
1918 | Tamil | 2026-03-17 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Day | 8 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
1916 | Tamil | 2026-03-17 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly& torquing of tower-4 &painting touch-up works
1919 | Tamil | 2026-03-17 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Painting Coating | Surface cleaning | Surface cleaning | Painting touch-up- tower 6&7
1920 | Tamil | 2026-03-17 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Pre-assembly&torquing of tower-4
1921 | Tamil | 2026-03-17 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1922 | Tamil | 2026-03-17 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Pre-assembly&torquing of tower-4
1923 | Tamil | 2026-03-17 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Pre-assembly&torquing of tower-4
1924 | Tamil | 2026-03-17 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly&torquing of tower-4
1925 | Tamil | 2026-03-17 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly& torquing of tower-4 &painting touch-up works
1926 | Tamil | 2026-03-17 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
1927 | Tamil | 2026-03-17 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly&torquing of tower-4
1928 | Tamil | 2026-03-17 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly& torquing of tower-4 &painting touch-up works
1929 | Tamil | 2026-03-17 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1930 | Tamil | 2026-03-17 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1931 | Tamil | 2026-03-17 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1932 | Tamil | 2026-03-17 | Encogroup | Mathan Kumar | 140796986 | Mechanical QC | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Pre-assembly&torquing of tower-4
1932 | Tamil | 2026-03-17 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly of tower-4&torquing
1933 | Tamil | 2026-03-17 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1934 | Tamil | 2026-03-17 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
1935 | Tamil | 2026-03-17 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Pre-assembly&torquing of tower-4
1936 | Tamil | 2026-03-17 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly&torquing of tower-4
1937 | Tamil | 2026-03-17 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly&torquing of tower-4
1938 | Tamil | 2026-03-17 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly&torquing of tower-4
1939 | Tamil | 2026-03-17 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly& torquing of tower-4 &painting touch-up works
1940 | Tamil | 2026-03-17 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
1941 | Tamil | 2026-03-17 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Common Area | _ |  | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
1942 | Tamil | 2026-03-17 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ |  | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
1941 | Tamil | 2026-03-17 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, pre-assembly& torquing of tower-4 &painting touch-up works
1943 | Tamil | 2026-03-17 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1943 | Tamil | 2026-03-17 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
1944 | Shijo | 2026-03-17 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3
1945 | Shijo | 2026-03-17 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3
1946 | Shijo | 2026-03-17 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1947 | Shijo | 2026-03-17 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1947 | Shijo | 2026-03-17 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1948 | Shijo | 2026-03-17 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works
1949 | Shijo | 2026-03-17 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 150T crawler crane is dis-manted
1950 | Shijo | 2026-03-17 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 6 |  |  |  | 150T crawler crane is dis-manted
1951 | Shijo | 2026-03-17 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1952 | Shijo | 2026-03-17 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1953 | Shijo | 2026-03-17 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
1954 | Shijo | 2026-03-17 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | No usage
1955 | Shijo | 2026-03-17 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | No usage
1956 | Shijo | 2026-03-17 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1957 | Shijo | 2026-03-17 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1958 | Shijo | 2026-03-17 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1959 | Shijo | 2026-03-17 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 130 Ton crawler crane parts to TR1010-26 assembly at parking area | TSF
1960 | Shijo | 2026-03-17 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1961 | Shijo | 2026-03-17 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 130 Ton crawler crane parts to TR1010-26 assembly at parking area | TSF
1962 | Shijo | 2026-03-17 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1963 | Shijo | 2026-03-17 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1964 | Shijo | 2026-03-17 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3 & 130 Ton crawler crane parts to TR1010-26 assembly at parking area | TSF
1965 | Shijo | 2026-03-17 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 130 Ton crawler crane parts to TR1010-26 assembly at parking area | TSF
1966 | Shijo | 2026-03-17 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
1967 | Shijo | 2026-03-17 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1968 | Shijo | 2026-03-17 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 9 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver
1969 | Shijo | 2026-03-17 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1970 | Shijo | 2026-03-17 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1971 | Shijo | 2026-03-17 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1972 | Shijo | 2026-03-17 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3
1973 | Shijo | 2026-03-17 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
1974 | Shijo | 2026-03-17 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1975 | Shijo | 2026-03-17 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1976 | Shijo | 2026-03-17 | ATS | Ali Haider | 100398391 | DRIVER | DRIVER | DRIVER | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1976 | Shijo | 2026-03-17 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator
1977 | Shijo | 2026-03-17 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1978 | Shijo | 2026-03-17 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1979 | Shijo | 2026-03-17 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1980 | Shijo | 2026-03-17 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
1981 | Shijo | 2026-03-17 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3
1982 | Shijo | 2026-03-17 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1983 | Shijo | 2026-03-17 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1984 | Shijo | 2026-03-17 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1985 | Shijo | 2026-03-17 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
1986 | Shijo | 2026-03-17 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 130 Ton crawler crane parts to TR1010-26 assembly at parking area | TSF
1987 | Shijo | 2026-03-17 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3 | TSF
1988 | Shijo | 2026-03-17 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 130 Ton crawler crane parts to TR1010-26 assembly at parking area | TSF
1989 | Shijo | 2026-03-17 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1990 | Shijo | 2026-03-17 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 130 Ton crawler crane parts to TR1010-26 assembly at parking area | TSF
1991 | Shijo | 2026-03-17 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
1992 | Shijo | 2026-03-17 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3 & 130 Ton crawler crane parts to TR1010-26 assembly at parking area
1993 | Shijo | 2026-03-17 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3 | TSF
1994 | Shijo | 2026-03-17 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3
1995 | Shijo | 2026-03-17 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material tagging & segregation | Material storage & preservation | Loading of CT1010-02 ( Case. 28) to yard-3 | TSF
1996 | Shijo | 2026-03-17 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1997 | Shijo | 2026-03-17 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
1998 | Shijo | 2026-03-17 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
1999 | Shijo | 2026-03-17 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2000 | Shijo | 2026-03-17 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3
2001 | Shijo | 2026-03-17 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3 | TSF
2002 | Shijo | 2026-03-17 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TSF works
2002 | Shijo | 2026-03-17 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2003 | Shijo | 2026-03-17 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2004 | Shijo | 2026-03-17 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2005 | Shijo | 2026-03-17 | ATS | Ali Haider | 100398391 | DRIVER | DRIVER | DRIVER | Common Area | _ | _ | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | TSF works
2005 | Shijo | 2026-03-17 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Common Area | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2005 | Shijo | 2026-03-17 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2006 | Shijo | 2026-03-17 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2007 | Shijo | 2026-03-17 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3 | TSF
2008 | Shijo | 2026-03-17 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of CT1010-02 ( Case. 28) to yard-3 | TSF
2009 | Shijo | 2026-03-17 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | TSF
2010 | Ebin | 2026-03-18 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2011 | Ebin | 2026-03-18 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2011 | Ebin | 2026-03-18 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2012 | Ebin | 2026-03-18 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Yard 3 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2013 | Ebin | 2026-03-18 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2014 | Ebin | 2026-03-18 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2014 | Ebin | 2026-03-18 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2015 | Ebin | 2026-03-18 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 4 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2014 | Ebin | 2026-03-18 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2014 | Ebin | 2026-03-18 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2014 | Ebin | 2026-03-18 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2012 | Ebin | 2026-03-18 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2016 | Ebin | 2026-03-18 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2017 | Ebin | 2026-03-18 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2018 | Ebin | 2026-03-18 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2019 | Ebin | 2026-03-18 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2020 | Ebin | 2026-03-18 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2021 | Ebin | 2026-03-18 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 042, CL 028), Offloading of 150T Hitachi crawler crane
2022 | Ebin | 2026-03-18 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2023 | Ebin | 2026-03-18 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2024 | Ebin | 2026-03-18 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2025 | Ebin | 2026-03-18 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2026 | Ebin | 2026-03-18 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2027 | Ebin | 2026-03-18 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2028 | Ebin | 2026-03-18 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2029 | Ebin | 2026-03-18 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2029 | Ebin | 2026-03-18 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2030 | Ebin | 2026-03-18 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2031 | Ebin | 2026-03-18 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2032 | Ebin | 2026-03-18 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2033 | Ebin | 2026-03-18 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2034 | Ebin | 2026-03-18 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 4 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2035 | Ebin | 2026-03-18 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2036 | Ebin | 2026-03-18 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2037 | Ebin | 2026-03-18 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2038 | Ebin | 2026-03-18 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2039 | Ebin | 2026-03-18 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2040 | Ebin | 2026-03-18 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2041 | Ebin | 2026-03-18 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2042 | Ebin | 2026-03-18 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2041 | Ebin | 2026-03-18 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2043 | Ebin | 2026-03-18 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2044 | Ebin | 2026-03-18 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2044 | Ebin | 2026-03-18 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2041 | Ebin | 2026-03-18 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2045 | Ebin | 2026-03-18 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2046 | Ebin | 2026-03-18 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2047 | Ebin | 2026-03-18 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 042, CL 028 along with material organization and segregation
2048 | Tamil | 2026-03-18 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2049 | Tamil | 2026-03-18 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Painting touch-up,Torquing of tower-3&4
2050 | Tamil | 2026-03-18 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane assembly
2051 | Tamil | 2026-03-18 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
2052 | Tamil | 2026-03-18 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | Crane assembly | TR-1010-26 | Idle | 10 |  |  |  | Crane Assembly is in-progress
2053 | Tamil | 2026-03-18 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | Crane assembly | TR-1010-26 | Idle | 10 |  |  |  | Crane Assembly is in-progress
2054 | Tamil | 2026-03-18 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Crane assembly, torquing of tower-3& 4 &painting touch-up works
2055 | Tamil | 2026-03-18 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower 3&4
2056 | Tamil | 2026-03-18 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2057 | Tamil | 2026-03-18 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
2058 | Tamil | 2026-03-18 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2059 | Tamil | 2026-03-18 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2060 | Tamil | 2026-03-18 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower 3&4
2061 | Tamil | 2026-03-18 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower-3& 4 &painting touch-up works
2062 | Tamil | 2026-03-18 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
2063 | Tamil | 2026-03-18 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 6 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly
2064 | Tamil | 2026-03-18 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, torquing of tower-3&4 &painting touch-up works
2065 | Tamil | 2026-03-18 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
2066 | Tamil | 2026-03-18 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
2067 | Tamil | 2026-03-18 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Crane assembly, torquing of tower 3&4
2068 | Tamil | 2026-03-18 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-5&6&7 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6&7
2069 | Tamil | 2026-03-18 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2070 | Tamil | 2026-03-18 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower 3&4
2071 | Tamil | 2026-03-18 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly
2072 | Tamil | 2026-03-18 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly
2073 | Tamil | 2026-03-18 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower-3& 4 &painting touch-up works
2074 | Tamil | 2026-03-18 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
2075 | Tamil | 2026-03-18 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower-3& 4 &painting touch-up works
2076 | Tamil | 2026-03-18 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2076 | Tamil | 2026-03-18 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
2077 | Tamil | 2026-03-18 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
2078 | Shijo | 2026-03-18 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2079 | Shijo | 2026-03-18 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2080 | Shijo | 2026-03-18 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2081 | Shijo | 2026-03-18 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2081 | Shijo | 2026-03-18 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works
2082 | Shijo | 2026-03-18 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 150T crawler crane is dis-manted & shifting to yard-3
2083 | Shijo | 2026-03-18 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 4 |  |  |  | 150T crawler crane is dis-mantled & shifting to yard-3
2084 | Shijo | 2026-03-18 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2085 | Shijo | 2026-03-18 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2086 | Shijo | 2026-03-18 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
2087 | Shijo | 2026-03-18 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2088 | Shijo | 2026-03-18 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | No usage
2089 | Shijo | 2026-03-18 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | No usage
2090 | Shijo | 2026-03-18 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2091 | Shijo | 2026-03-18 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2092 | Shijo | 2026-03-18 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3 | TSF
2093 | Shijo | 2026-03-18 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2094 | Shijo | 2026-03-18 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3 | TSF
2095 | Shijo | 2026-03-18 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2096 | Shijo | 2026-03-18 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2097 | Shijo | 2026-03-18 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2098 | Shijo | 2026-03-18 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2099 | Shijo | 2026-03-18 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3 | TSF
2100 | Shijo | 2026-03-18 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2101 | Shijo | 2026-03-18 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
2102 | Shijo | 2026-03-18 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2103 | Shijo | 2026-03-18 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver
2104 | Shijo | 2026-03-18 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation | TSF
2105 | Shijo | 2026-03-18 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2106 | Shijo | 2026-03-18 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2107 | Shijo | 2026-03-18 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2108 | Shijo | 2026-03-18 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
2109 | Shijo | 2026-03-18 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2110 | Shijo | 2026-03-18 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator
2111 | Shijo | 2026-03-18 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2112 | Shijo | 2026-03-18 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Laydown | _ | Crane Dis/Assembly | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Crane Diss-assembly
2113 | Shijo | 2026-03-18 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Laydown | _ | Crane Dis/Assembly | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Crane Diss-assembly
2114 | Shijo | 2026-03-18 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Crane Dis/Assembly | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Crane Diss-assembly
2115 | Shijo | 2026-03-18 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Laydown | _ | Crane Dis/Assembly | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Crane Diss-assembly
2112 | Shijo | 2026-03-18 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Laydown | _ | Crane Dis/Assembly | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Crane Diss-assembly
2116 | Shijo | 2026-03-18 | Al Jaber Heavy Lift | Shobuj Raza | #N/A | Technician | Manpower | Manpower | Laydown | _ | Crane Dis/Assembly | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Crane Diss-assembly
2112 | Shijo | 2026-03-18 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2117 | Shijo | 2026-03-18 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2118 | Shijo | 2026-03-18 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2119 | Shijo | 2026-03-18 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 4 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2120 | Shijo | 2026-03-18 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2121 | Shijo | 2026-03-18 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2122 | Shijo | 2026-03-18 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2123 | Shijo | 2026-03-18 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2124 | Shijo | 2026-03-18 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3 | TSF
2125 | Shijo | 2026-03-18 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2126 | Shijo | 2026-03-18 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3 | TSF
2127 | Shijo | 2026-03-18 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2128 | Shijo | 2026-03-18 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3 | TSF
2129 | Shijo | 2026-03-18 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2130 | Shijo | 2026-03-18 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2129 | Shijo | 2026-03-18 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
2131 | Shijo | 2026-03-18 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment
2131 | Shijo | 2026-03-18 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment
2131 | Shijo | 2026-03-18 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
2132 | Shijo | 2026-03-18 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
2131 | Shijo | 2026-03-18 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2133 | Shijo | 2026-03-18 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2134 | Shijo | 2026-03-18 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material tagging & segregation | Material storage & preservation | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2135 | Shijo | 2026-03-18 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2136 | Shijo | 2026-03-18 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2137 | Shijo | 2026-03-18 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2138 | Shijo | 2026-03-18 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2139 | Shijo | 2026-03-18 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3 | TSF
2140 | Shijo | 2026-03-18 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2141 | Shijo | 2026-03-18 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2142 | Shijo | 2026-03-18 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2143 | Shijo | 2026-03-18 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2144 | Shijo | 2026-03-18 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2145 | Shijo | 2026-03-18 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2146 | Shijo | 2026-03-18 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material CL006 ( Case. 14) to yard-3
2147 | Shijo | 2026-03-18 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | YARD 3
2148 | Ebin | 2026-03-19 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Offloading | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2149 | Ebin | 2026-03-19 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2150 | Ebin | 2026-03-19 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2151 | Ebin | 2026-03-19 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2152 | Ebin | 2026-03-19 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 4 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2152 | Ebin | 2026-03-19 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Offloading | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2152 | Ebin | 2026-03-19 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2152 | Ebin | 2026-03-19 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 8 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2152 | Ebin | 2026-03-19 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2153 | Ebin | 2026-03-19 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2154 | Ebin | 2026-03-19 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2155 | Ebin | 2026-03-19 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2156 | Ebin | 2026-03-19 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006) | YARD 2
2157 | Ebin | 2026-03-19 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2158 | Ebin | 2026-03-19 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2159 | Ebin | 2026-03-19 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material offloading and shifting to yard 2 (CL 006)
2160 | Ebin | 2026-03-19 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2161 | Ebin | 2026-03-19 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2162 | Ebin | 2026-03-19 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2163 | Ebin | 2026-03-19 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2164 | Ebin | 2026-03-19 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2165 | Ebin | 2026-03-19 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2166 | Ebin | 2026-03-19 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2167 | Ebin | 2026-03-19 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2167 | Ebin | 2026-03-19 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2168 | Ebin | 2026-03-19 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2169 | Ebin | 2026-03-19 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2170 | Ebin | 2026-03-19 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2171 | Ebin | 2026-03-19 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 3 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2172 | Ebin | 2026-03-19 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2173 | Ebin | 2026-03-19 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2174 | Ebin | 2026-03-19 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2175 | Ebin | 2026-03-19 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2176 | Ebin | 2026-03-19 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2171 | Ebin | 2026-03-19 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2177 | Ebin | 2026-03-19 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2178 | Ebin | 2026-03-19 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 4 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2179 | Ebin | 2026-03-19 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2180 | Ebin | 2026-03-19 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2181 | Ebin | 2026-03-19 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2182 | Ebin | 2026-03-19 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2183 | Ebin | 2026-03-19 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2184 | Ebin | 2026-03-19 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2185 | Ebin | 2026-03-19 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2186 | Ebin | 2026-03-19 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2187 | Ebin | 2026-03-19 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2188 | Ebin | 2026-03-19 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2189 | Ebin | 2026-03-19 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Offloading of materials from yard 3 to yard 2 such as CL 006 along with material organization and segregation
2190 | Tamil | 2026-03-19 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2191 | Tamil | 2026-03-19 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Painting touch-up,Torquing of tower-3&4
2192 | Tamil | 2026-03-19 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane assembly
2193 | Tamil | 2026-03-19 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
2194 | Tamil | 2026-03-19 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | Crane assembly | TR-1010-26 | Idle | 10 |  |  |  | Crane Assembly is completed
2195 | Tamil | 2026-03-19 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | Crane assembly | TR-1010-26 | Idle | 10 |  |  |  | Crane Assembly is completed
2196 | Tamil | 2026-03-19 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Crane assembly, torquing of tower-3& 4 &painting touch-up works
2197 | Tamil | 2026-03-19 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower 3&4
2198 | Tamil | 2026-03-19 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2199 | Tamil | 2026-03-19 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
2200 | Tamil | 2026-03-19 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2201 | Tamil | 2026-03-19 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 6 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2202 | Tamil | 2026-03-19 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower 3&4
2203 | Tamil | 2026-03-19 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower-3& 4 &painting touch-up works
2204 | Tamil | 2026-03-19 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
2205 | Tamil | 2026-03-19 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 6 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly
2206 | Tamil | 2026-03-19 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane offloading& assembly, torquing of tower-3&4 &painting touch-up works
2207 | Tamil | 2026-03-19 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5& 6
2208 | Tamil | 2026-03-19 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5& 6
2209 | Tamil | 2026-03-19 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Crane assembly, torquing of tower 3&4
2210 | Tamil | 2026-03-19 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5& 6
2211 | Tamil | 2026-03-19 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 8 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5& 6
2212 | Tamil | 2026-03-19 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-5&6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 5& 6
2213 | Tamil | 2026-03-19 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 3&4
2214 | Tamil | 2026-03-19 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower 3&4
2215 | Tamil | 2026-03-19 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly
2216 | Tamil | 2026-03-19 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 8 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly
2217 | Tamil | 2026-03-19 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower-3& 4 &painting touch-up works
2218 | Tamil | 2026-03-19 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
2219 | Tamil | 2026-03-19 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane assembly, torquing of tower-3& 4 &painting touch-up works
2220 | Tamil | 2026-03-19 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2220 | Tamil | 2026-03-19 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | Crane assembly, torquing of tower-3& 4 &painting touch-up works
2221 | Tamil | 2026-03-19 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
2222 | Shijo | 2026-03-19 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2223 | Shijo | 2026-03-19 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2224 | Shijo | 2026-03-19 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2225 | Shijo | 2026-03-19 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2225 | Shijo | 2026-03-19 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works
2226 | Shijo | 2026-03-19 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | 150T crawler crane is dis-manted & shifting to yard-3
2227 | Shijo | 2026-03-19 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Laydown | _ | Offloading | Idle | 4 |  |  |  | 150T crawler crane is dis-manted & shifting to yard-3
2228 | Shijo | 2026-03-19 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2229 | Shijo | 2026-03-19 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2230 | Shijo | 2026-03-19 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
2231 | Shijo | 2026-03-19 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2232 | Shijo | 2026-03-19 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | No usage
2233 | Shijo | 2026-03-19 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | No usage
2234 | Shijo | 2026-03-19 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2235 | Shijo | 2026-03-19 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2236 | Shijo | 2026-03-19 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2237 | Shijo | 2026-03-19 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2238 | Shijo | 2026-03-19 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2239 | Shijo | 2026-03-19 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2240 | Shijo | 2026-03-19 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2241 | Shijo | 2026-03-19 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2242 | Shijo | 2026-03-19 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2243 | Shijo | 2026-03-19 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2244 | Shijo | 2026-03-19 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2245 | Shijo | 2026-03-19 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 8 | Piping Works | Fit-up | Fit-up | TSF works
2246 | Shijo | 2026-03-19 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2247 | Shijo | 2026-03-19 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB driver
2248 | Shijo | 2026-03-19 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Site Office | _ | Offloading | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2249 | Shijo | 2026-03-19 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2250 | Shijo | 2026-03-19 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | Offloading | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2251 | Shijo | 2026-03-19 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2252 | Shijo | 2026-03-19 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | _
2253 | Shijo | 2026-03-19 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2254 | Shijo | 2026-03-19 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator
2255 | Shijo | 2026-03-19 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2256 | Shijo | 2026-03-19 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2257 | Shijo | 2026-03-19 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2258 | Shijo | 2026-03-19 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 8 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2259 | Shijo | 2026-03-19 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 4 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2260 | Shijo | 2026-03-19 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2261 | Shijo | 2026-03-19 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2262 | Shijo | 2026-03-19 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2263 | Shijo | 2026-03-19 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2264 | Shijo | 2026-03-19 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2265 | Shijo | 2026-03-19 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2266 | Shijo | 2026-03-19 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2267 | Shijo | 2026-03-19 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2268 | Shijo | 2026-03-19 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2269 | Shijo | 2026-03-19 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
2270 | Shijo | 2026-03-19 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2270 | Shijo | 2026-03-19 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2270 | Shijo | 2026-03-19 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
2270 | Shijo | 2026-03-19 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower
2270 | Shijo | 2026-03-19 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2271 | Shijo | 2026-03-19 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2272 | Shijo | 2026-03-19 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material tagging & segregation | Material storage & preservation | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2273 | Shijo | 2026-03-19 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2274 | Shijo | 2026-03-19 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2275 | Shijo | 2026-03-19 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2276 | Shijo | 2026-03-19 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2277 | Shijo | 2026-03-19 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2278 | Shijo | 2026-03-19 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2279 | Shijo | 2026-03-19 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2280 | Shijo | 2026-03-19 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2281 | Shijo | 2026-03-19 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2282 | Shijo | 2026-03-19 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2283 | Shijo | 2026-03-19 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2284 | Shijo | 2026-03-19 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2285 | Shijo | 2026-03-19 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver
2286 | Ebin | 2026-03-22 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material segregation
2287 | Ebin | 2026-03-22 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A | 70T Crawler Crane | Equipment | Equipment | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Inspection is on-going
2288 | Ebin | 2026-03-22 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Crane has not assembled yet
2289 | Ebin | 2026-03-22 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane has not assembled yet
2290 | Ebin | 2026-03-22 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Inspection is on-going
2291 | Ebin | 2026-03-22 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Inspection is on-going
2291 | Ebin | 2026-03-22 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Inspection is on-going
2291 | Ebin | 2026-03-22 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Inspection is on-going
2292 | Ebin | 2026-03-22 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Inspection is on-going
2291 | Ebin | 2026-03-22 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Inspection is on-going
2291 | Ebin | 2026-03-22 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material segregation
2293 | Ebin | 2026-03-22 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material segregation
2294 | Ebin | 2026-03-22 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material segregation
2295 | Ebin | 2026-03-22 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | 70T Crawler crane inspection is on going, Material segregation
2296 | Ebin | 2026-03-22 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material segregation
2297 | Ebin | 2026-03-22 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material segregation
2298 | Ebin | 2026-03-22 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material segregation
2299 | Ebin | 2026-03-22 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | 70T Crawler crane inspection is on going, Material segregation
2300 | Ebin | 2026-03-22 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | material organization,segregation and cleaning
2301 | Ebin | 2026-03-22 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | material organization,segregation and cleaning
2302 | Ebin | 2026-03-22 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2303 | Ebin | 2026-03-22 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2304 | Ebin | 2026-03-22 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2305 | Ebin | 2026-03-22 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2306 | Ebin | 2026-03-22 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2307 | Ebin | 2026-03-22 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | material organization,segregation and cleaning
2307 | Ebin | 2026-03-22 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | material organization,segregation and cleaning
2308 | Ebin | 2026-03-22 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2309 | Ebin | 2026-03-22 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2310 | Ebin | 2026-03-22 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2311 | Ebin | 2026-03-22 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2312 | Ebin | 2026-03-22 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | material organization,segregation and cleaning
2312 | Ebin | 2026-03-22 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | material organization,segregation and cleaning
2312 | Ebin | 2026-03-22 | Encogroup | Hassan Salah Mechhawi | 130805123 | Mechanic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | material organization,segregation and cleaning
2312 | Ebin | 2026-03-22 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2313 | Ebin | 2026-03-22 | Encogroup | Arunkumar Surendran | 127859069 | QC Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | material organization,segregation and cleaning
2312 | Ebin | 2026-03-22 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2314 | Ebin | 2026-03-22 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2315 | Ebin | 2026-03-22 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2316 | Ebin | 2026-03-22 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2317 | Ebin | 2026-03-22 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2318 | Ebin | 2026-03-22 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
| Ebin | 2026-03-22 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 2 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2319 | Ebin | 2026-03-22 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2320 | Ebin | 2026-03-22 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | material organization,segregation and cleaning
2321 | Ebin | 2026-03-22 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2322 | Ebin | 2026-03-22 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2323 | Ebin | 2026-03-22 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | material organization,segregation and cleaning
2324 | Ebin | 2026-03-22 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2325 | Ebin | 2026-03-22 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2326 | Ebin | 2026-03-22 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2327 | Ebin | 2026-03-22 | Encogroup | Shijo Saji | 140696356 | Mechanical engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2327 | Ebin | 2026-03-22 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | material organization,segregation and cleaning
2328 | Shijo | 2026-03-22 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2328 | Shijo | 2026-03-22 | Encogroup | Ashwin Shivaraman | 127414586 | HSE Officer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2328 | Shijo | 2026-03-22 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2328 | Shijo | 2026-03-22 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2328 | Shijo | 2026-03-22 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2328 | Shijo | 2026-03-22 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2328 | Tamil | 2026-03-22 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2329 | Tamil | 2026-03-22 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Painting touch-up,Torquing of tower-4
2330 | Tamil | 2026-03-22 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | No usage
2331 | Tamil | 2026-03-22 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane
2332 | Tamil | 2026-03-22 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator
2333 | Tamil | 2026-03-22 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Crane Assembly is completed
2334 | Tamil | 2026-03-22 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Crane Assembly is completed
2335 | Tamil | 2026-03-22 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works
2336 | Tamil | 2026-03-22 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2337 | Tamil | 2026-03-22 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
2338 | Tamil | 2026-03-22 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2339 | Tamil | 2026-03-22 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2340 | Tamil | 2026-03-22 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4&8&6 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works
2341 | Tamil | 2026-03-22 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4&8&6 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works
2342 | Tamil | 2026-03-22 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
2343 | Tamil | 2026-03-22 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | pre-assembly&torquing of tower-4
2344 | Tamil | 2026-03-22 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4&8&6 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works
2345 | Tamil | 2026-03-22 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2346 | Tamil | 2026-03-22 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2347 | Tamil | 2026-03-22 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | pre-assembly&torquing of tower-4
2348 | Tamil | 2026-03-22 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2349 | Tamil | 2026-03-22 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2350 | Tamil | 2026-03-22 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2351 | Tamil | 2026-03-22 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2352 | Tamil | 2026-03-22 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works
2353 | Tamil | 2026-03-22 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
2354 | Tamil | 2026-03-22 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works
2355 | Tamil | 2026-03-22 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2355 | Tamil | 2026-03-22 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
2356 | Tamil | 2026-03-22 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
2357 | Shijo | 2026-03-22 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2358 | Shijo | 2026-03-22 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Material segregation
2359 | Shijo | 2026-03-22 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Material segregation
2360 | Shijo | 2026-03-22 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2361 | Shijo | 2026-03-22 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2362 | Shijo | 2026-03-22 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2362 | Shijo | 2026-03-22 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works
2363 | Shijo | 2026-03-22 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2364 | Shijo | 2026-03-22 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2365 | Shijo | 2026-03-22 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 |  |  |  | _
2366 | Shijo | 2026-03-22 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2367 | Shijo | 2026-03-22 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2368 | Shijo | 2026-03-22 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2369 | Shijo | 2026-03-22 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2370 | Shijo | 2026-03-22 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2371 | Shijo | 2026-03-22 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2372 | Shijo | 2026-03-22 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2373 | Shijo | 2026-03-22 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2374 | Shijo | 2026-03-22 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2375 | Shijo | 2026-03-22 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2376 | Shijo | 2026-03-22 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2377 | Shijo | 2026-03-22 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2378 | Shijo | 2026-03-22 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2379 | Shijo | 2026-03-22 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2380 | Shijo | 2026-03-22 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | HIAB Driver Absent
2381 | Shijo | 2026-03-22 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Site Office | _ | Offloading | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2382 | Shijo | 2026-03-22 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2383 | Shijo | 2026-03-22 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Site Office | _ | Offloading | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2384 | Shijo | 2026-03-22 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2385 | Shijo | 2026-03-22 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
2386 | Shijo | 2026-03-22 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2387 | Shijo | 2026-03-22 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator
2388 | Shijo | 2026-03-22 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2389 | Shijo | 2026-03-22 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2390 | Shijo | 2026-03-22 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2391 | Shijo | 2026-03-22 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2392 | Shijo | 2026-03-22 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2393 | Shijo | 2026-03-22 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2394 | Shijo | 2026-03-22 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2395 | Shijo | 2026-03-22 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2396 | Shijo | 2026-03-22 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2397 | Shijo | 2026-03-22 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2398 | Shijo | 2026-03-22 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2399 | Shijo | 2026-03-22 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2400 | Shijo | 2026-03-22 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 3 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2401 | Shijo | 2026-03-22 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2402 | Shijo | 2026-03-22 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2403 | Shijo | 2026-03-22 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2400 | Shijo | 2026-03-22 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2404 | Shijo | 2026-03-22 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2405 | Shijo | 2026-03-22 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2406 | Shijo | 2026-03-22 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
2406 | Shijo | 2026-03-22 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Trailer driver absent
2407 | Shijo | 2026-03-22 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2408 | Shijo | 2026-03-22 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2409 | Shijo | 2026-03-22 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material tagging & segregation | Material storage & preservation | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2410 | Shijo | 2026-03-22 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2411 | Shijo | 2026-03-22 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2412 | Shijo | 2026-03-22 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2413 | Shijo | 2026-03-22 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2414 | Shijo | 2026-03-22 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2415 | Shijo | 2026-03-22 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2416 | Shijo | 2026-03-22 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2417 | Shijo | 2026-03-22 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2418 | Shijo | 2026-03-22 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2419 | Shijo | 2026-03-22 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 10 | Piping Works | Fit-up | Fit-up | TSF works
2420 | Shijo | 2026-03-22 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2421 | Shijo | 2026-03-22 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of 150T crawler crane & CT1010-02 column material BM245 (Case . 12), BM247 (Case 12), BM404 (Case 13)
2422 | Ebin | 2026-03-23 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2423 | Ebin | 2026-03-23 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A | 70T Crawler Crane | Equipment | Equipment | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2424 | Ebin | 2026-03-23 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2425 | Ebin | 2026-03-23 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2426 | Ebin | 2026-03-23 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2427 | Ebin | 2026-03-23 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2428 | Ebin | 2026-03-23 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2426 | Ebin | 2026-03-23 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2426 | Ebin | 2026-03-23 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2426 | Ebin | 2026-03-23 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2426 | Ebin | 2026-03-23 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2426 | Ebin | 2026-03-23 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2429 | Ebin | 2026-03-23 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 10 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2430 | Ebin | 2026-03-23 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 2 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2431 | Ebin | 2026-03-23 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2432 | Ebin | 2026-03-23 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2433 | Ebin | 2026-03-23 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 |  |  |  | Halting of Trailor Movement from Laydown Area to Yard- 3 due to Yard-3 Access Road Blockage (TR 1010.09 Counter Weight Arresting (Ocean Rubber ), Equipment & Manpower remained idle around 6 hours (Between 06:00 AM - 12:30 PM) |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2434 | Ebin | 2026-03-23 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2435 | Ebin | 2026-03-23 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2436 | Ebin | 2026-03-23 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2437 | Ebin | 2026-03-23 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2438 | Ebin | 2026-03-23 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2439 | Ebin | 2026-03-23 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2440 | Ebin | 2026-03-23 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2441 | Ebin | 2026-03-23 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2441 | Ebin | 2026-03-23 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2442 | Ebin | 2026-03-23 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2443 | Ebin | 2026-03-23 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2444 | Ebin | 2026-03-23 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 2 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2445 | Ebin | 2026-03-23 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2445 | Ebin | 2026-03-23 | Encogroup | Anandbabu subbiah | 81612139 | Mechanic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2446 | Ebin | 2026-03-23 | Encogroup | Sreejith Thekkedath Sivaraman | 141322471 | Welding Inspector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2445 | Ebin | 2026-03-23 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2445 | Ebin | 2026-03-23 | Encogroup | Arunkumar Surendran | 127859069 | QC Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2445 | Ebin | 2026-03-23 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2447 | Ebin | 2026-03-23 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2448 | Ebin | 2026-03-23 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2448 | Ebin | 2026-03-23 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2445 | Ebin | 2026-03-23 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2449 | Ebin | 2026-03-23 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2450 | Ebin | 2026-03-23 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2451 | Ebin | 2026-03-23 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2452 | Ebin | 2026-03-23 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2453 | Ebin | 2026-03-23 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2454 | Ebin | 2026-03-23 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2455 | Ebin | 2026-03-23 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2456 | Ebin | 2026-03-23 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2457 | Ebin | 2026-03-23 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2458 | Ebin | 2026-03-23 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2459 | Ebin | 2026-03-23 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2460 | Ebin | 2026-03-23 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2461 | Ebin | 2026-03-23 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2462 | Shijo | 2026-03-23 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2463 | Shijo | 2026-03-23 | Encogroup | Ashwin Shivaraman | 127414586 | HSE Officer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2462 | Shijo | 2026-03-23 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2464 | Shijo | 2026-03-23 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2462 | Shijo | 2026-03-23 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2462 | Shijo | 2026-03-23 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Preparation works and marking on-going
2462 | Tamil | 2026-03-23 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2465 | Tamil | 2026-03-23 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Painting touch-up,Torquing of tower-4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2466 | Tamil | 2026-03-23 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2467 | Tamil | 2026-03-23 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2468 | Tamil | 2026-03-23 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Crane Operator |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2469 | Tamil | 2026-03-23 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | Column stacking | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2470 | Tamil | 2026-03-23 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | Column stacking | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2471 | Tamil | 2026-03-23 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | _ | TR-1010-26 | Idle |  | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2472 | Tamil | 2026-03-23 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Common Area | [9 empty] | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2473 | Tamil | 2026-03-23 | Encogroup | Mathan Kumar | 140796986 | Mechanical QC | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2474 | Tamil | 2026-03-23 | Sarens Nass | Rampratap Chauhan | 112346941 | Rigger | Sub Contactor | Sub Contactor | Parking Area | Crane assembly | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2475 | Tamil | 2026-03-23 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | _ |  | Idle | 5 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2476 | Tamil | 2026-03-23 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area |  |  | Idle | 5 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2477 | Tamil | 2026-03-23 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | _ |  | Idle | 5 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2474 | Tamil | 2026-03-23 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Parking Area | _ |  | Idle | 5 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2471 | Tamil | 2026-03-23 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2478 | Tamil | 2026-03-23 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2479 | Tamil | 2026-03-23 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2480 | Tamil | 2026-03-23 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | pre-assembly&torquing of tower-4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2480 | Tamil | 2026-03-23 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2481 | Tamil | 2026-03-23 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2482 | Tamil | 2026-03-23 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-4&8&6 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2483 | Tamil | 2026-03-23 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-4&8&6 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2484 | Tamil | 2026-03-23 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2485 | Tamil | 2026-03-23 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns,pre-assembly of tower-8,offloading of packages 23&44 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2486 | Tamil | 2026-03-23 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns,pre-assembly of tower-8,offloading of packages 23&44 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2485 | Tamil | 2026-03-23 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | pre-assembly&torquing of tower-4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2487 | Tamil | 2026-03-23 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4&8&6 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2488 | Tamil | 2026-03-23 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2489 | Tamil | 2026-03-23 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2490 | Tamil | 2026-03-23 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-4 | TR-1010-26 | Idle | 5 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | pre-assembly&torquing of tower-4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2491 | Tamil | 2026-03-23 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2492 | Tamil | 2026-03-23 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2493 | Tamil | 2026-03-23 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2494 | Tamil | 2026-03-23 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2495 | Tamil | 2026-03-23 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2496 | Tamil | 2026-03-23 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2497 | Tamil | 2026-03-23 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, pre-assembly&torquing of tower-4 &painting touch-up works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2498 | Tamil | 2026-03-23 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2498 | Tamil | 2026-03-23 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2499 | Tamil | 2026-03-23 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2500 | Shijo | 2026-03-23 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2501 | Shijo | 2026-03-23 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2502 | Shijo | 2026-03-23 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2503 | Shijo | 2026-03-23 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2504 | Shijo | 2026-03-23 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2505 | Shijo | 2026-03-23 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2505 | Shijo | 2026-03-23 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2506 | Shijo | 2026-03-23 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2507 | Shijo | 2026-03-23 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2508 | Shijo | 2026-03-23 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2509 | Shijo | 2026-03-23 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2510 | Shijo | 2026-03-23 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2511 | Shijo | 2026-03-23 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2512 | Shijo | 2026-03-23 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2513 | Shijo | 2026-03-23 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2514 | Shijo | 2026-03-23 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2515 | Shijo | 2026-03-23 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2516 | Shijo | 2026-03-23 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2517 | Shijo | 2026-03-23 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2518 | Shijo | 2026-03-23 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2519 | Shijo | 2026-03-23 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2520 | Shijo | 2026-03-23 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2521 | Shijo | 2026-03-23 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2522 | Shijo | 2026-03-23 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2523 | Shijo | 2026-03-23 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2524 | Shijo | 2026-03-23 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB DRIVER |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2525 | Shijo | 2026-03-23 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2526 | Shijo | 2026-03-23 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2527 | Shijo | 2026-03-23 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2528 | Shijo | 2026-03-23 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2529 | Shijo | 2026-03-23 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2530 | Shijo | 2026-03-23 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2531 | Shijo | 2026-03-23 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2532 | Shijo | 2026-03-23 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator | PARKING AREA | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2533 | Shijo | 2026-03-23 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2534 | Shijo | 2026-03-23 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2535 | Shijo | 2026-03-23 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2536 | Shijo | 2026-03-23 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2537 | Shijo | 2026-03-23 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2538 | Shijo | 2026-03-23 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2539 | Shijo | 2026-03-23 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2540 | Shijo | 2026-03-23 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2541 | Shijo | 2026-03-23 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2542 | Shijo | 2026-03-23 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2543 | Shijo | 2026-03-23 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2544 | Shijo | 2026-03-23 | Encogroup | Muhammed Yasir | 118882687 | Permit Reciver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2545 | Shijo | 2026-03-23 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 3 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2546 | Shijo | 2026-03-23 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 3 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
| Shijo | 2026-03-23 | Encogroup | Syed Ihsan Haider | 100398391 | DuqmTrailer Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Duqm trailer offloading
2543 | Shijo | 2026-03-23 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2547 | Shijo | 2026-03-23 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2547 | Shijo | 2026-03-23 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2547 | Shijo | 2026-03-23 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | _
2548 | Shijo | 2026-03-23 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
2547 | Shijo | 2026-03-23 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2549 | Shijo | 2026-03-23 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | PARKING AREA | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2550 | Shijo | 2026-03-23 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2551 | Shijo | 2026-03-23 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2552 | Shijo | 2026-03-23 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2552 | Shijo | 2026-03-23 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2552 | Shijo | 2026-03-23 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2552 | Shijo | 2026-03-23 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material tagging & segregation | Material storage & preservation | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2553 | Shijo | 2026-03-23 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2554 | Shijo | 2026-03-23 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2555 | Shijo | 2026-03-23 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2556 | Shijo | 2026-03-23 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2557 | Shijo | 2026-03-23 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2558 | Shijo | 2026-03-23 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2559 | Shijo | 2026-03-23 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2560 | Shijo | 2026-03-23 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2561 | Shijo | 2026-03-23 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2562 | Shijo | 2026-03-23 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2563 | Shijo | 2026-03-23 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2564 | Shijo | 2026-03-23 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2565 | Ebin | 2026-03-24 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2566 | Ebin | 2026-03-24 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A | 70T Crawler Crane | Equipment | Equipment | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2567 | Ebin | 2026-03-24 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2568 | Ebin | 2026-03-24 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2569 | Ebin | 2026-03-24 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2570 | Ebin | 2026-03-24 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2571 | Ebin | 2026-03-24 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2572 | Ebin | 2026-03-24 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2573 | Ebin | 2026-03-24 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2574 | Ebin | 2026-03-24 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2573 | Ebin | 2026-03-24 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2575 | Ebin | 2026-03-24 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2573 | Ebin | 2026-03-24 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2573 | Ebin | 2026-03-24 | BUSHRA | Rashid | #N/A | Diesel Re-fueling team | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Diesel filling | Diesel filling | Diesel filling | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2576 | Ebin | 2026-03-24 | BUSHRA | Adil | Not Required | Diesel Re-fueling team | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Diesel filling | Diesel filling | Diesel filling | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2573 | Ebin | 2026-03-24 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2577 | Ebin | 2026-03-24 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2577 | Ebin | 2026-03-24 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2578 | Ebin | 2026-03-24 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2579 | Ebin | 2026-03-24 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled.
2580 | Ebin | 2026-03-24 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2581 | Ebin | 2026-03-24 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2582 | Ebin | 2026-03-24 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2583 | Ebin | 2026-03-24 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2584 | Ebin | 2026-03-24 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2585 | Ebin | 2026-03-24 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2585 | Ebin | 2026-03-24 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2586 | Ebin | 2026-03-24 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2587 | Ebin | 2026-03-24 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2587 | Ebin | 2026-03-24 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2588 | Ebin | 2026-03-24 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2589 | Ebin | 2026-03-24 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2590 | Ebin | 2026-03-24 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2591 | Ebin | 2026-03-24 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2592 | Ebin | 2026-03-24 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2593 | Ebin | 2026-03-24 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2594 | Ebin | 2026-03-24 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2595 | Ebin | 2026-03-24 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2596 | Ebin | 2026-03-24 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2597 | Ebin | 2026-03-24 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2597 | Ebin | 2026-03-24 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2597 | Ebin | 2026-03-24 | Encogroup | Arunkumar Surendran | 127859069 | QC Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2597 | Ebin | 2026-03-24 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2597 | Ebin | 2026-03-24 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2598 | Ebin | 2026-03-24 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2599 | Ebin | 2026-03-24 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2600 | Ebin | 2026-03-24 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2601 | Ebin | 2026-03-24 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2602 | Ebin | 2026-03-24 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2603 | Ebin | 2026-03-24 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation
2604 | Shijo | 2026-03-24 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation
2604 | Shijo | 2026-03-24 | Encogroup | Ashwin Shivaraman | 127414586 | HSE Officer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation
2604 | Shijo | 2026-03-24 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation | LAYDOWN
2605 | Shijo | 2026-03-24 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation
2604 | Shijo | 2026-03-24 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation
2604 | Shijo | 2026-03-24 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation
2606 | Shijo | 2026-03-24 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation
2604 | Shijo | 2026-03-24 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2607 | Shijo | 2026-03-24 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Painting touch-up,Torquing of tower-4
2608 | Shijo | 2026-03-24 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 10 |  |  |  | No usage
2609 | Shijo | 2026-03-24 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
2610 | Shijo | 2026-03-24 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Pre-assembly of tower-8, material offloading of tower-9&10, stacking of columns
2611 | Shijo | 2026-03-24 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns
2612 | Shijo | 2026-03-24 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns
2613 | Shijo | 2026-03-24 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
2614 | Shijo | 2026-03-24 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _
2615 | Shijo | 2026-03-24 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2616 | Shijo | 2026-03-24 | Encogroup | Mathan Kumar | 140796986 | Mechanical QC | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2617 | Shijo | 2026-03-24 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2618 | Shijo | 2026-03-24 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | _
2619 | Shijo | 2026-03-24 | Encogroup | Anandbabu subbiah | 81612139 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
2613 | Shijo | 2026-03-24 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-8,9,10&6 | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns
2620 | Shijo | 2026-03-24 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2621 | Shijo | 2026-03-24 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
2622 | Shijo | 2026-03-24 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | pre-assembly&torquing of tower-4
2623 | Shijo | 2026-03-24 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2624 | Shijo | 2026-03-24 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2625 | Shijo | 2026-03-24 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns
2626 | Shijo | 2026-03-24 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-8,9,10&6 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns
2627 | Shijo | 2026-03-24 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper
2628 | Shijo | 2026-03-24 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns,pre-assembly of tower-8,offloading of packages 23&44
2629 | Shijo | 2026-03-24 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns,pre-assembly of tower-8,offloading of packages 23&44
2630 | Shijo | 2026-03-24 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | pre-assembly&torquing of tower-4
2631 | Shijo | 2026-03-24 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4&8&6 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns
2632 | Shijo | 2026-03-24 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2633 | Shijo | 2026-03-24 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2634 | Shijo | 2026-03-24 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | pre-assembly&torquing of tower-4
2635 | Shijo | 2026-03-24 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2636 | Shijo | 2026-03-24 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2637 | Shijo | 2026-03-24 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2638 | Shijo | 2026-03-24 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns
2638 | Shijo | 2026-03-24 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4
2639 | Shijo | 2026-03-24 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-8,9,10&6 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns
2640 | Shijo | 2026-03-24 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man
2641 | Shijo | 2026-03-24 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2641 | Shijo | 2026-03-24 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
2642 | Shijo | 2026-03-24 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
2643 | Shijo | 2026-03-24 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2644 | Shijo | 2026-03-24 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2645 | Shijo | 2026-03-24 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2646 | Shijo | 2026-03-24 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Day | 5 |  |  |  | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2645 | Shijo | 2026-03-24 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2647 | Shijo | 2026-03-24 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2647 | Shijo | 2026-03-24 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works
2648 | Shijo | 2026-03-24 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2649 | Shijo | 2026-03-24 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2650 | Shijo | 2026-03-24 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _
2651 | Shijo | 2026-03-24 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2652 | Shijo | 2026-03-24 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2653 | Shijo | 2026-03-24 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2654 | Shijo | 2026-03-24 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2655 | Shijo | 2026-03-24 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2656 | Shijo | 2026-03-24 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2657 | Shijo | 2026-03-24 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2658 | Shijo | 2026-03-24 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works
2659 | Shijo | 2026-03-24 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works
2660 | Shijo | 2026-03-24 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2661 | Shijo | 2026-03-24 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2662 | Shijo | 2026-03-24 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. | TSF
2663 | Shijo | 2026-03-24 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. | TSF
2664 | Shijo | 2026-03-24 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works
2665 | Shijo | 2026-03-24 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | _
2666 | Shijo | 2026-03-24 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB DRIVER
2667 | Shijo | 2026-03-24 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. | TSF
2668 | Shijo | 2026-03-24 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2669 | Shijo | 2026-03-24 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2670 | Shijo | 2026-03-24 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2671 | Shijo | 2026-03-22 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2671 | Shijo | 2026-03-24 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2672 | Shijo | 2026-03-24 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
2673 | Shijo | 2026-03-24 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2673 | Shijo | 2026-03-24 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2674 | Shijo | 2026-03-24 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator | PARKING AREA
2675 | Shijo | 2026-03-24 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2676 | Shijo | 2026-03-24 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2677 | Shijo | 2026-03-24 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation
2678 | Shijo | 2026-03-24 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2679 | Shijo | 2026-03-24 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2680 | Shijo | 2026-03-24 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2681 | Shijo | 2026-03-24 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _
2682 | Shijo | 2026-03-24 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2683 | Shijo | 2026-03-24 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2684 | Shijo | 2026-03-24 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2685 | Shijo | 2026-03-24 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2686 | Shijo | 2026-03-24 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2686 | Shijo | 2026-03-24 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2686 | Shijo | 2026-03-24 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2687 | Shijo | 2026-03-24 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Offloading | Night | 5 |  |  |  | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2686 | Shijo | 2026-03-24 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | _
2688 | Shijo | 2026-03-24 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver | PARKING AREA
2689 | Shijo | 2026-03-24 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2690 | Shijo | 2026-03-24 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2691 | Shijo | 2026-03-24 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material tagging & segregation | Material storage & preservation | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2692 | Shijo | 2026-03-24 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2693 | Shijo | 2026-03-24 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material tagging & segregation | Material storage & preservation | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2693 | Shijo | 2026-03-24 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN
2694 | Shijo | 2026-03-24 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2695 | Shijo | 2026-03-24 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2696 | Shijo | 2026-03-24 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2697 | Shijo | 2026-03-24 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works
2698 | Shijo | 2026-03-24 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works
2699 | Shijo | 2026-03-24 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works
2700 | Shijo | 2026-03-24 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Day | 5 | Piping Works | Fit-up | Fit-up | TSF works
2701 | Shijo | 2026-03-24 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2701 | Shijo | 2026-03-24 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2702 | Shijo | 2026-03-24 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2703 | Ebin | 2026-03-25 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2704 | Ebin | 2026-03-25 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A | 70T Crawler Crane | Equipment | Equipment | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2705 | Ebin | 2026-03-25 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | Offloading | CT-1010-02 | Idle | 2 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2706 | Ebin | 2026-03-25 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2707 | Ebin | 2026-03-25 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2708 | Ebin | 2026-03-25 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 2 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2709 | Ebin | 2026-03-25 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2710 | Ebin | 2026-03-25 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2709 | Ebin | 2026-03-25 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2711 | Ebin | 2026-03-25 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2709 | Ebin | 2026-03-25 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2709 | Ebin | 2026-03-25 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2712 | Ebin | 2026-03-25 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Common Area | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2709 | Ebin | 2026-03-25 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2713 | Ebin | 2026-03-25 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2714 | Ebin | 2026-03-25 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2715 | Ebin | 2026-03-25 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2716 | Ebin | 2026-03-25 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2717 | Ebin | 2026-03-25 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Offloading | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | CT1010-02 material offloading of BM 092, BM 375, BM 376 and shifting of BM 092 to yard-2 and the 150T crawler crane assembly is underway, with the chain being assembled. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2718 | Ebin | 2026-03-25 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2719 | Ebin | 2026-03-25 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2720 | Ebin | 2026-03-25 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2721 | Ebin | 2026-03-25 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2722 | Ebin | 2026-03-25 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2723 | Ebin | 2026-03-25 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2724 | Ebin | 2026-03-25 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2725 | Ebin | 2026-03-25 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Strucutre Pre-Assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2725 | Ebin | 2026-03-25 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2726 | Ebin | 2026-03-25 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2727 | Ebin | 2026-03-25 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2728 | Ebin | 2026-03-25 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2729 | Ebin | 2026-03-25 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2730 | Ebin | 2026-03-25 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2731 | Ebin | 2026-03-25 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2732 | Ebin | 2026-03-25 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2733 | Ebin | 2026-03-25 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2734 | Ebin | 2026-03-25 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation | YARD 3 | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2735 | Ebin | 2026-03-25 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation | YARD 3 | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2736 | Ebin | 2026-03-25 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation | YARD 3 | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2735 | Ebin | 2026-03-25 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Electrical Works | Strucutre Pre-Assembly | Electrical testing | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2737 | Ebin | 2026-03-25 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2738 | Ebin | 2026-03-25 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2739 | Ebin | 2026-03-25 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2740 | Ebin | 2026-03-25 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2741 | Ebin | 2026-03-25 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2742 | Ebin | 2026-03-25 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Material Offloading of case no. 06& BM 092 from yard-3 and its segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2743 | Shijo | 2026-03-25 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation,Material Shifting to substation is on-going |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2743 | Shijo | 2026-03-25 | Encogroup | Ashwin Shivaraman | 127414586 | HSE Officer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation,Material Shifting to substation is on-going |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2744 | Shijo | 2026-03-25 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation,Material Shifting to substation is on-going | LAYDOWN | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2743 | Shijo | 2026-03-25 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation,Material Shifting to substation is on-going |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2745 | Shijo | 2026-03-25 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation,Material Shifting to substation is on-going |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2743 | Shijo | 2026-03-25 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation,Material Shifting to substation is on-going |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2743 | Shijo | 2026-03-25 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 5 | Electrical Works | Electrical Works | Cable tray support installation | Cable Tray Support Installation inside Reclaimer Substation, Drilling for base plate support fixation,Material Shifting to substation is on-going |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2743 | Shijo | 2026-03-25 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2746 | Shijo | 2026-03-25 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Painting touch-up,Torquing of tower-4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2747 | Shijo | 2026-03-25 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2748 | Shijo | 2026-03-25 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2749 | Shijo | 2026-03-25 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Pre-assembly of tower-8, material offloading of tower-9&10, stacking of columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2750 | Shijo | 2026-03-25 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2751 | Shijo | 2026-03-25 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2752 | Shijo | 2026-03-25 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Tower-8,9,10&6 | TR-1010-26 | Idle | 5 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2753 | Shijo | 2026-03-25 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 | _ | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2754 | Shijo | 2026-03-25 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 | _ | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2754 | Shijo | 2026-03-25 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2755 | Shijo | 2026-03-25 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Tower-4&8 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | pre-assembly&torquing of tower-4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2756 | Shijo | 2026-03-25 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2757 | Shijo | 2026-03-25 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2758 | Shijo | 2026-03-25 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2759 | Shijo | 2026-03-25 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Tower-8,9,10&6 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2760 | Shijo | 2026-03-25 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Store keeper |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2761 | Shijo | 2026-03-25 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns,pre-assembly of tower-8,offloading of packages 23&44 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2762 | Shijo | 2026-03-25 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Stacking of structural steel columns,pre-assembly of tower-8,offloading of packages 23&44 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2763 | Shijo | 2026-03-25 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | pre-assembly&torquing of tower-4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2764 | Shijo | 2026-03-25 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Tower-4&8&6 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2765 | Shijo | 2026-03-25 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns | _ | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2766 | Shijo | 2026-03-25 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 5 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _ | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2767 | Shijo | 2026-03-25 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 5 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | _ | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2768 | Shijo | 2026-03-25 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Common Area | _ | TR-1010-26 | Idle | 5 | Electrical Works | Electrical Works | Electrical Works | Electrical Works | _ | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2769 | Shijo | 2026-03-25 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | _ | TR-1010-26 | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ | _ | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2769 | Shijo | 2026-03-25 | Encogroup | Anandbabu subbiah | 81612139 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Idle | 5 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _ | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2766 | Shijo | 2026-03-25 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2770 | Shijo | 2026-03-25 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | pre-assembly&torquing of tower-4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2771 | Shijo | 2026-03-25 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2772 | Shijo | 2026-03-25 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2773 | Shijo | 2026-03-25 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2774 | Shijo | 2026-03-25 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Parking Area | Tower-6 | TR-1010-26 | Idle | 5 | Painting Coating | Touch-up painting | Touch-up painting | Painting touch-up- tower 6 & columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2775 | Shijo | 2026-03-25 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-4&3 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Torquing of tower- 4 |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2776 | Shijo | 2026-03-25 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Tower-8,9,10&6 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Pre-assembly of tower-8, material offloading of tower-9&10, Torquing of tower-3& 4 &painting touch-up works, stacking of columns |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2777 | Shijo | 2026-03-25 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Signal-Man |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2778 | Shijo | 2026-03-25 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2778 | Shijo | 2026-03-25 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2779 | Shijo | 2026-03-25 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Tower-8&9&10 | TR-1010-26 | Idle | 5 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2780 | Shijo | 2026-03-25 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2781 | Shijo | 2026-03-25 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 3 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2782 | Shijo | 2026-03-25 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown | _ | Offloading | Idle | 3 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2781 | Shijo | 2026-03-25 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2783 | Shijo | 2026-03-25 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2784 | Shijo | 2026-03-25 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2784 | Shijo | 2026-03-25 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Strucutre Pre-Assembly | Used for Enco works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2785 | Shijo | 2026-03-25 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2786 | Shijo | 2026-03-25 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2787 | Shijo | 2026-03-25 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2788 | Shijo | 2026-03-25 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2789 | Shijo | 2026-03-25 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2790 | Shijo | 2026-03-25 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2791 | Shijo | 2026-03-25 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2792 | Shijo | 2026-03-25 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2793 | Shijo | 2026-03-25 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2794 | Shijo | 2026-03-25 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2795 | Shijo | 2026-03-25 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2796 | Shijo | 2026-03-25 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2797 | Shijo | 2026-03-25 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2798 | Shijo | 2026-03-25 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2799 | Shijo | 2026-03-25 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. | TSF | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2800 | Shijo | 2026-03-25 | Encogroup | Muhammed Yasir | 118882687 | Permit Reciver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. | TSF | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2801 | Shijo | 2026-03-25 | OCI | Azhar | not required | DRIVER | DRIVER | DRIVER | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2801 | Shijo | 2026-03-25 | OCI | Tanveer | #N/A | DRIVER | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
2800 | Shijo | 2026-03-25 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2802 | Shijo | 2026-03-25 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2803 | Shijo | 2026-03-25 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2804 | Shijo | 2026-03-25 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | HIAB DRIVER |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2805 | Shijo | 2026-03-25 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2806 | Shijo | 2026-03-25 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2807 | Shijo | 2026-03-25 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2808 | Shijo | 2026-03-25 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2809 | Shijo | 2026-03-25 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2810 | Shijo | 2026-03-25 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2811 | Shijo | 2026-03-25 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2812 | Shijo | 2026-03-25 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2811 | Shijo | 2026-03-25 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2813 | Shijo | 2026-03-25 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Fork-lift operator |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2814 | Shijo | 2026-03-25 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2815 | Shijo | 2026-03-25 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2816 | Shijo | 2026-03-25 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Idle | 5 | Material Handling | Material storage & preservation | Material storage & preservation | Inspection&Preservation of idler rollers& Material segregation |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2817 | Shijo | 2026-03-25 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2818 | Shijo | 2026-03-25 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2819 | Shijo | 2026-03-25 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2820 | Shijo | 2026-03-25 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | _ |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2821 | Shijo | 2026-03-25 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2822 | Shijo | 2026-03-25 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2823 | Shijo | 2026-03-25 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2824 | Shijo | 2026-03-25 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2825 | Shijo | 2026-03-25 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2825 | Shijo | 2026-03-25 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2825 | Shijo | 2026-03-25 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | _
2826 | Shijo | 2026-03-25 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Offloading | Day | 8 | Material Handling | Material unloading by crane | Material unloading by crane | _
2825 | Shijo | 2026-03-25 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2827 | Shijo | 2026-03-25 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Trailer driver |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2828 | Shijo | 2026-03-25 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2829 | Shijo | 2026-03-25 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2830 | Shijo | 2026-03-25 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2831 | Shijo | 2026-03-25 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2832 | Shijo | 2026-03-25 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works | LAYDOWN | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2833 | Shijo | 2026-03-25 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2833 | Shijo | 2026-03-25 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2834 | Shijo | 2026-03-25 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | No usage |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2835 | Shijo | 2026-03-25 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower
2836 | Shijo | 2026-03-25 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 3 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area.
|  |  | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower
2835 | Shijo | 2026-03-25 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2837 | Shijo | 2026-03-25 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Site Office | _ | _ | Idle | 2 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2838 | Shijo | 2026-03-25 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2839 | Shijo | 2026-03-25 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2840 | Shijo | 2026-03-25 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Site Office | _ | _ | Idle | 5 | Piping Works | Fit-up | Fit-up | TSF works |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2841 | Shijo | 2026-03-25 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2842 | Shijo | 2026-03-25 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 Package No. 23 ( Tower- 10) and Package No. 44 ( Tower- 9 ) from laydown area to contractor's parking area. |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2843 | Ebin | 2026-03-26 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2844 | Ebin | 2026-03-26 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A | 70T Crawler Crane | Equipment | Equipment | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2845 | Ebin | 2026-03-26 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2846 | Ebin | 2026-03-26 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2847 | Ebin | 2026-03-26 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2848 | Ebin | 2026-03-26 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2849 | Ebin | 2026-03-26 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2850 | Ebin | 2026-03-26 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2851 | Ebin | 2026-03-26 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2852 | Ebin | 2026-03-26 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | _ | CT-1010-02 | Idle | 5 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2853 | Ebin | 2026-03-26 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2854 | Ebin | 2026-03-26 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2855 | Ebin | 2026-03-26 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2856 | Ebin | 2026-03-26 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2857 | Ebin | 2026-03-26 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2858 | Ebin | 2026-03-26 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2859 | Ebin | 2026-03-26 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2860 | Ebin | 2026-03-26 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2861 | Ebin | 2026-03-26 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2862 | Ebin | 2026-03-26 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2863 | Ebin | 2026-03-26 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2863 | Ebin | 2026-03-26 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2864 | Ebin | 2026-03-26 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2865 | Ebin | 2026-03-26 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2866 | Ebin | 2026-03-26 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 5 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2867 | Ebin | 2026-03-26 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2868 | Ebin | 2026-03-26 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2869 | Ebin | 2026-03-26 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2870 | Ebin | 2026-03-26 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2871 | Ebin | 2026-03-26 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2872 | Ebin | 2026-03-26 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2873 | Ebin | 2026-03-26 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2874 | Ebin | 2026-03-26 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2875 | Ebin | 2026-03-26 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2876 | Ebin | 2026-03-26 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2877 | Ebin | 2026-03-26 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2878 | Ebin | 2026-03-26 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2879 | Ebin | 2026-03-26 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2880 | Ebin | 2026-03-26 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2881 | Ebin | 2026-03-26 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2882 | Shijo | 2026-03-26 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2882 | Shijo | 2026-03-26 | Encogroup | Ashwin Shivaraman | 127414586 | HSE Officer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2883 | Shijo | 2026-03-26 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2882 | Shijo | 2026-03-26 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2884 | Shijo | 2026-03-26 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2882 | Shijo | 2026-03-26 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2882 | Shijo | 2026-03-26 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2882 | Shijo | 2026-03-26 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2885 | Shijo | 2026-03-26 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2886 | Shijo | 2026-03-26 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2887 | Shijo | 2026-03-26 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2888 | Shijo | 2026-03-26 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2889 | Shijo | 2026-03-26 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2890 | Shijo | 2026-03-26 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2891 | Shijo | 2026-03-26 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2891 | Shijo | 2026-03-26 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2892 | Shijo | 2026-03-26 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2893 | Shijo | 2026-03-26 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2894 | Shijo | 2026-03-26 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2895 | Shijo | 2026-03-26 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2896 | Shijo | 2026-03-26 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2896 | Shijo | 2026-03-26 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2897 | Shijo | 2026-03-26 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2898 | Shijo | 2026-03-26 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2899 | Shijo | 2026-03-26 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2900 | Shijo | 2026-03-26 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2901 | Shijo | 2026-03-26 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2902 | Shijo | 2026-03-26 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2903 | Shijo | 2026-03-26 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2904 | Shijo | 2026-03-26 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2905 | Shijo | 2026-03-26 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2906 | Shijo | 2026-03-26 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2907 | Shijo | 2026-03-26 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2908 | Shijo | 2026-03-26 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2909 | Shijo | 2026-03-26 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2910 | Shijo | 2026-03-26 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2911 | Shijo | 2026-03-26 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2912 | Shijo | 2026-03-26 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2913 | Shijo | 2026-03-26 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2914 | Shijo | 2026-03-26 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2914 | Shijo | 2026-03-26 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2915 | Shijo | 2026-03-26 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2916 | Shijo | 2026-03-26 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2917 | Shijo | 2026-03-26 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2918 | Shijo | 2026-03-26 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2919 | Shijo | 2026-03-26 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2919 | Shijo | 2026-03-26 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2920 | Shijo | 2026-03-26 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2921 | Shijo | 2026-03-26 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2922 | Shijo | 2026-03-26 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2923 | Shijo | 2026-03-26 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2924 | Shijo | 2026-03-26 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2925 | Shijo | 2026-03-26 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2926 | Shijo | 2026-03-26 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2927 | Shijo | 2026-03-26 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2928 | Shijo | 2026-03-26 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2929 | Shijo | 2026-03-26 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2930 | Shijo | 2026-03-26 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2931 | Shijo | 2026-03-26 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2932 | Shijo | 2026-03-26 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2933 | Shijo | 2026-03-26 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2934 | Shijo | 2026-03-26 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2935 | Shijo | 2026-03-26 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2936 | Shijo | 2026-03-26 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2937 | Shijo | 2026-03-26 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2938 | Shijo | 2026-03-26 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2939 | Shijo | 2026-03-26 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2940 | Shijo | 2026-03-26 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2941 | Shijo | 2026-03-26 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2942 | Shijo | 2026-03-26 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2943 | Shijo | 2026-03-26 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2944 | Shijo | 2026-03-26 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2945 | Shijo | 2026-03-26 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2946 | Shijo | 2026-03-26 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2947 | Shijo | 2026-03-26 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2948 | Shijo | 2026-03-26 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2949 | Shijo | 2026-03-26 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2950 | Shijo | 2026-03-26 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2951 | Shijo | 2026-03-26 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2952 | Shijo | 2026-03-26 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2953 | Shijo | 2026-03-26 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2954 | Shijo | 2026-03-26 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2955 | Shijo | 2026-03-26 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2956 | Shijo | 2026-03-26 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2957 | Shijo | 2026-03-26 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2958 | Shijo | 2026-03-26 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2958 | Shijo | 2026-03-26 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
2958 | Shijo | 2026-03-26 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 5 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions |  | *Work activities were suspended by Vale Safety at 12:30 pm due to adverse weather conditions.
2959 | Shijo | 2026-03-26 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 5 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2958 | Shijo | 2026-03-26 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2960 | Shijo | 2026-03-26 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2961 | Shijo | 2026-03-26 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2962 | Shijo | 2026-03-26 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2963 | Shijo | 2026-03-26 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2964 | Shijo | 2026-03-26 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions
2965 | Shijo | 2026-03-26 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions
2966 | Shijo | 2026-03-26 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2967 | Shijo | 2026-03-26 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2968 | Shijo | 2026-03-26 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2969 | Shijo | 2026-03-26 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions
2970 | Shijo | 2026-03-26 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions
2971 | Shijo | 2026-03-26 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions
2972 | Shijo | 2026-03-26 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Laydown | _ | _ | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale Safety due to adverse weather conditions
2973 | Shijo | 2026-03-26 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2974 | Shijo | 2026-03-26 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale Safety due to adverse weather conditions
2975 | Ebin | 2026-03-28 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2976 | Ebin | 2026-03-28 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A | 70T Crawler Crane | Equipment | Equipment | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2977 | Ebin | 2026-03-28 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2978 | Ebin | 2026-03-28 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2979 | Ebin | 2026-03-28 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2980 | Ebin | 2026-03-28 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2981 | Ebin | 2026-03-28 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 10 |  |  |  | Site wide de-watering operations
2982 | Ebin | 2026-03-28 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2983 | Ebin | 2026-03-28 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2984 | Ebin | 2026-03-28 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | _ | CT-1010-02 | Idle | 5 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2985 | Ebin | 2026-03-28 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2986 | Ebin | 2026-03-28 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Day | 10 |  |  |  | Site wide de-watering operations
2987 | Ebin | 2026-03-28 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2988 | Ebin | 2026-03-28 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2989 | Ebin | 2026-03-28 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2990 | Ebin | 2026-03-28 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2991 | Ebin | 2026-03-28 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2992 | Ebin | 2026-03-28 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2993 | Ebin | 2026-03-28 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2994 | Ebin | 2026-03-28 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2995 | Ebin | 2026-03-28 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2996 | Ebin | 2026-03-28 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2997 | Ebin | 2026-03-28 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2998 | Ebin | 2026-03-28 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
2999 | Ebin | 2026-03-28 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 5 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3000 | Ebin | 2026-03-28 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3001 | Ebin | 2026-03-28 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3002 | Ebin | 2026-03-28 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3003 | Ebin | 2026-03-28 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3004 | Ebin | 2026-03-28 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3004 | Ebin | 2026-03-28 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3005 | Ebin | 2026-03-28 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3006 | Ebin | 2026-03-28 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3007 | Ebin | 2026-03-28 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3008 | Ebin | 2026-03-28 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3009 | Ebin | 2026-03-28 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3010 | Ebin | 2026-03-28 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3011 | Ebin | 2026-03-28 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3012 | Ebin | 2026-03-28 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3013 | Ebin | 2026-03-28 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3014 | Ebin | 2026-03-28 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3015 | Shijo | 2026-03-28 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3016 | Shijo | 2026-03-28 | Encogroup | Ashwin Shivaraman | 127414586 | HSE Officer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3017 | Shijo | 2026-03-28 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3018 | Shijo | 2026-03-28 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3019 | Shijo | 2026-03-28 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3020 | Shijo | 2026-03-28 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3021 | Shijo | 2026-03-28 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3022 | Shijo | 2026-03-28 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3023 | Shijo | 2026-03-28 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3024 | Shijo | 2026-03-28 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3025 | Shijo | 2026-03-28 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3026 | Shijo | 2026-03-28 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3027 | Shijo | 2026-03-28 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3028 | Shijo | 2026-03-28 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3029 | Shijo | 2026-03-28 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3030 | Shijo | 2026-03-28 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3031 | Shijo | 2026-03-28 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3032 | Shijo | 2026-03-28 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Day | 10 |  |  |  | Site wide de-watering operations
3033 | Shijo | 2026-03-28 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3034 | Shijo | 2026-03-28 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3035 | Shijo | 2026-03-28 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3036 | Shijo | 2026-03-28 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3037 | Shijo | 2026-03-28 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3038 | Shijo | 2026-03-28 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3039 | Shijo | 2026-03-28 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Day | 10 |  |  |  | Site wide de-watering operations
3040 | Shijo | 2026-03-28 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3041 | Shijo | 2026-03-28 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3042 | Shijo | 2026-03-28 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3043 | Shijo | 2026-03-28 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3044 | Shijo | 2026-03-28 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3045 | Shijo | 2026-03-28 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3046 | Shijo | 2026-03-28 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3047 | Shijo | 2026-03-28 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3048 | Shijo | 2026-03-28 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3049 | Shijo | 2026-03-28 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3050 | Shijo | 2026-03-28 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3051 | Shijo | 2026-03-28 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3052 | Shijo | 2026-03-28 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3053 | Shijo | 2026-03-28 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3054 | Shijo | 2026-03-28 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3054 | Shijo | 2026-03-28 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3055 | Shijo | 2026-03-28 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | _ | TR-1010-26 | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3056 | Shijo | 2026-03-28 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3057 | Shijo | 2026-03-28 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3058 | Shijo | 2026-03-28 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3059 | Shijo | 2026-03-28 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3059 | Shijo | 2026-03-28 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3060 | Shijo | 2026-03-28 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3061 | Shijo | 2026-03-28 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3062 | Shijo | 2026-03-28 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3063 | Shijo | 2026-03-28 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3064 | Shijo | 2026-03-28 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3065 | Shijo | 2026-03-28 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3066 | Shijo | 2026-03-28 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3067 | Shijo | 2026-03-28 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3068 | Shijo | 2026-03-28 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3069 | Shijo | 2026-03-28 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3070 | Shijo | 2026-03-28 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3071 | Shijo | 2026-03-28 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Laydown | _ | _ | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3072 | Shijo | 2026-03-28 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3073 | Shijo | 2026-03-28 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3074 | Shijo | 2026-03-28 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3075 | Shijo | 2026-03-28 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3076 | Shijo | 2026-03-28 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Laydown | _ | _ | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3077 | Shijo | 2026-03-28 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3078 | Shijo | 2026-03-28 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3079 | Shijo | 2026-03-28 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3080 | Shijo | 2026-03-28 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3081 | Shijo | 2026-03-28 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3082 | Shijo | 2026-03-28 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3083 | Shijo | 2026-03-28 | Encogroup | Vicken Tcheroyan | 121668462 | Site Manager | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 |  |  |  | Site wide de-watering operations
3084 | Shijo | 2026-03-28 | Encogroup | Aneesh Joseph | 141253376 | Store Keeper | Manpower | Manpower | Laydown |  | Offloading | Day | 10 |  |  |  | Site wide de-watering operations
3085 | Shijo | 2026-03-28 | Encogroup | Ahmed Khadeem Said Al Tourashi | 19753414 | Bus Driver | Manpower | Manpower | Laydown |  | Offloading | Day | 10 |  |  |  | Site wide de-watering operations
3083 | Shijo | 2026-03-28 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Offloading | Day | 10 |  |  |  | Site wide de-watering operations
3086 | Shijo | 2026-03-28 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3087 | Shijo | 2026-03-28 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3088 | Shijo | 2026-03-28 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3089 | Shijo | 2026-03-28 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3090 | Shijo | 2026-03-28 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3091 | Shijo | 2026-03-28 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3092 | Shijo | 2026-03-28 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3093 | Shijo | 2026-03-28 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3094 | Shijo | 2026-03-28 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3095 | Shijo | 2026-03-28 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3096 | Shijo | 2026-03-28 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3097 | Shijo | 2026-03-28 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3098 | Shijo | 2026-03-28 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3099 | Shijo | 2026-03-28 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3100 | Shijo | 2026-03-28 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
3100 | Shijo | 2026-03-28 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | No usage
3100 | Shijo | 2026-03-28 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3101 | Shijo | 2026-03-28 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3100 | Shijo | 2026-03-28 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3102 | Shijo | 2026-03-28 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3103 | Shijo | 2026-03-28 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3104 | Shijo | 2026-03-28 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3105 | Shijo | 2026-03-28 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3106 | Shijo | 2026-03-28 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Idle | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale management due to adverse weather conditions
3107 | Shijo | 2026-03-28 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Idle | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale management due to adverse weather conditions
3108 | Shijo | 2026-03-28 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3109 | Shijo | 2026-03-28 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3110 | Shijo | 2026-03-28 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3111 | Shijo | 2026-03-28 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Laydown | _ | _ | Idle | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale management due to adverse weather conditions
3112 | Shijo | 2026-03-28 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Laydown | _ | _ | Idle | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale management due to adverse weather conditions
3113 | Shijo | 2026-03-28 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Laydown | _ | _ | Idle | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale management due to adverse weather conditions
3114 | Shijo | 2026-03-28 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Laydown | _ | _ | Idle | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Work activities were suspended by Vale management due to adverse weather conditions
3115 | Shijo | 2026-03-28 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3116 | Shijo | 2026-03-28 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Offloading | Idle | 10 |  |  |  | Work activities were suspended by Vale management due to adverse weather conditions
3117 | Ebin | 2026-03-29 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3118 | Ebin | 2026-03-29 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A | 70T Crawler Crane | Equipment | Equipment | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3119 | Ebin | 2026-03-29 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3120 | Ebin | 2026-03-29 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3121 | Ebin | 2026-03-29 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3122 | Ebin | 2026-03-29 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3123 | Ebin | 2026-03-29 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3124 | Ebin | 2026-03-29 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3125 | Ebin | 2026-03-29 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3126 | Ebin | 2026-03-29 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3127 | Ebin | 2026-03-29 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3128 | Ebin | 2026-03-29 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Common Area | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
3129 | Ebin | 2026-03-29 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Common Area | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3128 | Ebin | 2026-03-29 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard‑3, the 150T crawler crane assembly was halted.,As ground leveling was required to resume work.
3130 | Ebin | 2026-03-29 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Idle due to maintenance work,Requires repair but no access to remove the crane from area. Yard 2 access flooded
3131 | Ebin | 2026-03-29 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3132 | Ebin | 2026-03-29 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3133 | Ebin | 2026-03-29 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3134 | Ebin | 2026-03-29 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3135 | Ebin | 2026-03-29 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3136 | Ebin | 2026-03-29 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3137 | Ebin | 2026-03-29 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3138 | Ebin | 2026-03-29 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3139 | Ebin | 2026-03-29 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3140 | Ebin | 2026-03-29 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3141 | Ebin | 2026-03-29 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3142 | Ebin | 2026-03-29 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3143 | Ebin | 2026-03-29 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3144 | Ebin | 2026-03-29 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3145 | Ebin | 2026-03-29 | Encogroup | Arunkumar Surendran | 127859069 | QC Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3146 | Ebin | 2026-03-29 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3147 | Ebin | 2026-03-29 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3148 | Ebin | 2026-03-29 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3149 | Ebin | 2026-03-29 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3150 | Ebin | 2026-03-29 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3151 | Ebin | 2026-03-29 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3152 | Ebin | 2026-03-29 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Idle due to maintenance work,Requires repair but no access to remove the crane from area. Yard 2 access flooded
3153 | Ebin | 2026-03-29 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3154 | Ebin | 2026-03-29 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3155 | Ebin | 2026-03-29 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3155 | Ebin | 2026-03-29 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation. | YARD 3
3156 | Ebin | 2026-03-29 | Bright Light | Jalaludeen S | 103199925 | Mechanic | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3156 | Ebin | 2026-03-29 | Bright Light | Subash H.K | 83935096 | Technician | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3156 | Ebin | 2026-03-29 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3155 | Ebin | 2026-03-29 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3157 | Ebin | 2026-03-29 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 094 (7 nos), BM 388, BM 372, BM 373, VB 046, VB 048 and material segregation.
3158 | Shijo | 2026-03-29 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3159 | Shijo | 2026-03-29 | Encogroup | Ashwin Shivaraman | 127414586 | HSE Officer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3160 | Shijo | 2026-03-29 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 8 | Electrical Works | Electrical Works | Cable tray support installation | _
3161 | Shijo | 2026-03-29 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3162 | Shijo | 2026-03-29 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 8 | Electrical Works | Electrical Works | Cable tray support installation | _
3163 | Shijo | 2026-03-29 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3164 | Shijo | 2026-03-29 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 8 | Electrical Works | Electrical Works | Cable tray support installation | _
3165 | Shijo | 2026-03-29 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3166 | Shijo | 2026-03-29 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3167 | Shijo | 2026-03-29 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Painting Coating | Painting Coating | Painting Coating | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3168 | Shijo | 2026-03-29 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3169 | Shijo | 2026-03-29 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3170 | Shijo | 2026-03-29 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3171 | Shijo | 2026-03-29 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3172 | Shijo | 2026-03-29 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3173 | Shijo | 2026-03-29 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3174 | Shijo | 2026-03-29 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3175 | Shijo | 2026-03-29 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Signalman | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3176 | Shijo | 2026-03-29 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3177 | Shijo | 2026-03-29 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3178 | Shijo | 2026-03-29 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3179 | Shijo | 2026-03-29 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3180 | Shijo | 2026-03-29 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3181 | Shijo | 2026-03-29 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3182 | Shijo | 2026-03-29 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Store-Keeper | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material tagging & segregation | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3183 | Shijo | 2026-03-29 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3184 | Shijo | 2026-03-29 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3185 | Shijo | 2026-03-29 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3186 | Shijo | 2026-03-29 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3187 | Shijo | 2026-03-29 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3188 | Shijo | 2026-03-29 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3189 | Shijo | 2026-03-29 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3190 | Shijo | 2026-03-29 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3191 | Shijo | 2026-03-29 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3192 | Shijo | 2026-03-29 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3193 | Shijo | 2026-03-29 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3194 | Shijo | 2026-03-29 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3195 | Shijo | 2026-03-29 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
3196 | Shijo | 2026-03-29 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Common Area | _ | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
3197 | Shijo | 2026-03-29 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3198 | Shijo | 2026-03-29 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3199 | Shijo | 2026-03-29 | Encogroup | Anandbabu subbiah | 81612139 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3200 | Shijo | 2026-03-29 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Electrical Works | Electrical Works | Electrical Works | _
3200 | Shijo | 2026-03-29 | Encogroup | Deepu Chauhan | 117871996 | Electrical Supervisor | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Electrical Works | Electrical Works | Electrical Works | _
3200 | Shijo | 2026-03-29 | Encogroup | Hassan Salah Mechhawi | 130805123 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3201 | Shijo | 2026-03-29 | Encogroup | Mostafa Khaled Fattouh | 140623552 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3199 | Shijo | 2026-03-29 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3202 | Shijo | 2026-03-29 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3195 | Shijo | 2026-03-29 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3203 | Shijo | 2026-03-29 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Signalman | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3204 | Shijo | 2026-03-29 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3205 | Shijo | 2026-03-29 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3206 | Shijo | 2026-03-29 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | Erection of DDSTW10CL001,DDSTW10CL002,DDSTW10BM013,DDSTW10BM019-2(no),DDSTW10BM018,DDSTW10BM012
3207 | Shijo | 2026-03-29 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3208 | Shijo | 2026-03-29 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown |  | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3209 | Shijo | 2026-03-29 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 02 | #N/A | 70T Crawler Crane | Equipment | Equipment | Laydown |  | Offloading | Idle | 10 |  |  |  | Crane Assembly is in progress
3208 | Shijo | 2026-03-29 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3210 | Shijo | 2026-03-29 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown |  | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3210 | Shijo | 2026-03-29 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3211 | Shijo | 2026-03-29 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3212 | Shijo | 2026-03-29 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3213 | Shijo | 2026-03-29 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3214 | Shijo | 2026-03-29 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3215 | Shijo | 2026-03-29 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3216 | Shijo | 2026-03-29 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 | Material Handling | Material unloading by crane | Material unloading by crane | No usage
3217 | Shijo | 2026-03-29 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3218 | Shijo | 2026-03-29 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3219 | Shijo | 2026-03-29 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3220 | Shijo | 2026-03-29 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3221 | Shijo | 2026-03-29 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3222 | Shijo | 2026-03-29 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3223 | Shijo | 2026-03-29 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3224 | Shijo | 2026-03-29 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3225 | Shijo | 2026-03-29 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3226 | Shijo | 2026-03-29 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3227 | Shijo | 2026-03-29 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3228 | Shijo | 2026-03-29 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3229 | Shijo | 2026-03-29 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3230 | Shijo | 2026-03-29 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3231 | Shijo | 2026-03-29 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3232 | Shijo | 2026-03-29 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3233 | Shijo | 2026-03-29 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3234 | Shijo | 2026-03-29 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3235 | Shijo | 2026-03-29 | Encogroup | Vicken Tcheroyan | 121668462 | Site Manager | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3236 | Shijo | 2026-03-29 | Encogroup | Aneesh Joseph | 141253376 | Store Keeper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3237 | Shijo | 2026-03-29 | Encogroup | Ahmed Khadeem Said Al Tourashi | 19753414 | Bus Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3238 | Shijo | 2026-03-29 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3239 | Shijo | 2026-03-29 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3240 | Shijo | 2026-03-29 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3240 | Shijo | 2026-03-29 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3241 | Shijo | 2026-03-29 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 |  |  |  | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3242 | Shijo | 2026-03-29 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3243 | Shijo | 2026-03-29 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3244 | Shijo | 2026-03-29 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3245 | Shijo | 2026-03-29 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3246 | Shijo | 2026-03-29 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3247 | Shijo | 2026-03-29 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3248 | Shijo | 2026-03-29 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3249 | Shijo | 2026-03-29 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3250 | Shijo | 2026-03-29 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3251 | Shijo | 2026-03-29 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3252 | Shijo | 2026-03-29 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3253 | Shijo | 2026-03-29 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3254 | Shijo | 2026-03-29 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3255 | Shijo | 2026-03-29 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3256 | Shijo | 2026-03-29 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3257 | Shijo | 2026-03-29 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3258 | Shijo | 2026-03-29 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 |  |  |  | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3259 | Shijo | 2026-03-29 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3260 | Shijo | 2026-03-29 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3261 | Shijo | 2026-03-29 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3262 | Shijo | 2026-03-29 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3262 | Shijo | 2026-03-29 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3263 | Shijo | 2026-03-29 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3264 | Shijo | 2026-03-29 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3265 | Shijo | 2026-03-29 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3266 | Shijo | 2026-03-29 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3267 | Shijo | 2026-03-29 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3268 | Shijo | 2026-03-29 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3269 | Shijo | 2026-03-29 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3270 | Shijo | 2026-03-29 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3271 | Shijo | 2026-03-29 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3272 | Shijo | 2026-03-29 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3272 | Shijo | 2026-03-29 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 2 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3273 | Shijo | 2026-03-29 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Laydown | _ | Loading | Day | 2 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3272 | Shijo | 2026-03-29 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 2 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3274 | Shijo | 2026-03-29 | Encogroup | Sandeep Kumar Sugreev | 141365042 | Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3271 | Shijo | 2026-03-29 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3275 | Shijo | 2026-03-29 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of TR1010-26 materials (Case No. 24 -Tower-10) to contractor's parking area and 150T crawler crane materials to yard-3,loading of CT1010-02 materials to yard-2,removal of materials from inside of the module and shifting of electrical supports for substation
3276 | Ebin | 2026-03-30 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3277 | Ebin | 2026-03-30 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A | 70T Crawler Crane | Equipment | Equipment | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3278 | Ebin | 2026-03-30 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3279 | Ebin | 2026-03-30 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3280 | Ebin | 2026-03-30 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3281 | Ebin | 2026-03-30 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3282 | Ebin | 2026-03-30 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3283 | Ebin | 2026-03-30 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3284 | Ebin | 2026-03-30 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3285 | Ebin | 2026-03-30 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 3 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3285 | Ebin | 2026-03-30 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3285 | Ebin | 2026-03-30 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3285 | Ebin | 2026-03-30 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3286 | Ebin | 2026-03-30 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3286 | Ebin | 2026-03-30 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3287 | Ebin | 2026-03-30 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3288 | Ebin | 2026-03-30 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3285 | Ebin | 2026-03-30 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3289 | Ebin | 2026-03-30 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3290 | Ebin | 2026-03-30 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Common Area | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
3291 | Ebin | 2026-03-30 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | At Yard-3, the 150T crawler crane assembly is underway, with the completion of counter weights installation, At Yard‑3, the 150T crawler crane assembly was halted, as ground leveling was required to resume work
3292 | Ebin | 2026-03-30 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Idle due to maintenance work,Requires repair but no access to remove the crane from area. Yard 2 access flooded
3293 | Ebin | 2026-03-30 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3294 | Ebin | 2026-03-30 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3295 | Ebin | 2026-03-30 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3296 | Ebin | 2026-03-30 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3297 | Ebin | 2026-03-30 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3298 | Ebin | 2026-03-30 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3299 | Ebin | 2026-03-30 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3300 | Ebin | 2026-03-30 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3301 | Ebin | 2026-03-30 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3302 | Ebin | 2026-03-30 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3303 | Ebin | 2026-03-30 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3304 | Ebin | 2026-03-30 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3305 | Ebin | 2026-03-30 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3306 | Ebin | 2026-03-30 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3307 | Ebin | 2026-03-30 | Encogroup | Arunkumar Surendran | 127859069 | QC Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3308 | Ebin | 2026-03-30 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3309 | Ebin | 2026-03-30 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3310 | Ebin | 2026-03-30 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3311 | Ebin | 2026-03-30 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3312 | Ebin | 2026-03-30 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3313 | Ebin | 2026-03-30 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3314 | Ebin | 2026-03-30 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Idle due to maintenance work,Requires repair but no access to remove the crane from area. Yard 2 access flooded
3315 | Ebin | 2026-03-30 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3316 | Ebin | 2026-03-30 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3317 | Ebin | 2026-03-30 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3318 | Ebin | 2026-03-30 | Bright Light | Jalaludeen S | 103199925 | Mechanic | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3319 | Ebin | 2026-03-30 | Bright Light | Subash H.K | 83935096 | Technician | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3320 | Ebin | 2026-03-30 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3321 | Ebin | 2026-03-30 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3322 | Ebin | 2026-03-30 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of BM 92, BM 229, CL 025 and torquing of CL 042, CL 028 along with material segregation
3323 | Shijo | 2026-03-30 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3324 | Shijo | 2026-03-30 | Encogroup | Ashwin Shivaraman | 127414586 | HSE Officer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3325 | Shijo | 2026-03-30 | Encogroup | Fadi Al Asmar | 140841472 | Electrical Superintendent | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3325 | Shijo | 2026-03-30 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3326 | Shijo | 2026-03-30 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3327 | Shijo | 2026-03-30 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3328 | Shijo | 2026-03-30 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3329 | Shijo | 2026-03-30 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3330 | Shijo | 2026-03-30 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3331 | Shijo | 2026-03-30 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3332 | Shijo | 2026-03-30 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Painting Coating | Painting Coating | Painting Coating | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3333 | Shijo | 2026-03-30 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3334 | Shijo | 2026-03-30 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3335 | Shijo | 2026-03-30 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3336 | Shijo | 2026-03-30 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3337 | Shijo | 2026-03-30 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3338 | Shijo | 2026-03-30 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3339 | Shijo | 2026-03-30 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3340 | Shijo | 2026-03-30 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Signalman | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3341 | Shijo | 2026-03-30 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3342 | Shijo | 2026-03-30 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3343 | Shijo | 2026-03-30 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3344 | Shijo | 2026-03-30 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3345 | Shijo | 2026-03-30 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3346 | Shijo | 2026-03-30 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3347 | Shijo | 2026-03-30 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Store-Keeper | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material tagging & segregation | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3348 | Shijo | 2026-03-30 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3349 | Shijo | 2026-03-30 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3350 | Shijo | 2026-03-30 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3351 | Shijo | 2026-03-30 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3352 | Shijo | 2026-03-30 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3353 | Shijo | 2026-03-30 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3354 | Shijo | 2026-03-30 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3355 | Shijo | 2026-03-30 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3356 | Shijo | 2026-03-30 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3357 | Shijo | 2026-03-30 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3358 | Shijo | 2026-03-30 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3359 | Shijo | 2026-03-30 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3360 | Shijo | 2026-03-30 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
3361 | Shijo | 2026-03-30 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Common Area | _ | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
3362 | Shijo | 2026-03-30 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3363 | Shijo | 2026-03-30 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3364 | Shijo | 2026-03-30 | Encogroup | Anandbabu subbiah | 81612139 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3365 | Shijo | 2026-03-30 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Electrical Works | Electrical Works | Electrical Works | _
3366 | Shijo | 2026-03-30 | Encogroup | Deepu Chauhan | 117871996 | Electrical Supervisor | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Electrical Works | Electrical Works | Electrical Works | _
3367 | Shijo | 2026-03-30 | Encogroup | Hassan Salah Mechhawi | 130805123 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3368 | Shijo | 2026-03-30 | Encogroup | Mostafa Khaled Fattouh | 140623552 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3369 | Shijo | 2026-03-30 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3370 | Shijo | 2026-03-30 | Encogroup | Anandbabu subbiah | 81612139 | Mechanic | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3370 | Shijo | 2026-03-30 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3370 | Shijo | 2026-03-30 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3371 | Shijo | 2026-03-30 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3372 | Shijo | 2026-03-30 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Signalman | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3373 | Shijo | 2026-03-30 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3374 | Shijo | 2026-03-30 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3375 | Shijo | 2026-03-30 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | Erection of DDSTW10CL004,DDSTW10CL005,DDSTW10BM003,DDSTW10BM001-2(no),DDSTW10BM038,DDSTW10BM046,DDSTW10BM039
3376 | Shijo | 2026-03-30 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3377 | Shijo | 2026-03-30 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown |  | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3378 | Shijo | 2026-03-30 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 02 | #N/A | 70T Crawler Crane | Equipment | Equipment | Laydown |  | Offloading | Idle | 10 |  |  |  | Crane Assembly is in progress
3379 | Shijo | 2026-03-30 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3380 | Shijo | 2026-03-30 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown |  | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3381 | Shijo | 2026-03-30 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3382 | Shijo | 2026-03-30 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3383 | Shijo | 2026-03-30 | Encogroup | 55 SEAT BUS 7885YM (RENTAL) | #N/A | 55 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3383 | Shijo | 2026-03-30 | Encogroup | FLATBED TRAILER | #N/A | FLATBED TRAILER | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3383 | Shijo | 2026-03-30 | Encogroup | 4T JCB TELEHANDLER | #N/A | TELEHANDLER | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3383 | Shijo | 2026-03-30 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3384 | Shijo | 2026-03-30 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3385 | Shijo | 2026-03-30 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3386 | Shijo | 2026-03-30 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3387 | Shijo | 2026-03-30 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 | Material Handling | Material unloading by crane | Material unloading by crane | No usage
3388 | Shijo | 2026-03-30 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3389 | Shijo | 2026-03-30 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3390 | Shijo | 2026-03-30 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3391 | Shijo | 2026-03-30 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3392 | Shijo | 2026-03-30 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3393 | Shijo | 2026-03-30 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3394 | Shijo | 2026-03-30 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3395 | Shijo | 2026-03-30 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3396 | Shijo | 2026-03-30 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3397 | Shijo | 2026-03-30 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3398 | Shijo | 2026-03-30 | Encogroup | Muhammed Yasir | 118882687 | Permit Reciver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3398 | Shijo | 2026-03-30 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3399 | Shijo | 2026-03-30 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3400 | Shijo | 2026-03-30 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3401 | Shijo | 2026-03-30 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3402 | Shijo | 2026-03-30 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3403 | Shijo | 2026-03-30 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3404 | Shijo | 2026-03-30 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3405 | Shijo | 2026-03-30 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3406 | Shijo | 2026-03-30 | Encogroup | Vicken Tcheroyan | 121668462 | Site Manager | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3407 | Shijo | 2026-03-30 | Encogroup | Aneesh Joseph | 141253376 | Store Keeper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3408 | Shijo | 2026-03-30 | Encogroup | Ahmed Khadeem Said Al Tourashi | 19753414 | Bus Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3409 | Shijo | 2026-03-30 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3410 | Shijo | 2026-03-30 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3411 | Shijo | 2026-03-30 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3412 | Shijo | 2026-03-30 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 |  |  |  | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3413 | Shijo | 2026-03-30 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3414 | Shijo | 2026-03-30 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3415 | Shijo | 2026-03-30 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3416 | Shijo | 2026-03-30 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3417 | Shijo | 2026-03-30 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3418 | Shijo | 2026-03-30 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3419 | Shijo | 2026-03-30 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3420 | Shijo | 2026-03-30 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3421 | Shijo | 2026-03-30 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3422 | Shijo | 2026-03-30 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3423 | Shijo | 2026-03-30 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3424 | Shijo | 2026-03-30 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3425 | Shijo | 2026-03-30 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3426 | Shijo | 2026-03-30 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3427 | Shijo | 2026-03-30 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3428 | Shijo | 2026-03-30 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3429 | Shijo | 2026-03-30 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 |  |  |  | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3430 | Shijo | 2026-03-30 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3431 | Shijo | 2026-03-30 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3432 | Shijo | 2026-03-30 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3433 | Shijo | 2026-03-30 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3434 | Shijo | 2026-03-30 | Encogroup | Syed Ihsan Haider | 100398391 | DuqmTrailer Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Duqm Trailer
3435 | Shijo | 2026-03-30 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3433 | Shijo | 2026-03-30 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3436 | Shijo | 2026-03-30 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3437 | Shijo | 2026-03-30 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3438 | Shijo | 2026-03-30 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3439 | Shijo | 2026-03-30 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 2 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3439 | Shijo | 2026-03-30 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3440 | Shijo | 2026-03-30 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ | Loading | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3440 | Shijo | 2026-03-30 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3441 | Shijo | 2026-03-30 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3442 | Shijo | 2026-03-30 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3443 | Shijo | 2026-03-30 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3444 | Shijo | 2026-03-30 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3445 | Shijo | 2026-03-30 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3446 | Shijo | 2026-03-30 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3447 | Shijo | 2026-03-30 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3448 | Shijo | 2026-03-30 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3449 | Shijo | 2026-03-30 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3450 | Shijo | 2026-03-30 | Encogroup | Sandeep Kumar Sugreev | 141365042 | Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3451 | Shijo | 2026-03-30 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3452 | Shijo | 2026-03-30 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3453 | Ebin | 2026-03-31 | Encogroup | Ebin Ben | 116589569 | Mechanical Engineer | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3454 | Ebin | 2026-03-31 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A | 70T Crawler Crane | Equipment | Equipment | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3455 | Ebin | 2026-03-31 | Al Jaber Heavy Lift | Abid Hussain | 112778626 | Crane Operator-150T Hitachi Crawler | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3456 | Ebin | 2026-03-31 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3457 | Ebin | 2026-03-31 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 | Crane Operator | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3458 | Ebin | 2026-03-31 | Encogroup | Sonu Kumar Pandey | 140764706 | Rigger | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3459 | Ebin | 2026-03-31 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 3 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3460 | Ebin | 2026-03-31 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3461 | Ebin | 2026-03-31 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3459 | Ebin | 2026-03-31 | Al Jaber Heavy Lift | Shobul Rata | #N/A | Technician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3462 | Ebin | 2026-03-31 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3459 | Ebin | 2026-03-31 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3459 | Ebin | 2026-03-31 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3459 | Ebin | 2026-03-31 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3463 | Ebin | 2026-03-31 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3459 | Ebin | 2026-03-31 | Encogroup | Atif Rasheed | 127331574 | Permit Receiver | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3464 | Ebin | 2026-03-31 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | HSE Officer | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3465 | Ebin | 2026-03-31 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3466 | Ebin | 2026-03-31 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Assistant/Helper | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 10 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3467 | Ebin | 2026-03-31 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Common Area | Crane Assembly | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
3468 | Ebin | 2026-03-31 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Yard 3 | Crane Assembly | CT-1010-02 | Idle | 5 |  |  |  | idle as area clearing and leveling executed using excavator support to facilitate crane access
3469 | Ebin | 2026-03-31 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A | 100T Telescopic Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Idle due to maintenance work,Requires repair but no access to remove the crane from area. Yard 2 access flooded
3470 | Ebin | 2026-03-31 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A | 150T-Crawler Crane | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3471 | Ebin | 2026-03-31 | Encogroup | 28M LCMG MANLIFT | #N/A | 28M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3472 | Ebin | 2026-03-31 | Encogroup | 22M LCMG MANLIFT | #N/A | 22M-Manlift | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3473 | Ebin | 2026-03-31 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3474 | Ebin | 2026-03-31 | Encogroup | Rajesh Thakur | 124565057 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3475 | Ebin | 2026-03-31 | Encogroup | Dharmvir Upadhyay | 140844797 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3476 | Ebin | 2026-03-31 | Encogroup | 22KVA GENERATOR | #N/A | 22KVA-Generator | Equipment | Equipment | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3477 | Ebin | 2026-03-31 | Bright Light | Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3478 | Ebin | 2026-03-31 | Encogroup | Pappu Kumar Yadaw | 122082769 | Grinder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3479 | Ebin | 2026-03-31 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3480 | Ebin | 2026-03-31 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 2 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3481 | Ebin | 2026-03-31 | Encogroup | Shyam Dhani | 140806218 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3482 | Ebin | 2026-03-31 | Encogroup | Rabih Rifai | 116915582 | Mechanical Superintendent | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3483 | Ebin | 2026-03-31 | Encogroup | Rogie Jr Mabilog | 141169071 | Welding Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3484 | Ebin | 2026-03-31 | Encogroup | Arunkumar Surendran | 127859069 | QC Mechanical Engineer | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3485 | Ebin | 2026-03-31 | Encogroup | Clyde Abrazaldo | 141169085 | Welder | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3486 | Ebin | 2026-03-31 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | RIgger | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3487 | Ebin | 2026-03-31 | Encogroup | Ranaanand Kumar | 140742088 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3488 | Ebin | 2026-03-31 | Encogroup | Lav Kansaraj | 140697039 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 5 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3489 | Ebin | 2026-03-31 | Encogroup | Rajeev Kumar Sah | 141359216 | Electrician | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3490 | Ebin | 2026-03-31 | Encogroup | Shivam Yadhav | 141365126 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3491 | Ebin | 2026-03-31 | Bright Light | Siyaram Yadav | 81379273 | Crane Operator-100T Sany Telescopic | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Idle | 10 |  |  |  | Idle due to maintenance work,Requires repair but no access to remove the crane from area. Yard 2 access flooded
3492 | Ebin | 2026-03-31 | Encogroup | Tamoor Ali Khan | 135325259 | Permit Receiver | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3493 | Ebin | 2026-03-31 | Encogroup | Tej Pradap Sharma | 141365089 | Fitter | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3494 | Ebin | 2026-03-31 | Encogroup | Gulshan Gautham | 141365075 | Helper | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3495 | Ebin | 2026-03-31 | Bright Light | Jalaludeen S | 103199925 | Mechanic | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3496 | Ebin | 2026-03-31 | Bright Light | Subash H.K | 83935096 | Technician | Sub Contactor | Sub Contactor | Yard 2 | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3497 | Ebin | 2026-03-31 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ | CT-1010-02 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3498 | Ebin | 2026-03-31 | Encogroup | Vinay Chaudhary | 122179604 | Fitter/Erector | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3499 | Ebin | 2026-03-31 | Encogroup | Wesley Jan Estandarte | 117255966 | Mechanical Supervisor | Manpower | Manpower | Yard 2 | _ | CT-1010-02 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of TR 001, VB 009, VB 010 and torquing of CL 042, CL 028, Levelling adjustment of CL 009, CL 010, CL 051 along with material segregation.
3500 | Shijo | 2026-03-31 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3501 | Shijo | 2026-03-31 | Encogroup | Ashwin Shivaraman | 127414586 | HSE Officer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3502 | Shijo | 2026-03-31 | Encogroup | Fadi Al Asmar | 140841472 | Electrical Superintendent | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3503 | Shijo | 2026-03-31 | Encogroup | Elias Zaatar | 121594839 | Electrical Engineer | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3502 | Shijo | 2026-03-31 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3504 | Shijo | 2026-03-31 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3505 | Shijo | 2026-03-31 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3506 | Shijo | 2026-03-31 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3507 | Shijo | 2026-03-31 | Encogroup | Ashwini Kumar | 127414586 | Electrician | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 5 | Electrical Works | Electrical Works | Cable tray support installation | _
3507 | Shijo | 2026-03-31 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Reclaimer Substation | _ | Cable tray supports | Day | 10 | Electrical Works | Electrical Works | Cable tray support installation | _
3508 | Shijo | 2026-03-31 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3509 | Shijo | 2026-03-31 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A | 22M-Manlift | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3510 | Shijo | 2026-03-31 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Painting Coating | Painting Coating | Painting Coating | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3511 | Shijo | 2026-03-31 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3512 | Shijo | 2026-03-31 | SARENS NASS | Gulzar Singh | 79502392 | Crane Operator- 70T Liebherr Telescopic Crane-01 | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3513 | Shijo | 2026-03-31 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A | 130T Crawler Crane | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3514 | Shijo | 2026-03-31 | SARENS NASS | Shinu S | 109957631 | Crane Operator-130T Liebherr Crawler | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3515 | Shijo | 2026-03-31 | Encogroup | Tamilselvan Tamilmani | 141250908 | Mechanical Engineer | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Ground pre-assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3516 | Shijo | 2026-03-31 | Encogroup | Ahmad Kerbaj | 132915855 | Mechanical Supervisor | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3517 | Shijo | 2026-03-31 | Encogroup | Akhilesh Kumar | 141359235 | Fitter | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3518 | Shijo | 2026-03-31 | Encogroup | Dipu Sing | 140697025 | Assistant/Helper | Manpower | Manpower | Parking Area | Signalman | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3519 | Shijo | 2026-03-31 | Encogroup | Ryan Batuto | 141169028 | Welder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3520 | Shijo | 2026-03-31 | Encogroup | Erick Atienza | 141169052 | Welder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3521 | Shijo | 2026-03-31 | Encogroup | Reymond Cruz | 141169033 | Welder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3522 | Shijo | 2026-03-31 | Encogroup | Hadi Moussa | 141358993 | Fitter | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3523 | Shijo | 2026-03-31 | Encogroup | Jaison Vijay Menezes | R3971143 | Mechanical Foreman | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3524 | Shijo | 2026-03-31 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material storage & preservation | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3525 | Shijo | 2026-03-31 | Encogroup | Sajith Saji Kanagam | 140805568 | Assistant/Helper | Manpower | Manpower | Parking Area | Store-Keeper | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material tagging & segregation | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3526 | Shijo | 2026-03-31 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3527 | Shijo | 2026-03-31 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger | Sub Contactor | Sub Contactor | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3528 | Shijo | 2026-03-31 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3529 | Shijo | 2026-03-31 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | Permit Receiver | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3530 | Shijo | 2026-03-31 | Encogroup | Md Rashed Mohmed | 140663253 | Painting Inspector | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3531 | Shijo | 2026-03-31 | Encogroup | Jitendra Kumar Yadav | AG111207 | Assistant/Helper | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3532 | Shijo | 2026-03-31 | Encogroup | Ajin Paramesvaran | 141377747 | Painter | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3533 | Shijo | 2026-03-31 | Encogroup | Balister Yadhav | S3549132 | Grinder | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3534 | Shijo | 2026-03-31 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3535 | Shijo | 2026-03-31 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Parking Area | Painting works | TR-1010-26 | Day | 10 | Painting Coating | Touch-up painting | Touch-up painting | _
3536 | Shijo | 2026-03-31 | Encogroup | Ravi Yadav | 141365164 | Helper | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3537 | Shijo | 2026-03-31 | Encogroup | Rejin Rebi | 140805554 | Assistant/Helper | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Torque tightening | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3538 | Shijo | 2026-03-31 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
3539 | Shijo | 2026-03-31 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Common Area | _ | TR-1010-26 | Day | 10 | Material Handling | Strucutre Pre-Assembly | Material unloading by crane | _
3540 | Shijo | 2026-03-31 | Encogroup | Pinto Kuriakose | 132423982 | Mechanic Supervisor | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3541 | Shijo | 2026-03-31 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3542 | Shijo | 2026-03-31 | Encogroup | Anandbabu subbiah | 81612139 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3543 | Shijo | 2026-03-31 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Electrical Works | Electrical Works | Electrical Works | _
3544 | Shijo | 2026-03-31 | Encogroup | Deepu Chauhan | 117871996 | Electrical Supervisor | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Electrical Works | Electrical Works | Electrical Works | _
3545 | Shijo | 2026-03-31 | Encogroup | Hassan Salah Mechhawi | 130805123 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3546 | Shijo | 2026-03-31 | Encogroup | Mostafa Khaled Fattouh | 140623552 | Mechanic | Manpower | Manpower | Common Area | _ | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3547 | Shijo | 2026-03-31 | Encogroup | Afaaq Hussain | 126724428 | Surveyor | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3548 | Shijo | 2026-03-31 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3548 | Shijo | 2026-03-31 | Encogroup | Anandbabu subbiah | 81612139 | Mechanic | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3548 | Shijo | 2026-03-31 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3548 | Shijo | 2026-03-31 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver | Manpower | Manpower | Common Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3548 | Shijo | 2026-03-31 | Encogroup | Pradip Rai | 141365023 | Grinder | Manpower | Manpower | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Alignment of surveyor | Alignment of surveyor | Alignment of surveyor | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3549 | Shijo | 2026-03-31 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | HSE Officer | Sub Contactor | Sub Contactor | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3550 | Shijo | 2026-03-31 | Encogroup | Surajit Maity | 140846684 | Assistant/Helper | Manpower | Manpower | Parking Area | Signalman | TR-1010-26 | Day | 10 | Steel Structure Works | Strucutre Pre-Assembly | Ground pre-assembly | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3551 | Shijo | 2026-03-31 | Encogroup | 55 SEAT BUS | #N/A | 55 Seat Bus | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Interenal Transportation | Enco Interenal Transportation | Enco Interenal Transportation | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3552 | Shijo | 2026-03-31 | Encogroup | TOWER LIGHT -4 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3553 | Shijo | 2026-03-31 | Encogroup | TOWER LIGHT -5 | #N/A | TOWER LIGHT | Equipment | Equipment | Parking Area | Pre-assembly | TR-1010-26 | Day | 10 | Enco Internal Utilities | Enco Internal Utilities | Enco Internal Utilities | Erection of DDSTW10VB005-2(no),DDSTW10VB002-2(no),DDSTW10BM032,DDSTW09CL001,DDSTW09CL002,DDSTW09BM001-2(no),DDSTW09BM003,DDSTW09BM004,DDSTW09BM005
3554 | Shijo | 2026-03-31 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A | 70T-Telescopic crane | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3555 | Shijo | 2026-03-31 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A | 100T Telescopic Crane | Equipment | Equipment | Laydown |  | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3556 | Shijo | 2026-03-31 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 02 | #N/A | 70T Crawler Crane | Equipment | Equipment | Laydown |  | Offloading | Idle | 10 |  |  |  | Crane Assembly is in progress
3557 | Shijo | 2026-03-31 | SARENS NASS | Harpreet Singh | 78753612 | Crane Operator- 70T Liebherr Telescopic Crane-02 | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3558 | Shijo | 2026-03-31 | Rial Al Khaleej | Shahzad Latif | 98845403 | Crane Operator-100T Zoomlion Telescopic | Manpower | Manpower | Laydown |  | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3559 | Shijo | 2026-03-31 | Encogroup | 55 SEAT BUS 7885YM (RENTAL) | #N/A | 55 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3559 | Shijo | 2026-03-31 | Encogroup | FLATBED TRAILER | #N/A | FLATBED TRAILER | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | loading and shifting of TR1010-26 materials (Case No. 45 -Tower- 11) to contractor's parking area,loading and shifting of CT1010-02 materials Case no. 12 (BM261, BM339, BM405), Case no. 14 (CL008 ,CL050), Case no. 30 (BM320-1, BM354-2) to yard-3,removal of materials from inside of the module and shifting of electrical supports for substation,offloading of the new 70T crawler crane and cable trays for reclaimer substation .
3559 | Shijo | 2026-03-31 | Encogroup | 4T JCB TELEHANDLER | #N/A | TELEHANDLER | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3559 | Shijo | 2026-03-31 | Encogroup | 13 SEAT BUS 4546MH | #N/A | 13 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3560 | Shijo | 2026-03-31 | Encogroup | 15 SEAT BUS 9405YR | #N/A | 15 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3561 | Shijo | 2026-03-31 | Encogroup | 14T FORKLIFT 2088LD | #N/A | 14T Fork lift | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3562 | Shijo | 2026-03-31 | Encogroup | 22 SEAT BUS 2498YD | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3563 | Shijo | 2026-03-31 | Encogroup | 22 SEAT BUS 8028WA | #N/A | 22 Seat Bus | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3564 | Shijo | 2026-03-31 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A | 300 KVA Generator | Equipment | Equipment | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3565 | Shijo | 2026-03-31 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A | 35 KVA Generator | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 | Material Handling | Material unloading by crane | Material unloading by crane | No usage
3566 | Shijo | 2026-03-31 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3567 | Shijo | 2026-03-31 | Encogroup | Akhilesh Kumar-Welder | U4181508 | Welder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3568 | Shijo | 2026-03-31 | Encogroup | Ameer Ali | 125440631 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3569 | Shijo | 2026-03-31 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3570 | Shijo | 2026-03-31 | Encogroup | Arunbhai Balubhai | 140764355 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3571 | Shijo | 2026-03-31 | Encogroup | Deepak Kumar | 140742125 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3572 | Shijo | 2026-03-31 | Encogroup | Dharmendra Kumar | 125199963 | Electrician | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3573 | Shijo | 2026-03-31 | Encogroup | Kadir Ansari | 140844778 | Painter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3574 | Shijo | 2026-03-31 | Encogroup | Amit Gupta | 140844783 | Painter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3575 | Shijo | 2026-03-31 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3576 | Shijo | 2026-03-31 | Encogroup | Muhammed Yasir | 118882687 | Permit Reciver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3576 | Shijo | 2026-03-31 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Fitter/Erector | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3577 | Shijo | 2026-03-31 | Encogroup | Haleem Ansari | 140683436 | Scaffolder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3578 | Shijo | 2026-03-31 | Encogroup | 7T HI-UP 1077DS | #N/A | 7T-HIAB | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3579 | Shijo | 2026-03-31 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | HIAB Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3580 | Shijo | 2026-03-31 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3581 | Shijo | 2026-03-31 | Encogroup | Kamal Kumar Sharma | 140848828 | Pipe Fitter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3582 | Shijo | 2026-03-31 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3583 | Shijo | 2026-03-31 | Encogroup | Jitu Kumar | 140844759 | Welder | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3584 | Shijo | 2026-03-31 | Encogroup | Vicken Tcheroyan | 121668462 | Site Manager | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3585 | Shijo | 2026-03-31 | Encogroup | Aneesh Joseph | 141253376 | Store Keeper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3586 | Shijo | 2026-03-31 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 | Mechanic | Manpower | Manpower | Common Area | _ | Loading | Day | 10 | Equipment Maintenance | Equipment Maintenance | Equipment Maintenance | _
3586 | Shijo | 2026-03-31 | Encogroup | Ahmed Khadeem Said Al Tourashi | 19753414 | Bus Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3587 | Shijo | 2026-03-31 | Encogroup | Mahmoud Khodr Hassan | 140623599 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3588 | Shijo | 2026-03-31 | Encogroup | Mohamed Irfan | 121937785 | Scaffolding Inspector | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3589 | Shijo | 2026-03-31 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3589 | Shijo | 2026-03-31 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | Scaffolding Inspector | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3590 | Shijo | 2026-03-31 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | Forklift Operator | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 |  |  |  | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3591 | Shijo | 2026-03-31 | Encogroup | Neeraj Gautham | 140844586 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3592 | Shijo | 2026-03-31 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 | Scaffolder | Sub Contactor | Sub Contactor | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3593 | Shijo | 2026-03-31 | Encogroup | Ismail Moussa | 141359024 | Hydraulic Mechanic | Manpower | Manpower | Laydown | _ | Preservation | Day | 10 | Material Handling | Material storage & preservation | Material storage & preservation | _
3594 | Shijo | 2026-03-31 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3595 | Shijo | 2026-03-31 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3596 | Shijo | 2026-03-31 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3597 | Shijo | 2026-03-31 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A | PICK-UP | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3598 | Shijo | 2026-03-31 | Encogroup | Prabin Brnnet Rani | 140805592 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3599 | Shijo | 2026-03-31 | Encogroup | Prakash Pandey | 140683371 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3600 | Shijo | 2026-03-31 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | RIgger | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 5 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of Crane dissambled parts
3601 | Shijo | 2026-03-31 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 | Crane Operator- 70T Crawler Crane- 02 | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of Crane dissambled parts
3602 | Shijo | 2026-03-31 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 | Technician | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of Crane dissambled parts
3603 | Shijo | 2026-03-31 | Bright Light | Sawar Khan | 122771611 | Mechanic | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of Crane dissambled parts
3601 | Shijo | 2026-03-31 | Bright Light | Imran Khan | 125287583 | Mechanic | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of Crane dissambled parts
3601 | Shijo | 2026-03-31 | Al Jaber Heavy Lift | Shobuj Raza | #N/A | Technician | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading of Crane dissambled parts
3604 | Shijo | 2026-03-31 | Encogroup | Syed Ihsan Haider | 100398391 | DuqmTrailer Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Duqm Trailer
3605 | Shijo | 2026-03-31 | Encogroup | Umesh Singh | 137114773 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3600 | Shijo | 2026-03-31 | Encogroup | Priyaranjan Kumar | 140844848 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3606 | Shijo | 2026-03-31 | Encogroup | Rajkumar Dubey | 140683399 | Rigger | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3607 | Shijo | 2026-03-31 | Encogroup | SCISSOR LIFT-01 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3608 | Shijo | 2026-03-31 | Encogroup | SCISSOR LIFT-02 | #N/A | SCISSOR LIFT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
3609 | Shijo | 2026-03-31 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3610 | Shijo | 2026-03-31 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3611 | Shijo | 2026-03-31 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A | Trailer | Equipment | Equipment | Laydown | _ | Loading | Day | 10 |  |  |  | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3612 | Shijo | 2026-03-31 | FAL Transport | Zain Ul Abdin | 124233837 | Trailer Driver | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 |  |  |  | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3613 | Shijo | 2026-03-31 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3614 | Shijo | 2026-03-31 | Encogroup | Samanta Soumitra | 140846698 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3615 | Shijo | 2026-03-31 | Encogroup | Sujeet Kumar | 140742177 | Grinder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3616 | Shijo | 2026-03-31 | Encogroup | Manjesh Bharti | 140696975 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
3617 | Shijo | 2026-03-31 | Encogroup | Pravesh Kumar | 140844572 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | TOWER LIGHT-1 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
0 | Shijo | 2026-03-31 | Encogroup | TOWER LIGHT-2 | #N/A | TOWER LIGHT | Equipment | Equipment | Laydown | _ | Loading | Idle | 10 |  |  |  | No usage
0 | Shijo | 2026-03-31 | Encogroup | Vinod Kumar | 122082863 | Grinder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Vivek Kumar | 140696989 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Suman Kumar Mandal | 116853914 | Electrical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Mukesh Kumar Rai | 117974933 | Scaffolder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Manoj Choudhary | 141502853 | Scaffolder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Lokesh Gupta | 140696961 | Assistant/Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Lema Kelly | 141307921 | Mechanical Assistant | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Duncan Lee Kelly | 141307968 | Mechanical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Daniel Jr Mosiquira | 141169047 | Welder | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Benny Thomas | 71437827 | Electrical Supervisor | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | AL Omar International | Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor | Sub Contactor | Sub Contactor | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Sandeep Kumar Sugreev | 141365042 | Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Ram Moorat Chandrabali | 141365061 | Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
| Shijo | 2026-03-31 | Encogroup | Balkishuan Muralidhar | 141365131 | Painter | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress
0 | Shijo | 2026-03-31 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Helper | Manpower | Manpower | Laydown | _ | Loading | Day | 10 | Material Handling | Material unloading by crane | Material unloading by crane | Loading and shifting of TR1010-26 materials Case No. 46 & 47 (Tower- 11&12) to contractor's parking area,removal of materials from inside of the module and shifting of electrical supports for substation,assembly of the new 70T crawler crane is in-progress

## Tasks
Mobilization Preparation | Mobilization Preparation | Material Handling & Segregation | Steel Structure Works |  | Grouting Works | Piping Works | Electrical Works | Instrumentation Works | Painting Coating | Finalization | Working Area | Item Tag
Material Handling | Site access preparation | Material unloading by crane | Ground pre-assembly | Strucutre Pre-Assembly | Foundation surface cleaning | Pipe rack support installation | Cable tray support installation | Instrument support installation | Surface cleaning | Final inspection | Yard 2 | CT-1010-02
Steel Structure Works | Area barricading | Material inspection | Trial fit-up | Strucutre Assembly | Formwork installation | Pipe erection | Cable tray installation | Instrument mounting | Surface inspection | Dimensional survey | Yard 3 | CT-1010-20
Grouting Works | Safety signage installation | Material verification with drawings | Temporary bolting | Dismantling | Grout mixing | Fit-up | Cable pulling | Tubing installation | Touch-up painting | Punch list clearance | Laydown | CT-1010-21
Piping Works | Crane mobilization & inspection | Material storage & preservation | Column erection |  | Grout pouring | Welding | Cable termination | Hook-up works | Final painting | As-built documentation | Parking Area | CT-1010-27
Electrical Works | Manlift mobilization | Material tagging & segregation | Beam erection |  | Grout curing | NDT inspection | Electrical testing | Loop checking | DFT inspection | Area handover | Long Conveyor | TR-1010-01
Instrumentation Works | Scaffolding mobilization | Equipment Maintenance | Platform installation |  |  | Pipe alignment | Dismantling of Electrical Cable | Dismantling of Junction box |  |  | Site Office | TR-1010-21
Painting Coating |  |  | Ladder & handrail installation |  |  |  | Dismantling of Cable Rack |  |  |  | Main Office | TR-1010-26
Finalization |  |  | Alignment (vertical & horizontal) | [7 empty] | Reclaimer Substation | TR-1010-20
Idle |  |  | Shim installation | [7 empty] | Common Area | TR-1010-27
Enco Interenal Transportation |  |  | Final bolting | [8 empty] | DBD Bld
Alignment of surveyor |  |  | Torque tightening | [8 empty] | Offloading
Enco Internal Utilities |  |  | Bolt marking | [8 empty] | Preservation
Equipment Maintenance |  |  | Dismantling of Cover | [8 empty] | Cable tray supports
Diesel filling |  |  | Dismantling of Structure | [8 empty] | Loading
|  |  | Equipment Maintenance | [8 empty] | Material Segregation
|  |  | Diesel filling | [8 empty] | Crane Dis/Assembly

## Manpower
=xlookup(Table134526_79101120212223242526[@[Name Surname]],'Manpower'!A1
S/N | ID# | Name |  | Nationality | Skill | Direct/Indirect | Category
1 | Encogroup | George Tcheroyan | 121598538 | LEBANESE | Project Manager | Indirect | Manpower
2 | Encogroup | Vicken Tcheroyan | 121668462 | LEBANESE | Site Manager | Indirect | Manpower
3 | Encogroup | Mhamed Sheikh | 122370101 | LEBANESE | Quality Manager | Indirect | Manpower
4 | Encogroup | Rabih Ali El Borji | 123541357 | LEBANESE | Admin Manager | Indirect | Manpower
5 | Encogroup | Peter Farah | 122045765 | LEBANESE | Lead Mechanical Engineer | Indirect | Manpower
14 | Encogroup | Abdullah Humaid Al Nofali | 27637114 | OMANI | Driver | Indirect | Manpower
7 | Encogroup | Maroun Raymond Sarkis | 127387473 | LEBANESE | Mechanical engineer | Indirect | Manpower
8 | Encogroup | Cherbel Nabih Gebrael | 116894252 | LEBANESE | Purchasing Manager | Indirect | Manpower
9 | Encogroup | Fenil Paul | 137098196 | Indian | Lifting engineer | Indirect | Manpower
17 | Encogroup | Abishek Pandey | 123487214 | Indian | Gas Cutter | Direct | Manpower
239 | BUSHRA | Adil | Not Required |  | Diesel Re-fueling team | Equipment MP | Manpower
12 | Encogroup | Gokul Reghu | 123472431 | Indian | Site Coordinator / Timekeeper | Indirect | Manpower
13 | Encogroup | Fatema Al Abri | 12782421 | OMANI | Admin Assistant | Indirect | Manpower
219 | Encogroup | Akhilesh Kumar-Welder | U4181508 |  | Welder | Direct | Manpower
85 | Encogroup | Ali Riza | 140849254 | TURKIYE | Construction Manager | Indirect | Manpower
16 | Encogroup | Pappu Kumar Yadaw | 122082769 | Indian | Grinder | Direct | Manpower
58 | Encogroup | Arun Kumar | 123039392 | Indian | Fitter/Erector | Direct | Manpower
10 | Encogroup | Arunraj Rajendiren | 118833981 | Indian | Scheduler / Planning Engineer | Indirect | Manpower
19 | Encogroup | Ameer Ali | 125440631 | PAKISTANI | Rigger | Direct | Manpower
20 | Encogroup | Wesley Jan Estandarte | 117255966 | Philipino | Mechanical Supervisor | Direct | Manpower
128 | Encogroup | Ashwini Kumar | 127414586 | Indian | Electrician | Direct | Manpower
31 | Encogroup | Azzam Ahmed | 124346519 | LEBANESE | Mechanical Foreman | Direct | Manpower
110 | Encogroup | Bader Al-Buloshi | 15290981 | OMANI | Driver | Indirect | Manpower
24 | Encogroup | Jaison Marottikkal Lorance | 120892366 | Indian | HSE Officer | Indirect | Manpower
32 | Encogroup | Bader Nasser Said Masoud Al Nofali | 28065391 | OMANI | Driver | Indirect | Manpower
26 | Encogroup | Umesh Singh | 137114773 | Indian | Rigger | Direct | Manpower
27 | Encogroup | Prakash Pandey | 140683371 | Indian | Rigger | Direct | Manpower
28 | Encogroup | Rajkumar Dubey | 140683399 | Indian | Rigger | Direct | Manpower
29 | Encogroup | Haleem Ansari | 140683436 | Indian | Scaffolder | Direct | Manpower
122 | Encogroup | Bal Krishna Bishwakarma | 122179637 | NEPALI | Mechanical Supervisor | Direct | Manpower
59 | Encogroup | Balister Yadhav | S3549132 | Indian | Grinder | Direct | Manpower
134 | Encogroup | Basheer Abubakkar | 141177603 | Indian | Crane Operator | Equipment MP | Manpower
86 | Encogroup | Bhanu Kumar | 140848833 | Indian | Welder | Direct | Manpower
34 | Encogroup | Dipu Sing | 140697025 | Indian | Assistant/Helper | Direct | Manpower
35 | Encogroup | Manjesh Bharti | 140696975 | Indian | Assistant/Helper | Direct | Manpower
36 | Encogroup | Lokesh Gupta | 140696961 | Indian | Assistant/Helper | Direct | Manpower
37 | Encogroup | Vivek Kumar | 140696989 | Indian | Assistant/Helper | Direct | Manpower
38 | Encogroup | Lav Kansaraj | 140697039 | Indian | Fitter/Erector | Direct | Manpower
39 | Encogroup | Shijo Saji | 140696356 | Indian | Mechanical engineer | Indirect | Manpower
40 | Encogroup | Fawaz Aamir Said Hamdoon Al-Naamani | 23659394 | OMANI | Junior PRO | Indirect | Manpower
71 | Encogroup | Dharmendra Kumar | 125199963 | Indian | Electrician | Direct | Manpower
42 | Encogroup | Emile Baradhi | 118041216 | LEBANESE | Material Manager | Indirect | Manpower
43 | Encogroup | Vinay Chaudhary | 122179604 | Indian | Fitter/Erector | Direct | Manpower
44 | Encogroup | Maryam Abdallah Said Al Matrosushi | 14246361 | OMANI | QS Engineer | Indirect | Manpower
45 | Encogroup | Sheikha Abdallah Said Al Matrosushi | 11196769 | OMANI | HR Officer | Indirect | Manpower
23 | Encogroup | Dhinesh Vaithiyanathan | 140645388 | Indian | Store keeper | Indirect | Manpower
242 | Al Jaber Heavy Lift | Fawad Ahmed | 102607563 |  | Technician | Equipment MP | Manpower
48 | Encogroup | Afaaq Hussain | 126724428 | PAKISTANI | Surveyor | Indirect | Manpower
49 | Encogroup | Vinod Kumar | 122082863 | Indian | Grinder | Direct | Manpower
50 | Encogroup | Abhishek Kumar Tiwari | 140742144 | Indian | Assistant/Helper | Direct | Manpower
51 | Encogroup | Ranaanand Kumar | 140742088 | Indian | Fitter/Erector | Direct | Manpower
52 | Encogroup | Deepak Kumar | 140742125 | Indian | Assistant/Helper | Direct | Manpower
6 | Encogroup | George Zouhair Abi Farah | 121820536 | LEBANESE | Facility Management | Indirect | Manpower
95 | Encogroup | Ghulam Qadir Muhammad Yousaf | 124398279 | PAKISTANI | Permit Receiver | Indirect | Manpower
55 | Encogroup | Sujeet Kumar | 140742177 | Indian | Grinder | Direct | Manpower
133 | Encogroup | Gurpreet Sing | 86971535 | Indian | Crane Operator | Equipment MP | Manpower
70 | Encogroup | Gyenendra Kumar Gupta | 140809004 | Indian | Fitter/Erector | Direct | Manpower
57 | Encogroup | Hareendra Shahani | X6330749 | Indian | Welder | Direct | Manpower
111 | Encogroup | Ibrahim Rashid Mubarak Al-Abri | 9138415 | OMANI | HIAB Driver | Equipment MP | Manpower
60 | Encogroup | Sajilal Sasidharan | 103717582 | Indian | Accountant | Indirect | Manpower
61 | Encogroup | Arunbhai Balubhai | 140764355 | Indian | Fitter/Erector | Direct | Manpower
62 | Encogroup | Sonu Kumar Pandey | 140764706 | Indian | Rigger | Direct | Manpower
63 | Encogroup | Sulthan Humaid Mohammed Humaid Al Nofli | 19255078 | OMANI | Driver | Indirect | Manpower
64 | Encogroup | Mathan Kumar | 140796986 | Indian | Mechanical QC | Indirect | Manpower
65 | Encogroup | Rejin Rebi | 140805554 | Indian | Assistant/Helper | Direct | Manpower
66 | Encogroup | Sajith Saji Kanagam | 140805568 | Indian | Assistant/Helper | Direct | Manpower
109 | Encogroup | Imaran Ahamad Taj Mohammad | 140954262 | Indian | Welding Inspector | Indirect | Manpower
68 | Encogroup | Shyam Dhani | 140806218 | Indian | Fitter/Erector | Direct | Manpower
153 | Encogroup | Irshad Ejas Hussain Shaikh | #N/A | Indian | HSE Administrative | Indirect | Manpower
129 | Encogroup | Jaison Vijay Menezes | R3971143 | Indian | Mechanical Foreman | Direct | Manpower
41 | Encogroup | Jean-Luc-Joseph | 140694441 | FRANCE | Welding Engineer | Indirect | Manpower
72 | Encogroup | Suman Kumar Mandal | 116853914 | NEPALI | Electrical Supervisor | Direct | Manpower
87 | Encogroup | Jitendra Kumar Yadav | AG111207 | Indian | Assistant/Helper | Direct | Manpower
78 | Encogroup | Kadir Ansari | 140844778 | Indian | Painter | Direct | Manpower
75 | Encogroup | Fadi Al Asmar | 140841472 | LEBANESE | Electrical Superintendent | Indirect | Manpower
76 | Encogroup | Rajesh Thakur | 124565057 | Indian | Fitter/Erector | Direct | Manpower
77 | Encogroup | Amit Gupta | 140844783 | Indian | Painter | Direct | Manpower
151 | Encogroup | Lema Kelly | 141307921 | Lituanie | Mechanical Assistant | Indirect | Manpower
79 | Encogroup | Dharmvir Upadhyay | 140844797 | Indian | Fitter/Erector | Direct | Manpower
80 | Encogroup | Priyaranjan Kumar | 140844848 | Indian | Assistant/Helper | Direct | Manpower
81 | Encogroup | Jitu Kumar | 140844759 | Indian | Welder | Direct | Manpower
82 | Encogroup | Verendra Kumar Hari Lal | 140844618 | Indian | Assistant/Helper | Direct | Manpower
83 | Encogroup | Pravesh Kumar | 140844572 | Indian | Assistant/Helper | Direct | Manpower
84 | Encogroup | Neeraj Gautham | 140844586 | Indian | Assistant/Helper | Direct | Manpower
21 | Encogroup | Mahmoud Khodr Hassan | 140623599 | LEBANESE | Mechanical Supervisor | Direct | Manpower
121 | Encogroup | Mahmoud Mohamad Moussa | 116858297 | LEBANESE | Mechanical Superintendent | Indirect | Manpower
25 | Encogroup | Md Rashed Mohmed | 140663253 | Indian | Painting Inspector | Indirect | Manpower
88 | Encogroup | Surajit Maity | 140846684 | Indian | Assistant/Helper | Direct | Manpower
245 | BG | MD Rizwan | #N/A |  | Driver | Equipment MP | Manpower
90 | Encogroup | Kamal Kumar Sharma | 140848828 | Indian | Pipe Fitter | Direct | Manpower
91 | Encogroup | Arunkumar Surendran | 127859069 | Indian | QC Mechanical Engineer | Indirect | Manpower
47 | Encogroup | Mohamed Irfan | 121937785 | PAKISTANI | Scaffolding Inspector | Direct | Manpower
93 | Encogroup | Sathishkumar Kasthurisamy | 140859482 | Indian | Draftsman Engineer | Indirect | Manpower
231 | Al Jaber Heavy Lift | Mohammad Ismail | 116448869 |  | Crane Operator | Equipment MP | Manpower
241 | Al Jaber Heavy Lift | Mohammed Attiq | 113787454 |  | Crane Operator- 70T Crawler Crane- 02 | Equipment MP | Manpower
96 | Encogroup | Tamoor Ali Khan | 135325259 | PAKISTANI | Permit Receiver | Indirect | Manpower
97 | Encogroup | Mohammad Shoaib Akhtar | 136277866 | PAKISTANI | Permit Receiver | Indirect | Manpower
98 | Encogroup | Ibrahim Karam Ali Al Balushi | 15485532 | OMANI | Driver | Indirect | Manpower
228 | SARENS NASS | Moshin Saleem Salim AL-Shukaili | 14552941 |  | Crane Operator- 70T Hitachi Crawler crane | Equipment MP | Manpower
100 | Encogroup | Alla Said Abdallah Al Jabri | 12441043 | OMANI | IT Engineer | Indirect | Manpower
101 | Encogroup | Ahmed Khadeem Said Al Tourashi | 19753414 | OMANI | Bus Driver | Indirect | Manpower
102 | Encogroup | Nasr Nasser Said Masoud Al Nofli | 19110768 | OMANI | Driver | Indirect | Manpower
103 | Encogroup | Samar Habib | 141246094 | LEBANESE | Mechanical Engineer | Indirect | Manpower
104 | Encogroup | Amran Hamood Marhoon Al-Hashemi | 10612625 | OMANI | Junior HSE Officer | Indirect | Manpower
105 | Encogroup | Md Siddiqur Rahaman Md Ramizuddin | 123805496 | BANGLADESHI | Fitter/Erector | Direct | Manpower
106 | AL Omar International TRAD AND CONT | Md Tarek Hossain | 114929202 | BANGLADESHI | RIgger | Direct | Sub Contactor
107 | AL Omar International TRAD AND CONT | Omar Faruk Sarafat Ali | 106093463 | BANGLADESHI | RIgger | Direct | Sub Contactor
108 | AL Omar International TRAD AND CONT | Md Hasan Howlader | 115018512 | BANGLADESHI | RIgger | Direct | Sub Contactor
147 | Encogroup | Motaseem Kariem | #N/A | LEBANESE | Welding Foreman | Direct | Manpower
18 | Encogroup | Muhammad Zeeshan | 125440626 | PAKISTANI | Fitter/Erector | Direct | Manpower
15 | Encogroup | Muhammed Ramzan | 122179642 | PAKISTANI | Grinder | Direct | Manpower
112 | Encogroup | Ajithkumar Aravindakshanpillai | 140693697 | Indian | HSE Officer | Indirect | Manpower
113 | Encogroup | Rogie Jr Mabilog | 141169071 | Philipino | Welding Supervisor | Direct | Manpower
114 | Encogroup | Daniel Jr Mosiquira | 141169047 | Philipino | Welder | Direct | Manpower
115 | Encogroup | Reymond Cruz | 141169033 | Philipino | Welder | Direct | Manpower
116 | Encogroup | Ryan Batuto | 141169028 | Philipino | Welder | Direct | Manpower
117 | Encogroup | Erick Atienza | 141169052 | Philipino | Welder | Direct | Manpower
118 | Encogroup | Clyde Abrazaldo | 141169085 | Philipino | Welder | Direct | Manpower
119 | Encogroup | Prathip Sundaram | 140995321 | Indian | Scheduling Engineer | Indirect | Manpower
120 | Encogroup | Mustafa Moosa Ahned Al Balushi | 18114443 | OMANI | Driver | Indirect | Manpower
22 | Encogroup | Omaima Sultan Saif Al- Busaidi | 12825038 | OMANI | Admin Assistant | Indirect | Manpower
131 | Encogroup | Othman Mohammed Najman Al Zadjali | #N/A | OMANI | Trailer Driver | Indirect | Manpower
123 | Encogroup | Pinto Kuriakose | 132423982 | Indian | Mechanic Supervisor | Direct | Manpower
124 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 | PAKISTANI | HSE Officer | Indirect | Sub Contactor
125 | Encogroup | Prasad Vadakkedath Me Ramankutty | 83070339 | Indian | HSE Engineer | Indirect | Manpower
126 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 | PAKISTANI | RIgger | Direct | Sub Contactor
127 | Encogroup | Akhilesh Kumar | 141359235 | Indian | Fitter | Direct | Manpower
67 | Encogroup | Prabin Brnnet Rani | 140805592 | Indian | Assistant/Helper | Direct | Manpower
73 | Encogroup | Pradeep Pandey | 122274652 | Indian | Welder | Direct | Manpower
130 | AL Omar International TRAD AND CONT | Mohammed Rokan Mia | 105813698 | BANGLADESHI | Scaffolding Inspector | Indirect | Sub Contactor
53 | Encogroup | Praful Kumar Rai | 117020738 | Indian | Fitter/Erector | Direct | Manpower
132 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 | BANGLADESHI | RIgger | Direct | Sub Contactor
56 | Encogroup | Praveen Singh | 122015438 | Indian | Erector/Manlift Operator | Direct | Manpower
74 | Encogroup | Rabih Rifai | 116915582 | LEBANESE | Mechanical Superintendent | Indirect | Manpower
135 | Encogroup | Shawaj Alam | 141179467 | Indian | Crane Operator | Equipment MP | Manpower
136 | AL Omar International TRAD AND CONT | Mohammed Gias Uddin | 96409155 | BANGLADESHI | Scaffolder | Direct | Sub Contactor
137 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain Muhammad Hussain | 76647648 | PAKISTANI | RIgger | Direct | Sub Contactor
138 | Encogroup | Mazin Abdullah Ali Al -Aisaee | 8125926 | OMANI | Driver | Indirect | Manpower
139 | AL Omar International TRAD AND CONT | Ripon Tofayel Ahmmad | 116676257 | BANGLADESHI | Scaffolder | Direct | Sub Contactor
140 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 | PAKISTANI | Forklift Operator | Equipment MP | Sub Contactor
141 | AL Omar International TRAD AND CONT | Arifur Rahman | 115731078 | BANGLADESHI | Scaffolder | Direct | Sub Contactor
142 | Encogroup | Senthil Vel Sekar | 141228922 | Indian | Document controller | Indirect | Manpower
143 | Encogroup | Tamilselvan Tamilmani | 141250908 | Indian | Mechanical Engineer | Indirect | Manpower
144 | Encogroup | Aneesh Joseph | 141253376 | Indian | Store Keeper | Indirect | Manpower
145 | AL Omar International TRAD AND CONT | Mohammad Shahadat Hossain Sikdar | 95335424 | BANGLADESHI | Scaffolder | Direct | Sub Contactor
146 | Encogroup | Ibrahim Karime | 71257815 | LEBANESE | Logistics Supervisor | Direct | Manpower
238 | BUSHRA | Rashid | #N/A |  | Diesel Re-fueling team | Equipment MP | Manpower
99 | Encogroup | Raya Salim Khamis Said Al Junaibi | 14915995 | OMANI | Admin Coordinator | Indirect | Manpower
149 | Encogroup | Ahmad Kerbaj | 132915855 | LEBANESE | Mechanical Supervisor | Direct | Manpower
150 | Encogroup | Ebin Ben | 116589569 | Indian | Mechanical Engineer | Indirect | Manpower
11 | Encogroup | Rijo Pappachan Thankachan | 140477664 | Indian | Junior HSE Officer | Indirect | Manpower
152 | Encogroup | Duncan Lee Kelly | 141307968 | Lituanie | Mechanical Supervisor | Direct | Manpower
148 | Encogroup | Rodie Jabber | 141505123 | LEBANESE | Mechanical Engineer | Indirect | Manpower
154 | Encogroup | Khundrakpam Shyamsan Singh | 99596058 | Indian | HSE Officer | Indirect | Manpower
155 | Encogroup | Sreejith Thekkedath Sivaraman | 141322471 | Indian | Welding Inspector | Indirect | Manpower
156 | Encogroup | Amal Kannoor Ramachandran | 141322485 | Indian | Electrical Engineer | Indirect | Manpower
157 | AL Omar International TRAD AND CONT | Mohammad Alam | 85813175 | BANGLADESHI | Scaffolding Supervisor | Direct | Sub Contactor
158 | Encogroup | Manikandaraj Muthaia | 99112308 | Indian | HR Manager | Indirect | Manpower
159 | Encogroup | Mahmoud Moussa | 141358988 | LEBANESE | Hydraulic Mechanic | Direct | Manpower
160 | Encogroup | Hadi Moussa | 141358993 | LEBANESE | Fitter | Direct | Manpower
161 | Encogroup | Ismail Moussa | 141359024 | LEBANESE | Hydraulic Mechanic | Direct | Manpower
162 | Encogroup | Akhilesh Kumar | 141359235 | Indian | Welder | Direct | Manpower
163 | Encogroup | Rajeev Kumar Sah | 141359216 | Indian | Electrician | Direct | Manpower
164 | Encogroup | Tej Pradap Sharma | 141365089 | Indian | Fitter | Direct | Manpower
165 | Encogroup | Pradip Rai | 141365023 | Indian | Grinder | Direct | Manpower
166 | Encogroup | Yogendra Kumar Rupachand | 141365094 | Indian | Helper | Direct | Manpower
167 | Encogroup | Shivam Yadhav | 141365126 | Indian | Helper | Direct | Manpower
168 | Encogroup | Sandeep Kumar Sugreev | 141365042 | Indian | Helper | Direct | Manpower
169 | Encogroup | Ravi Yadav | 141365164 | Indian | Helper | Direct | Manpower
170 | Encogroup | Ram Moorat Chandrabali | 141365061 | Indian | Helper | Direct | Manpower
171 | Encogroup | Gulshan Gautham | 141365075 | Indian | Helper | Direct | Manpower
172 | Encogroup | Sanjay Kumar Suresh Ram | 141365037 | Indian | Painter | Direct | Manpower
173 | Encogroup | Balkishuan Muralidhar | 141365131 | Indian | Painter | Direct | Manpower
174 | Encogroup | Ramesh Kumar | 141365056 | Indian | Fitter | Direct | Manpower
175 | Encogroup | Atif Rasheed | 127331574 | PAKISTANI | Permit Receiver | Indirect | Manpower
176 | Encogroup | Muhammad Bilal Hussain Al Taf | 120653364 | PAKISTANI | Surveyor | Indirect | Manpower
94 | Encogroup | Said Helal Mohammed Al-Amri | #N/A | OMANI | Driver | Indirect | Manpower
178 | Encogroup | Ajin Paramesvaran | 141377747 | Indian | Painter | Direct | Manpower
179 | Encogroup | Rajeev Kumar Sadasivam | 141377771 | Indian | Painter | Direct | Manpower
180 | Encogroup | Vijay Kumar Muthu | 141377714 | Indian | Painter | Direct | Manpower
181 | Encogroup | Renjith Kumar | 141377752 | Indian | Rigger | Direct | Manpower
182 | Encogroup | Rajesh Sadahanndan Pillai | 141381507 | Indian | HSE Manager | Indirect | Manpower
183 | Encogroup | Elias Zaatar | 121594839 | LEBANESE | Electrical Engineer | Indirect | Manpower
184 | Encogroup | MD shahnawaj Ahmed | 141402153 | Indian | Forklift Operator | Indirect | Manpower
185 | Encogroup | Mohammad Khalfan Juma Al-Aufi | 1487544 | OMANI | Driver | Indirect | Manpower
186 | SARENS NASS | Shinu S | 109957631 |  | Crane Operator-130T Liebherr Crawler | Equipment MP | Manpower
187 | Al Jaber Heavy Lift | Abid Hussain | 112778626 |  | Crane Operator-150T Hitachi Crawler | Equipment MP | Manpower
188 | GAF | Umesh Kumar | 96405686 |  | Helper | Direct | Sub Contactor
189 | Rial Al Khaleej | Shahzad Latif | 98845403 |  | Crane Operator-100T Zoomlion Telescopic | Equipment MP | Manpower
190 | GAF | Biomanna Mohanan | - |  | Helper | Direct | Sub Contactor
191 | GAF | Irfan Ansari | 78785394 |  | Helper | Direct | Sub Contactor
192 | GAF | Vijaya Kumar (5036) | 71345102 |  | Mason | Direct | Sub Contactor
193 | AL NAHDHA | MD Sadiq | 123805496 |  | Forklift Operator-7T | Equipment MP | Sub Contactor
194 | AL Omar International | MD Hasan Howlander | 115018512 |  | Rigger | Direct | Sub Contactor
195 | AL Omar International | Omar Faruk Sarafat Ali | 106093463 |  | Rigger/Man-Lift Operator | Direct | Sub Contactor
196 | SARENS NASS | Gulzar Singh | 79502392 |  | Crane Operator- 70T Liebherr Telescopic Crane-01 | Equipment MP | Manpower
197 | AL Omar International | Md Tarek Hossain | 114929202 |  | Rigger | Direct | Sub Contactor
198 | GAF | DILIP KUMAR (5042) | 113484195 |  | Supervisor | Direct | Sub Contactor
199 | Bright Light | Siyaram Yadav | 81379273 |  | Crane Operator-100T Sany Telescopic | Equipment MP | Manpower
200 | FAL Transport | Zain Ul Abdin | 124233837 |  | Trailer Driver | Equipment MP | Sub Contactor
201 | Rabwu Ahamal AL Khaleej Trad | Saqib Ali | 131431131 |  | Rigger | Direct | Sub Contactor
202 | AL Omar International | Mohammed Rokan Mia | 105813698 |  | Scaffolding Inspector | Indirect | Sub Contactor
203 | AL Saif & Al QALLM ENT LLC | Shoib Akhtar | 135762195 |  | HSE Officer | Indirect | Sub Contactor
204 | AL Saif & Al QALLM ENT LLC | MD Ayub Ali | 108478006 |  | Rigger | Direct | Sub Contactor
205 | AL Omar International | Mohammed Gias Uddin | 96409155 |  | Scaffolder | Direct | Sub Contactor
206 | AL Saif & Al QALLM ENT LLC | Sakhawat Hussain | 76647648 |  | Rigger | Direct | Sub Contactor
207 | AL Saif & Al QALLM ENT LLC | Muhammed Rafi | 135340657 |  | Forklift Operator-14T | Equipment MP | Sub Contactor
208 | AL Omar International | Ripon Tofayel Ahmmad | 116676257 |  | Scaffolder | Direct | Sub Contactor
209 | AL Omar International | Arifur Rahman | 115731078 |  | Scaffolder | Direct | Sub Contactor
210 | Sarens Nass | Rampratap Chauhan | 112346941 |  | Rigger | Direct | Sub Contactor
211 | Sarens Nass | Dinesh Yadav | 12284034 |  | Rigger | Direct | Sub Contactor
212 | Sarens Nass | Padmanaban Sevu | 77873529 |  | Mechanic | Direct | Sub Contactor
213 | AL Omar International | Mohammad Shahadat Hossain Sikdar | 95335424 |  | Scaffolder | Direct | Sub Contactor
214 | AL Omar International | Mohammad Jehangir Alam | 85812175 |  | Scaffolding Supervisor | Direct | Sub Contactor
215 | Bright Light | Subash H.K | 83935096 |  | Technician | Direct | Sub Contactor
| Bright Light | Praveen Prakash | #N/A |  | Technician | Direct | Sub Contactor
216 | Bright Light | Jalaludeen S | 103199925 |  | Mechanic | Direct | Sub Contactor
217 | Bright Light | Gurtirath Singh | 114531608 |  | Crane Operator-150T Sany Crawler | Equipment MP | Manpower
218 | Encogroup | Hadi Moussa | 141358993 |  | Hydraulic Mechanic | Direct | Manpower
89 | Encogroup | Samanta Soumitra | 140846698 | Indian | Assistant/Helper | Direct | Manpower
220 | Encogroup | Laxman Chaudhary | 117207568 |  | Electrician | Direct | Manpower
221 | Encogroup | Ejaz Hussein | 112952143 |  | HSE Coordinator | Indirect | Manpower
222 | Encogroup | Bittu Kumar | 140844604 |  | Painter | Direct | Manpower
223 | SARENS NASS | Harpreet Singh | 78753612 |  | Crane Operator- 70T Liebherr Telescopic Crane-02 | Equipment MP | Manpower
224 | Bright Light | Sawar Khan | 122771611 |  | Mechanic | Direct | Sub Contactor
225 | Bright Light | Imran Khan | 125287583 |  | Mechanic | Direct | Sub Contactor
226 | AL Omar International Tarde&Contracting SPC | Md Totul | 115122635 |  | Scaffolder | Direct | Sub Contactor
227 | Encogroup | Jayakrishnan Chandrasekaran | 75199413 |  | Mechanic | Direct | Manpower
30 | Encogroup | Sandeep Kumar Yadhav | P6050502 | Indian | Welder | Direct | Manpower
229 | Encogroup | Mukesh Kumar Rai | 117974933 |  | Scaffolder | Direct | Manpower
230 | Encogroup | Manoj Choudhary | 141502853 |  | Scaffolder | Direct | Manpower
46 | Encogroup | Sheikha Rashid Saif-Al Ghaithi | 12637107 | OMANI | QS Engineer | Indirect | Manpower
232 | Encogroup | Ashwin Shivaraman | 127414586 |  | HSE Officer | Indirect | Manpower
233 | Encogroup | Benny Thomas | 71437827 |  | Electrical Supervisor | Indirect | Manpower
234 | Encogroup | Abdullah Khalfan Humaid Al Saidi | 7065269 |  | Lowbed Trailer Driver | Indirect | Manpower
235 | Encogroup | Deepu Chauhan | 117871996 |  | Electrical Supervisor | Indirect | Manpower
236 | Encogroup | Anandbabu subbiah | 81612139 |  | Mechanic | Direct | Manpower
237 | Encogroup | Hassan Salah Mechhawi | 130805123 |  | Mechanic | Direct | Manpower
246 | Al Jaber Heavy Lift | Shobuj Raza | #N/A |  | Technician | Equipment MP | Manpower
243 | Al Jaber Heavy Lift | Shobul Rata | #N/A |  | Technician | Equipment MP | Manpower
240 | Encogroup | Mostafa Khaled Fattouh | 140623552 |  | Mechanic | Direct | Manpower
69 | Encogroup | Sohan Gupta | 140806191 | Indian | Welder | Direct | Manpower
54 | Encogroup | Subodh Sah | S8474313 | Indian | Assistant/Helper | Direct | Manpower
177 | Encogroup | Suresh Selvam | 141377709 | Indian | Helper | Direct | Manpower
244 | Encogroup | Syed Ihsan Haider | 100398391 |  | DuqmTrailer Driver | Manpower | Manpower
250 | OCI | Tanveer | #N/A |  | DRIVER | Equipment MP | Manpower
92 | Encogroup | Venkatesh Annapu | 84357232 | Indian | Rigger | Direct | Manpower
247 | Encogroup | Muhammed Yasir | 118882687 |  | Permit Reciver | Indirect | Manpower
248 | OCI | Azhar | not required |  | DRIVER | DRIVER | DRIVER
249 | ATS | Ali Haider | 100398391 |  | DRIVER | DRIVER | DRIVER
33 | Encogroup | Vijai Kumar Yadhav | 123039387 | Indian | Fitter/Erector | Direct | Manpower
251 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 01 | #N/A |  | 70T Crawler Crane | Equipment | Equipment
252 | Al Jaber Heavy Lift | 70T Hitachi Crawler Crane- 02 | #N/A |  | 70T Crawler Crane | Equipment | Equipment
253 | Bright Light | 100T TELESCOPIC CRANE (RENTAL)-Sany | #N/A |  | 100T Telescopic Crane | Equipment | Equipment
254 | Riyan Al Khaleej | 100T TELESCOPIC CRANE (RENTAL)-ZL | #N/A |  | 100T Telescopic Crane | Equipment | Equipment
255 | Nass Group | 70T TELESCOPIC CRANE-02 (RENTAL)-Liebherr | #N/A |  | 70T-Telescopic crane | Equipment | Equipment
256 | Encogroup | 12M SCISSOR LIFT | #N/A |  | 12M Scissor Lift | Equipment | Equipment
257 | Encogroup | 13 SEAT BUS 4546MH | #N/A |  | 13 Seat Bus | Equipment | Equipment
258 | Nass Group | 130T CRAWLER CRANE (RENTAL)-Liebherr | #N/A |  | 130T Crawler Crane | Equipment | Equipment
259 | Encogroup | 14T FORKLIFT 2088LD | #N/A |  | 14T Fork lift | Equipment | Equipment
260 | Encogroup | 15 SEAT BUS 9405YR | #N/A |  | 15 Seat Bus | Equipment | Equipment
261 | Al Jaber Heavy Lift | 150T CRAWLER CRANE (RENTAL)-Hitachi | #N/A |  | 150T-Crawler Crane | Equipment | Equipment
262 | Bright Light | 150T CRAWLER CRANE (RENTAL)-Sany | #N/A |  | 150T-Crawler Crane | Equipment | Equipment
263 | Encogroup | 55 SEAT BUS | #N/A |  | 55 Seat Bus | Equipment | Equipment
264 | Encogroup | 55 SEAT BUS 7885YM (RENTAL) | #N/A |  | 55 Seat Bus | Equipment | Equipment
265 | Encogroup | 22 SEAT BUS 2498YD | #N/A |  | 22 Seat Bus | Equipment | Equipment
266 | Encogroup | 22 SEAT BUS 2746MB | #N/A |  | 22 Seat Bus | Equipment | Equipment
267 | Encogroup | 22 SEAT BUS 8028WA | #N/A |  | 22 Seat Bus | Equipment | Equipment
268 | Encogroup | 22KVA GENERATOR | #N/A |  | 22KVA-Generator | Equipment | Equipment
269 | Encogroup | 22M HAULOTTE MANLIFT-1 | #N/A |  | 22M-Manlift | Equipment | Equipment
270 | Encogroup | 22M HAULOTTE MANLIFT-2 | #N/A |  | 22M-Manlift | Equipment | Equipment
271 | Encogroup | 22M LCMG MANLIFT | #N/A |  | 22M-Manlift | Equipment | Equipment
272 | Encogroup | 28M LCMG MANLIFT | #N/A |  | 28M-Manlift | Equipment | Equipment
273 | Encogroup | 300/330KVA CUMMINS GENERATOR | #N/A |  | 300 KVA Generator | Equipment | Equipment
274 | Encogroup | 35/40KVA CUMMINS GENERATOR | #N/A |  | 35 KVA Generator | Equipment | Equipment
275 | Encogroup | 40KVA CUMMINS GENERATOR | #N/A |  | 40KVA Generator | Equipment | Equipment
276 | Encogroup | 22KVA GENERATOR | #N/A |  | 22 KVA Generator | Equipment | Equipment
277 | Encogroup | 40M JLG MANLIFT | #N/A |  | 40M-Manlift | Equipment | Equipment
278 | Encogroup | 4T JCB TELEHANDLER | #N/A |  | TELEHANDLER | Equipment | Equipment
279 | Nass Group | 70T TELESCOPIC CRANE-01 (RENTAL)-Liebherr | #N/A |  | 70T-Telescopic crane | Equipment | Equipment
280 | Encogroup | 7T FORKLIFT | #N/A |  | 7T-Fork lift | Equipment | Equipment
281 | Encogroup | 80T GROVE TELESCOPIC CRANE | #N/A |  | 80T-Telescopic crane | Equipment | Equipment
282 | Bright Light | Renault FLATBED TRAILER 3576MD (RENTAL) | #N/A |  | Trailer | Equipment | Equipment
283 | Encogroup | 7T HI-UP 1077DS | #N/A |  | 7T-HIAB | Equipment | Equipment
284 | Encogroup | FLATBED TRAILER | #N/A |  | FLATBED TRAILER | Equipment | Equipment
285 | Encogroup | Renault Lowbed Trailer 2939ML | #N/A |  | Trailer | Equipment | Equipment
286 | Al Asrah Al Mumayaza Trad | PICK-UP 15BM (RENTAL) | #N/A |  | PICK-UP | Equipment | Equipment
287 | Al Asrah Al Mumayaza Trad | PICK-UP 2819DA (RENTAL) | #N/A |  | PICK-UP | Equipment | Equipment
288 | Al Asrah Al Mumayaza Trad | PICK-UP 4265BM (RENTAL) | #N/A |  | PICK-UP | Equipment | Equipment
289 | Al Asrah Al Mumayaza Trad | PICK-UP 569WA (RENTAL) | #N/A |  | PICK-UP | Equipment | Equipment
290 | Encogroup | SCISSOR LIFT-01 | #N/A |  | SCISSOR LIFT | Equipment | Equipment
291 | Encogroup | SCISSOR LIFT-02 | #N/A |  | SCISSOR LIFT | Equipment | Equipment
292 | Encogroup | SCISSOR LIFT-03 | #N/A |  | SCISSOR LIFT | Equipment | Equipment
293 | Encogroup | SCISSOR LIFT-04 | #N/A |  | SCISSOR LIFT | Equipment | Equipment
294 | Encogroup | TOWER LIGHT-1 | #N/A |  | TOWER LIGHT | Equipment | Equipment
295 | Encogroup | TOWER LIGHT-2 | #N/A |  | TOWER LIGHT | Equipment | Equipment
296 | Encogroup | TOWER LIGHT-3 | #N/A |  | TOWER LIGHT | Equipment | Equipment
297 | Encogroup | TOWER LIGHT -4 | #N/A |  | TOWER LIGHT | Equipment | Equipment
298 | Encogroup | TOWER LIGHT -5 | #N/A |  | TOWER LIGHT | Equipment | Equipment

## April 2026
Name | ID # | Skill |  | 0
Aaisha Abdallah Said AL Balushi | 12704175 | Process Engineer
Abdullah Humaid Al Nofali | 27637114 | Junior PRO
Abdullah Khalfan Humaid Al Saidi | 7065269 | Lowbed Trailer Driver
Abhishek Kumar | 140545152 | Painter
Abhishek Kumar Tiwari | 140742144 | Helper
Abid Hussain | 112778626 | Crane Operator -150T
Abishek Pandey | 123487214
Adhikesavan Chandrasekaran | 141793239 | QC Document Controller
Adil | Not Required
Afaaq Hussain | 126724428 | Surveyor
Ahmad Kerbaj | 132915855 | Mechanical Supervisor
AHMED KHADEEM SAID AL TOURASHI | 19753414 | Bus Driver
Aiyaj Najirhussain Patel | AN071596 | Gas Cutter
Ajin Paramesvaran | 141377747 | Painter
Ajithkumar Aravindakshanpillai | 140693697 | HSE Officer
Akhilesh Kumar | 141359235 | Welder
Akhilesh Kumar | 122179745 | Fitter
Akhilesh Kumar-Welder | U4181508
Akram Hossain | 126825676 | Fitter
Akther Sanaulla | 89442153 | Fitter
Alamin Robeul Islam | 98021462 | Mechanical Foreman
Alamin Sheikh | 128486351 | Helper
Ali Haider | 100398391
Ali Riza | 140849254 | Construction Manager
Alla Said Abdallah Al Jabri | 12441043 | IT Engineer
Amal Kannoor Ramachandran | 141322485 | Electrical Engineer
Amdadul Haque | 131662411 | Helper
Ameer Ali | 125440631 | Rigger
Amit Gupta | 140844783 | Painter
Amna Aadil Khalaf Al-Marroushi | 14496555 | Admin Assistant
Amran Hamood Marhoon Al-Hashemi | 10612625 | Junior HSE Officer
Anandbabu subbiah | 81612139 | Mechanic
Aneesh Joseph | 141253376 | Store Keeper
Anil Baitha | AD797743 | Gas Cutter
Aravind Kumar Tiwari | 141818413 | Fitter
Arifur Rahman | 115731078 | Scaffolder
Arun Baby | 128954904 | Nurse
Arun Kumar | 123039392
Arunbhai Balubhai | 140764355 | Fitter/Erector
Arunkumar Kakkanad Chandran | 85213329 | Electrician
Arunkumar Surendran | 127859069 | QC Mechanical Engineer
Arunraj Rajendiren | 118833981 | Scheduler / Planning Engineer
Ashwani Kumar | 125199977 | Electrician
Ashwin Shivaraman | 127414586 | HSE Officer | #REF!
Ashwini Kumar | 127414586 | HSE Officer
Atif Rasheed | 127331574 | Permit Receiver
Azhar | not required
Azzam Ahmed | 124346519
Bader Al-Buloshi | 15290981 | Driver
Bader Nasser Said Masoud Al Nofali | 28065391 | Driver
Bal Krishna Bishwakarma | 122179637
Balister Yadav Yadav | 128660782 | Grinder
Balister Yadhav | S3549132
Balkishuan Muralidhar | 141365131 | Painter
Baraili Man Bahadur | 105610932 | Crane Operator
Basanthu Ram | 95128256 | Helper
Basheer Abubakkar | 141177603
Basheer Abubakkar | 14177603 | Crane Operator
Benny Thomas | 71437827 | Electrical Supervisor
Bhanu Kumar | 140848833
Bilal Rabi'a Al Rufa'i | 140741175 | CNC Operator Assistant
Biomanna Mohanan | -
Bittu Kumar | 140844604 | Painter
Bivishin Kumar Sing | 117058003 | Instrument fitter
Bul Bul Ahmed | 129082332 | Fitter
Cherbel Nabih Gebrael | 116894252 | Purchasing Manager
Clyde Abrazaldo | 141169085 | Welder
Daniel JR Mosiquira | 141169047 | Welder
Deepak Kumar | 140742125 | Helper
Deepu Chauhan | 117871996 | Electrical Supervisor
Dharmendra Kumar | 125199963 | Electrician
Dharmvir Upadhyay | 140844797 | Fitter/Erector
Dhinesh Vaithiyanathan | 140645388 | Store keeper
Didarul Alam Golam Rabbani | 121473076 | Helper
DILIP KUMAR (5042) | 113484195
Dinesh Yadav | 12284034
Dipu Sing | 140697025 | Helper
Duncan Lee Kelly | 141307968 | Mechanical Supervisor
Easak Sheikh | 126131237 | Fitter
Ebin Ben | 116589569 | Mechanical Engineer
Ejaz Hussein | 112952143 | HSE Coordinator
Elias Zaatar | 121594839 | Electrical Engineer
Emaran Hossain | 116836161 | Fitter
Emile Baradhi | 118041216 | Material Manager
Erick Atienza | 141169052 | Welder
Erwin Sandoval | 117210204 | Painting Foreman
Fadi Al Asmar | 140841472 | Electrical Superintendent
Fahad Ahmed Obaid Al Qaidi | 15169287 | Driver
Fatema Al Abri | 12782421 | Admin Assistant
Fawad Ahmed | 102607563
Fawaz Aamir Said Hamdoon Al-Naamani | 23659394 | Junior PRO
Felix George | 141809314 | Material Controller
Fenil Paul | 137098196 | Lifting engineer
Ganta Mohan Rady | AH746467 | Rigger
George Tcheroyan | 121598538 | Project Manager
George Zouhair Abi Farah | 121820536
Ghulam Qadir Muhammad Yousaf | 124398279 | Permit Receiver
Gokul Reghu | 123472431 | Site Coordinator / Timekeeper
Govind Sahani | 140844623 | Painter
Gulshan Gautham | 141365075 | Helper
Gulzar Singh | 79502392 | Crane Operator-150T Sany Crawler
Gurpreet Sing | 86971535 | Crane Operator | #REF!
Gurpreet Singh | 86971535 | Crane Operator
Gurtirath Singh | 114531608 | Crane Operator-150T Sany Crawler
Gyan Prakash Singh | 123487228 | Welder
Gyenendra Kumar Gupta | 140809004 | Fitter/Erector
Hadi Moussa | 141358993 | Fitter
Haleem Ansari | 140683436 | Scaffolder
Hamed Ali Sai al Washahi | 13513098 | Mechanical Engineer
Hamzha Khalid | 128926146 | Mechanical engineer
Hareendra Shahani | X6330749
Harpreet Singh | 78753612 | Crane Operator-70T
Hasan Mia | 125864032 | Fitter
Hassan Salah Mechhawi | 130805123 | Electrical Foreman
Hiralal Prasad Gupta | 141620935 | Mechanic
Hussain Bubal | 128621304 | Helper
Hussain Owayed | 141879726 | Mechanical Foreman
IBRAHIM KARAM ALI AL BALUSHI | 15485532 | Driver
Ibrahim Karime | 71257815 | Logistics Supervisor
Ibrahim Rashid Mubarak Al-Abri | 9138415 | Driver
Imaran Ahamad Taj Mohammad | 140954262
Imran Khan | 125287583
Iqbal Hossain | 89783691 | Fitter
Irfan Ansari | 78785394
Irshad Ejas Hussain Shaikh | #N/A
Ismail Moussa | 141359024 | Fitter
Jagger Arguila | 121974161 | Mechanic Forman
Jahir Islam | 91742907 | Fitter
Jaison Marottikkal Lorance | 120892366 | HSE Officer
Jaison Vijay Menezes | R3971143
Jaison Vijay Menezes | 141118698 | Mechanical Foreman
Jalaludeen S | 103199925
Jayakrishnan Chandrasekaran | 75199413 | Mechanic
Jean-Luc-Joseph | 140694441 | QC Manager
Jerin Madapilly Johnson | 117066499 | Mechanical Engineer
Jitendra Kumar Yadav | AG111207
Jitendra Kumar Yadav | 125258455 | Fitter
Jithendra Kumar Rauta | P2082614 | Fitter
Jitu Kumar | 140844759 | Welder
John Paul George | 141904019 | Electrician
Kadir Ansari | 140844778 | Painter
Kamal Kumar Sharma | 140848828 | Pipe Fitter
Kawanchal kumar | 116388526 | Painter
Kawsar Mahmud | 117827334 | Fitter
Khundrakpam Shyamsan Singh | 99596058 | HSE Officer
Lav Kansaraj | 140697039 | Fitter/Erector
Laxman Chaudhary | 117207568 | Electrician
Lema Kelly | 141307921 | Mechanical Assistant
Lokesh Gupta | 140696961 | Helper
Mahmoud Khoder Hassan | 140623599 | Mechanical Supervisor
Kamalesh Maddheshiya | 141914922 | Electrical Assistant
Mahmoud Khodr Hassan | 140623599 | Foreman | #REF!
Mahmoud Mohamad Moussa | 116858297 | Mechanical Superintendent
Mahmoud Moussa | 141358988 | Fitter
Manikandaraj Muthaia | 99112308 | HR Manager
Manjesh Bharti | 140696975 | Helper
Manoj Choudhary | 141502853 | Scaffolder
Manoj Kumar Ram | T2058009 | Mechanic
Mansur Malita | 91229515 | Crane Operator
Maroun Raymond Sarkis | 127387473 | Mechanical engineer
Maryam Abdallah Said Al Matrosushi | 14246361 | QS Engineer
Mathan Kumar | 140796986 | Mechanical QC
Mazin Abdullah Ali Al -Aisaee | 8125926 | Driver
Md Zafor | 134209579 | Helper
MD Abu Sarbath Ali | 97943625 | Helper
Md Ashik Mondol | 127487784 | Fitter
MD Ayub Ali | 108478006 | RIgger
Md Hasan Howlader | 115018512 | RIgger
MD Hasan Howlander | 115018512 | Rigger | #REF!
Md Humayun Kabir | 129416769 | Helper
MD Kamaluddin | 129670382 | Helper
Md Mahmudul Hasan | 108510173 | Helper
Md Moin Uddin | 128800506 | Helper
MD Rashed Mohammed | 140663253 | Painting Inspector
Md Rashed Mohmed | 140663253 | Painting Inspector | #REF!
MD Rizwan | #N/A
MD Sadiq | 123805496 | Fitter/Erector | #REF!
Md Sahadat | 132060253 | Helper
Md Sakanter Hossain | 132125723 | Helper
Md Shahid Ansari | P8996919
Md Shahin | 122761027 | Helper
MD shahnawaj Ahmed | 141402153 | Forklift Operator
Md Siddiqur Rahaman Md Ramizuddin | 123805496 | Fitter/Erector
Md Tarek Hossain | 114929202 | RIgger
Md Totul | 115122635 | Scaffolder
Mehdi Hasan | 127212203 | Fitter
Mhamed Sheikh | 122370101 | Quality Manager
Minto Das | 131777365 | Helper
Mohamed Irfan | 121937785 | Scaffolder | #REF!
Mohammad Jalal Uddin | 110117612 | Fitter
Mohammad Main Uddin | 103887648 | Helper
Mohammad Abulkasem Abdul Kader | 113921438 | Helper
Mohammad Alam | 85813175
Mohammad Ejaz Ansari | T0680335 | Electrician
Mohammad Ismail | 116448869
Mohammad Jakir Hossain | 94720515 | Fitter
Mohammad Jehangir Alam | 85812175 | Scaffolding Supervisor
Mohammad Khalfan Juma Al-Aufi | 1487544 | Driver
Mohammad Shahadat Hossain Sikdar | 95335424
Mohammad Shoaib Akhtar | 136277866 | Permit Receiver
Mohammad Shobuj Raza | 116109626 | Crane Operator
Mohammad Sonu | 141819561 | Electrician
Mohammed Abdullah Rashid Al Maamari | 8608865
Mohammed Akber | 116136586 | Fitter
Mohammed Attiq | 113787454 | Crane operator | #REF!
Mohammed Gias Uddin | 96409155 | Scaffolder
Mohammed Irfan | 121937785 | Scaffolding Inspector
Mohammed Khalifa Mohammed Al Jabri | 19323128 | Driver
Mohammed Mobin | 73507569 | Permit Receiver
Mohammed Rokan Mia | 105813698 | Scaffolding Inspector
Mohammed Rustam Ali Khan | R9967505 | Electrician
Mohammed Zahid | 141904038 | Electrician
Mohmmed Abdullah Ali Al-Aisaee | 10916249 | Mechanic
Moshin Saleem Salim AL-Shukaili | 14552941
Mostafa Khaled Fattouh | 140623552 | Mechanic
Motaseem Kariem | #N/A
Muhammad Attiq | 113787454 | Crane Operator
Muhammad Bilal Hussain Al Taf | 120653364 | Surveyor
Muhammad Zeeshan | 125440626
Muhammed Rafi | 135340657 | Forklift Operator
Muhammed Ramzan | 122179642
Muhammed Yasir | 118882687 | Permit Receiver
Mukesh Kumar Rai | 117974933 | Scaffolder
Mustafa Moosa Ahmed Al Balushi | 18114443 | Driver
Mustafa Moosa Ahned Al Balushi | 18114443 | Driver | #REF!
Nandana Kandoth Pariyali | AA231087 | Accountant
Nasr Nasser Said Masoud Al Nofli | 19110768 | Driver
Naveed Hussain | 131250286 | Helper
Nazrul Islam | 89847535 | Fitter
Neeraj Gautham | 140844586 | Helper
Nilesh Sharma | 117058093 | Instrument fitter
Omaima Sultan Saif Al- Busaidi | 12825038 | Admin Assistant
Omar Faruk Sarafat Ali | 106093463 | RIgger
Othman Mohammed Najman Al Zadjali | #N/A
Padmanaban Sevu | 77873529
Pappu Kumar Yadaw | 122082769 | Grinder
Peter Farah | 122045765 | Lead Mechanical Engineer
Pinto Kuriakose | 132423982 | Mechanic Supervisor | #REF!
Pinto Kuriakose | 132423982 | Mechanic Supervisor
Prabin Brnnet Rani | 140805592 | Helper
Pradeep Pandey | 122274652
Pradip Rai | 141365023 | Grinder
Praful Kumar Rai | 117020738
Pragat Sing | 141724889 | Crane Operator
Prakash Pandey | 140683371 | Rigger
Prasad Vadakkedath ME Ramankutty | 83070339 | HSE Engineer
Prathip Sundaram | 140995321 | Scheduling Engineer
Pravin Prakash Singh | 116902132 | Erector / Manlift Operator | #REF!
Praveen Singh | 122015438
Pravesh Kumar | 140844572 | Helper
Priyaranjan Kumar | 140844848 | Helper
Rabih Ali El Borji | 123541357 | Admin Manager
Rabih Rifai | 116915582 | Mechanical Superintendent
Rajeev Kumar Sadasivam | 141377771 | Painter
Rajeev Kumar Sah | 141359216 | Electrician
Rajesh Sadahanndan Pillai | 141381507 | HSE Manager
Rajesh Thakur | 124565057 | Fitter/Erector
Rajkumar Dubey | 140683399 | Rigger
Rakesh Radhakrishnan | 141745198 | Electrical QC Engineer
Ram Moorat Chandrabali | 141365061 | Helper
Ramesh Kumar | 141365056 | Fitter
Rampratap Chauhan | 112346941
Ranaanand Kumar | 140742088 | Fitter/Erector
Rashid | #N/A
Ravi Yadav | 141365164 | Helper
Raya Salim Khamis Said Al Junaibi | 14915995 | Admin Coordinator
Rejin Rebi | 140805554 | Helper
Renjith Kumar | 141377752 | Rigger
Renu Sutharshan | 122179623 | QC Mechanical Lead
Reymond Cruz | 141169033 | Welder
Rijo Pappachan Thankachan | 140477664 | Junior HSE Officer
Ripon Tofayel Ahmmad | 116676257 | Scaffolder
Robert Michel Salameh Haddad | 121736531 | Electrical Superintendent
Robul Hoque Abdul Bark | 104225357 | Helper
Rodie Jabber | 141505123 | Mechanical Engineer
Rogie JR Mabilog | 141169071 | Welding Supervisor
Ruhul Amin | 128627083 | Helper
Ryan Batuto | 141169028 | Fitter
Saddam Hussain | W3304280 | Mechanic
Said Helal Mohammed Al-Amri | #N/A
Said Hilal Mohammed ALAmri | 10974059 | Driver
Said Mohammed Said Al-Kaabi | 14793103 | Electrical Engineer
Saidul Sheikh | 115958227 | Fitter
Sajilal Sasidharan | 103717582 | Accountant
Sajith Saji Kanagam | 140805568 | Helper
Sakhawat Hussain | 76647648 | Rigger | #REF!
Sakhawat Hussain Muhammad Hussain | 76647648 | RIgger
Samanta Soumitra | 140846698 | Helper
Samar Habib | 141246094 | Mechanical Engineer
Sandeep Kumar Sugreev | 141365042 | Helper
Sandeep Kumar Yadhav | P6050502
Sandeep Yadav | 141804768 | Pipe Fitter
Sanjay Kumar Suresh Ram | 141365037 | Painter
Santhosh Kumar | 141804716
Santosh Kumar Yadav | 140848814 | Painter
Saqib Ali | 131431131 | RIgger
Sathishkumar Kasthurisamy | 140859482 | Draftsman Engineer
Sawar Khan | 122771611
Senthil Vel Sekar | 141228922 | Document controller
Shafiqe Tariqe | 102087073 | Permit Receiver
Shahzad Latif | 98845403 | Crane Operator-100T | #REF!
Shawaj Alam | 141179467 | Crane Operator
Sheikha Abdallah Said Al Matrosushi | 11196769 | HR Officer
Sheikha Rashid Saif Al Ghaithi | 12637107 | QS Engineer
Sheikha Rashid Saif-Al Ghaithi | 12637107 | Electrical Engineer | #REF!
Shijo Saji | 140696356 | Mechanical engineer
Shinu S | 109957631 | Crane Operator-130T
Shivam Yadhav | 141365126 | Helper
Shoaib Akhtar | 135762195 | HSE Officer
Shobuj Raza | #N/A
Shobul Rata | #N/A
Shoib Akhtar | 135762195 | HSE Officer | #REF!
Shyam Dhani | 140806218 | Fitter/Erector
Siyaram Yadav | 81379273 | Crane Operator
Sofikul Isalm | 131376633 | Helper
Sohan Gupta | 140806191
Solaiman Abul Bashar | 118046382 | Helper
Sonu Kumar Pandey | 140764706 | Rigger
Sreejith Satheesh kumar | 141809441 | Arc Welder
Sreejith Thekkedath Sivaraman | 141322471 | Welding Inspector
Subash H.K | 83935096
Subodh Sah | S8474313
Sujeet Kumar | 140742177 | Grinder
Sujon Sarkar | 131137678 | Helper
Sulthan Humaid Mohammed Humaid Al Nofli | 19255078 | Driver
Suman Kumar Mandal | 116853914 | Electrical Supervisor
Surajit Maity | 140846684 | Helper
Suresh Selvam | 141377709
Syed Mamunur Rashid | 89362471 | Fitter
Syed Ihsan Haider | 100398391
Syed Ishan Haider | 100398341 | Trailer Driver
Syed Mohammed | 101712007 | Trailer Driver
Tamilselvan Tamilmani | 141250908 | Mechanical Engineer
Tamoor Ali Khan | 135325259 | Permit Receiver
Tanveer | #N/A
Tej Pradap Sharma | 141365089 | Fitter
Triloki Nath | 141817533 | Pipe Fitter
Umar Gull | 137353583 | Permit Receiver
Umesh Kumar | 96405686
Umesh Singh | 137114773 | Rigger
Venkatesh Annapu | 84357232
Verendra Kumar Hari Lal | 140844618 | Helper
Vicken Tcheroyan | 121668462 | Site Manager
Vijai Kumar Yadhav | 123039387
Vijay Kumar Muthu | 141377714 | Painter
Vijay Prasad | 141819542 | Cable Tray Fitter
Vijaya Kumar (5036) | 71345102
Vinay Chaudhary | 122179604 | Fitter/Erector
Vinod Kumar | 122082863 | Grinder
Vivek Kumar | 140696989 | Electrician
Wesley Jan Estandarte | 117255966 | Mechanical Supervisor
Yam Kumar Rai | 131000987 | Electrician
Yogendra Kumar Rupachand | 141365094 | Helper
Zain Ul Abdin | 124233837 | Trailer Driver
Zakar Hossain | 131968269 | Fitter
#REF!
#REF!
#REF!